## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Alameda County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
ALA | 2113A |  | Alameda Contra Costa Transit District | RIP | 0 | 628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628 | 0 | 0 | 0 | 0 | [9 empty] | 628 | [38 empty] | 10600000446 | RIP |  |  |  |  | 0 | 0 | 1256 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1256 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B000BA |  | AC Transit Bus Engine Transmission Rehab | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (LTF) | 3091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3091 | 0 | 0 | 0 | 0 | [8 empty] | 3091 | [39 empty] | 0 | [5 empty] | 6182 | 6182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3091 | 3091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 3091 | 628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3719 | 0 | 0 | 0 | 0 | [48 empty] | 0
ALA | 2009A |  | Alameda Contra Costa Transit District | Othr. State | 0 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 0 | 0 | 0 | 0 | [9 empty] | 481 | [38 empty] | 20600002155 | [5 empty] | 0 | 0 | 962 | 962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 962 | 962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | AC Transit Maintenance Facilities Upgrad | RIP | 0 | 0 | 0 | 0 | 0 | 3705 | 0 | 0 | 0 | 3705 | 0 | 0 | 0 | 0 | [13 empty] | 3705 | [34 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7410 | 7410 | 0 | 0 | 0 | 0 | 0 | 0 | 22230 | 22230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 481 | 0 | 0 | 0 | 3705 | 0 | 0 | 0 | 4186 | 0 | 0 | 0 | 0 | [48 empty] | 0
ALA | 2009B |  | Alameda Contra Costa Transit District | Othr. State | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | [9 empty] | 111 | [38 empty] | 20600002156 | [5 empty] | 0 | 0 | 222 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | AC Transit SATCOM Expansion | RIP | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | [13 empty] | 1000 | [34 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 111 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1111 | 0 | 0 | 0 | 0 | [48 empty] | 0
ALA | 2009C |  | Alameda Contra Costa Transit District | Othr. State | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | [25 empty] | 350 | [22 empty] | 20600002157 | [5 empty] | 0 | 0 | 1400 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 0 | 0
|  | 0.0 | Berkeley/Oakland/S.Leandro Corr MIS Study | RIP | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 0 | [27 empty] | 2700 | [20 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 10800 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 350 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3050 | 0 | 0 | [48 empty] | 0
ALA | 2009D |  | Alameda Contra Costa Transit District | Othr. State | 0 | 1105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1105 | 0 | 0 | 0 | 0 | [9 empty] | 1105 | [38 empty] | 20600002159 | [5 empty] | 0 | 0 | 2210 | 2210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2210 | 2210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Bus Component Rehabilitation | RIP | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 0 | 0 | 0 | 0 | [10 empty] | 8500 | [37 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 17000 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25500 | 25500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 1105 | 8500 | 0 | 0 | 0 | 0 | 0 | 0 | 9605 | 0 | 0 | 0 | 0 | [48 empty] | 0
ALA | 1015 |  | Alameda County | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10600000723 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073134 |  | Crow Canyon Road Safety Improvements | Future Need | 0 | 1050 | 2800 | 0 | 0 | 0 | 0 | 0 | 1050 | 2800 | 0 | 0 | 0 | 0 |  | 1050 | [8 empty] | 2800 | [37 empty] | 0 | [5 empty] | 0 | 0 | 1050 | 1050 | 5600 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CO) | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | [27 empty] | 450 | [20 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 1050 | 2800 | 450 | 0 | 0 | 0 | 0 | 1050 | 2800 | 0 | 450 | 0 | 0 | [48 empty] | 0
ALA | 2179 |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10600000530 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073414 |  | Planning, Programming and Monitoring | Loc Funds (CO) | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | [10 empty] | 112 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 224 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336 | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | [48 empty] | 0
ALA | 2179A |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | [11 empty] | 112 | [36 empty] | 10600000964 | RIP |  | X |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448 | 448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AB 3090 Replacement Project | TOTAL | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 1015A |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | [11 empty] | 450 | [36 empty] | 10600000965 | RIP |  | X |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AB 3090 Replacement Project | TOTAL | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 2020A |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 890 | 0 | 0 | 0 | 0 | 0 | 890 | 0 | 0 | 0 | 0 | [11 empty] | 890 | [36 empty] | 10600000966 | RIP |  | X |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1780 | 1780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3560 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AB 3090 Replacement Project | TOTAL | 0 | 0 | 0 | 890 | 0 | 0 | 0 | 0 | 0 | 890 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 2009T |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | [11 empty] | 630 | [36 empty] | 10600000967 | RIP |  | X |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AB 3090 Replacement Project | TOTAL | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 2009U |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | [11 empty] | 405 | [36 empty] | 10600000968 | RIP |  | X |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 810 | 810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1620 | 1620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AB 3090 Replacement Project | TOTAL | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | 0 | 405 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 2198A |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | [11 empty] | 240 | [36 empty] | 10600000970 | RIP |  | X |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AB 3090 Replacement Project | TOTAL | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 0016Q |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 25037 | 0 | 0 | 0 | 0 | 0 | 25037 | 0 | 0 | 0 | 0 | [11 empty] | 25037 | [36 empty] | 10600000972 | RIP |  | X |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50074 | 50074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100148 | 100148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AB 3090 Replacement Project | TOTAL | 0 | 0 | 0 | 25037 | 0 | 0 | 0 | 0 | 0 | 25037 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 0016R |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | [11 empty] | 11800 | [36 empty] | 10600000975 | RIP | X |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 23600 | 23600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47200 | 47200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | AB 3090 Reimbursement | TOTAL | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 2009L |  | Alameda County Congestion Management Agency | RIP | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | [11 empty] | 1400 | [36 empty] | 20600002167 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Vasco Road Safety Improvements | RIP (CC ) | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | [11 empty] | 2500 | [36 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TCRP | 150 | 1170 | 5180 | 0 | 0 | 0 | 0 | 0 | 1170 | 5180 | 150 | 0 | 0 | 0 |  | 1170 | [8 empty] | 5180 | [5 empty] | 150 | [31 empty] | 0 | [5 empty] | 450 | 450 | 1170 | 1170 | 10360 | 10360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 2340 | 15540 | 15540 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (GEN) | 837 | 0 | 2263 | 0 | 0 | 0 | 0 | 0 | 0 | 2263 | 337 | 500 | 0 | 0 | [10 empty] | 2263 | [5 empty] | 337 | [7 empty] | 500 | [23 empty] | 0 | [5 empty] | 3011 | 3011 | 0 | 0 | 4526 | 4526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6789 | 6789 | 337 | 337 | 500 | 500 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 987 | 1170 | 7443 | 3900 | 0 | 0 | 0 | 0 | 1170 | 11343 | 487 | 500 | 0 | 0 | [48 empty] | 0
ALA | 2009N |  | Alameda, City of | RIP | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | [13 empty] | 4000 | [34 empty] | 20600000655 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Tinker Avenue Extension | Federal Disc. | 0 | 9600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9600 | 0 | 0 | 0 | 0 | [9 empty] | 9600 | [38 empty] | 0 | [5 empty] | 0 | 0 | 19200 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19200 | 19200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (GEN) | 2560 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 350 | 60 | 700 | 0 | 0 | 1800 | [8 empty] | 350 | [6 empty] | 60 | [7 empty] | 700 | [23 empty] | 0 | [5 empty] | 4780 | 4780 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 700 | 700 | 60 | 60 | 700 | 700 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 2560 | 9950 | 0 | 0 | 0 | 4000 | 0 | 0 | 1800 | 13950 | 60 | 700 | 0 | 0 | [48 empty] | 0
ALA | 2103 |  | Bay Area Rapid Transit District | RIP | 0 | 0 | 7200 | 0 | 0 | 15800 | 0 | 0 | 0 | 23000 | 0 | 0 | 0 | 0 | [10 empty] | 7200 |  |  | 15800 | [34 empty] | 10600000112 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 14400 | 14400 | 0 | 0 | 0 | 0 | 31600 | 31600 | 0 | 0 | 0 | 0 | 0 | 0 | 116400 | 116400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| R735SA |  | BART Oakland Airport Connector - PA&ED | IIP | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | [10 empty] | 10000 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (GEN) | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | [9 empty] | 100000 | [38 empty] | 0 | [5 empty] | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 100000 | 17200 | 0 | 0 | 15800 | 0 | 0 | 0 | 133000 | 0 | 0 | 0 | 0 | [48 empty] | 0
ALA | 2009H |  | Bay Area Rapid Transit District | FTA Funds | 217057 | 21564 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 238956 | 0 | 0 | 0 | 0 | [8 empty] | 217057 | 21564 | 335 | [37 empty] | 20600000214 | [5 empty] | 434114 | 434114 | 43128 | 43128 | 670 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 261190 | 261190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | BART A and B Car Rehabilitation | Othr. State | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 0 | 0 | 0 | 0 | [8 empty] | 36000 | [39 empty] | 0 | [5 empty] | 72000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | RIP | 0 | 0 | 0 | 0 | 6995 | 0 | 0 | 0 | 0 | 6995 | 0 | 0 | 0 | 0 | [12 empty] | 6995 | [35 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13990 | 13990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34975 | 34975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | RSTP | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | [8 empty] | 15000 | [39 empty] | 0 | [5 empty] | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (FARE) | 137924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137924 | 0 | 0 | 0 | 0 | [8 empty] | 137924 | [39 empty] | 0 | [5 empty] | 275848 | 275848 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137924 | 137924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 405981 | 21564 | 335 | 0 | 6995 | 0 | 0 | 0 | 0 | 434875 | 0 | 0 | 0 | 0 | [48 empty] | 0
ALA | 2009G |  | Bay Area Rapid Transit District | FTA Funds | 1977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 0 | 0 | 0 | 0 | [8 empty] | 1977 | [39 empty] | 20600001016 | [5 empty] | 3954 | 3954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1977 | 1977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | BART Stations Platform Edge Tiles | RIP | 0 | 0 | 0 | 0 | 0 | 1248 | 0 | 0 | 0 | 1248 | 0 | 0 | 0 | 0 | [13 empty] | 1248 | [34 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2496 | 2496 | 0 | 0 | 0 | 0 | 0 | 0 | 7488 | 7488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | RSTP | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 0 | 54 | 0 | 0 | [8 empty] | 716 | [15 empty] | 54 | [23 empty] | 0 | [5 empty] | 1648 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 716 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (FARE) | 594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587 | 0 | 7 | 0 | 0 | [8 empty] | 587 | [15 empty] | 7 | [23 empty] | 0 | [5 empty] | 1202 | 1202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 587 | 587 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 3341 | 0 | 0 | 0 | 0 | 1248 | 0 | 0 | 0 | 4528 | 0 | 61 | 0 | 0 | [48 empty] | 0
ALA | 2009E |  | Bay Area Rapid Transit District | RIP | 0 | 0 | 0 | 0 | 2283 | 0 | 0 | 0 | 0 | 2283 | 0 | 0 | 0 | 0 | [12 empty] | 2283 | [35 empty] | 20600002160 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4566 | 4566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11415 | 11415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | BART Automatic Fare Collection Moderniza | TOTAL | 0 | 0 | 0 | 0 | 2283 | 0 | 0 | 0 | 0 | 2283 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 2009F |  | Bay Area Rapid Transit District | RIP | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | [13 empty] | 2000 | [34 empty] | 20600002161 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | BART Lake Merritt Channel Subway Repair | Loc Funds (GEN) | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | [24 empty] | 500 | [23 empty] | 0 | [5 empty] | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 500 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 500 | 0 | 0 | [48 empty] | 0
ALA | 2020 |  | Emeryville, City of | RIP | 0 | 0 | 0 | 0 | 0 | 2110 | 0 | 0 | 0 | 2110 | 0 | 0 | 0 | 0 | [13 empty] | 2110 | [34 empty] | 10600000907 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4220 | 4220 | 0 | 0 | 0 | 0 | 0 | 0 | 12660 | 12660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.5/4.5 | Emeryville Intermodal Transfer Station | IIP | 0 | 0 | 0 | 1200 | 3000 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | [11 empty] | 1200 | 3000 | [35 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2400 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19800 | 19800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 7390 | 0 | 0 | 7390 | 0 | 0 | 0 | 0 | [14 empty] | 7390 | [33 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14780 | 14780 | 0 | 0 | 0 | 0 | 51730 | 51730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (CITY) | 100 | 110 | 0 | 890 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 1000 | 0 | 0 | [16 empty] | 100 | [8 empty] | 110 |  | 890 | [20 empty] | 0 | [5 empty] | 300 | 300 | 440 | 440 | 0 | 0 | 3560 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 3780 | 3780 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 100 | 110 | 0 | 2090 | 3000 | 2110 | 7390 | 0 | 0 | 13700 | 100 | 1000 | 0 | 0 | [48 empty] | 0
ALA | 2009M |  | Emeryville, City of | RIP | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 1900 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1900 | [44 empty] | 20600002168 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1900 | 1900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7600 | 7600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Mandela Parkway Extension Phase II | Future Need | 0 | 0 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 740 | 0 | 0 | 0 | 0 | [11 empty] | 740 | [36 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1480 | 1480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2960 | 2960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CITY) | 0 | 110 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 110 | 0 | 0 |  |  |  | 50 | [21 empty] | 110 | [22 empty] | 0 | [5 empty] | 0 | 0 | 440 | 440 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 220 | 220 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 110 | 0 | 2690 | 0 | 0 | 0 | 0 | 1950 | 740 | 0 | 110 | 0 | 0 | [48 empty] | 0
ALA | 2109 |  | Fremont, City of | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10600000118 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0U0501 |  | Washington/Paseo Padre Grade Separation | Loc Funds (CITY) | 16392 | 0 | 34554 | 2318 | 0 | 0 | 0 | 0 | 13059 | 37195 | 230 | 2780 | 0 | 0 | 13059 | [7 empty] | 323 |  | 34554 | 2318 |  |  |  |  | 230 | [7 empty] | 2780 | [23 empty] | 0 | [5 empty] | 25515 | 25515 | 0 | 0 | 69108 | 69108 | 4636 | 4636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13059 | 13059 | 113257 | 113257 | 230 | 230 | 2780 | 2780 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 16392 | 0 | 34554 | 2318 | 0 | 0 | 0 | 0 | 13059 | 37195 | 230 | 2780 | 0 | 0 | [48 empty] | 0
ALA | 2009K |  | Livermore Amador Valley Transit District | FTA Funds | 0 | 1400 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 1400 | 0 | 0 | 0 | [10 empty] | 2600 | [6 empty] | 1400 | [30 empty] | 10600000455 | [5 empty] | 0 | 0 | 4200 | 4200 | 5200 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | 7800 | 2800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | LAVTA Satellite Bus Operating Facility Exp. | RIP | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | [13 empty] | 4000 | [34 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (TDA4) | 5600 | 0 | 4400 | 0 | 0 | 0 | 0 | 0 | 5600 | 4400 | 0 | 0 | 0 | 0 | 5600 | [9 empty] | 4400 | [37 empty] | 0 | [5 empty] | 5600 | 5600 | 0 | 0 | 8800 | 8800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 5600 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 5600 | 1400 | 7000 | 0 | 0 | 4000 | 0 | 0 | 5600 | 11000 | 1400 | 0 | 0 | 0 | [48 empty] | 0
ALA | 2100 |  | Metropolitan Transportation Commission | RIP | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | [10 empty] | 86 | [37 empty] | 10600000109 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 172 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073324 |  | Planning, Programming and Monitoring | TOTAL | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 2159 |  | Metropolitan Transportation Commission | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10600000126 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 072124 |  | CMAQ Match Reserve | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 1022 |  | Oakland, City of | RIP | 0 | 0 | 0 | 0 | 0 | 3130 | 0 | 0 | 3130 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3130 | [42 empty] | 10600000722 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3130 | 3130 | 0 | 0 | 0 | 0 | 18780 | 18780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 072584 |  | 42nd Ave/High St Access to I-880 | Future Need | 0 | 0 | 0 | 0 | 0 | 5100 | 4870 | 0 | 0 | 9970 | 0 | 0 | 0 | 0 | [13 empty] | 5100 | 4870 | [33 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10200 | 10200 | 9740 | 9740 | 0 | 0 | 0 | 0 | 64690 | 64690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CITY) | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | [16 empty] | 800 | [31 empty] | 0 | [5 empty] | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 800 | 0 | 0 | 0 | 0 | 8230 | 4870 | 0 | 3130 | 9970 | 800 | 0 | 0 | 0 | [48 empty] | 0
ALA | 2110 |  | Union City, City of | RIP | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | [27 empty] | 3300 | [20 empty] | 10600000119 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13200 | 13200 | 0 | 0 | 0 | 0
| R738SA |  | Union City Intermodal Station | Future Need | 0 | 0 | 0 | 7100 | 0 | 0 | 0 | 0 | 7100 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7100 | [44 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7100 | 7100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28400 | 28400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (GEN) | 1229 | 3180 | 7227 | 0 | 0 | 0 | 0 | 0 | 450 | 7227 | 1229 | 2730 | 0 | 0 |  | 450 | [8 empty] | 7227 | [5 empty] | 1229 | [8 empty] | 2730 | [22 empty] | 0 | [5 empty] | 3687 | 3687 | 11370 | 11370 | 14454 | 14454 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 | 21681 | 21681 | 1229 | 1229 | 5460 | 5460 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (LTF) | 0 | 0 | 10673 | 0 | 0 | 0 | 0 | 0 | 0 | 10673 | 0 | 0 | 0 | 0 | [10 empty] | 10673 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 21346 | 21346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32019 | 32019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 1229 | 3180 | 17900 | 10400 | 0 | 0 | 0 | 0 | 7550 | 17900 | 1229 | 6030 | 0 | 0 | [48 empty] | 0
ALA | 0096A | 238 | Caltrans | RIP | 6846 | 0 | 0 | 0 | 28213 | 0 | 0 | 0 | 225 | 24832 | 1704 | 4640 | 277 | 3381 | 225 | [11 empty] | 24832 |  |  |  | 1704 | [7 empty] | 4640 | [7 empty] | 277 | [11 empty] | 3381 |  |  |  | 10600000161 | RIP |  |  |  | X | 25282 | 25282 | 0 | 0 | 0 | 0 | 0 | 0 | 69950 | 69950 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 225 | 124160 | 124160 | 1704 | 1704 | 4640 | 4640 | 277 | 277 | 16905 | 16905
| 249000 | 22.9/26.9 | Route 238 Northbound Widening | TOTAL | 6846 | 0 | 0 | 0 | 28213 | 0 | 0 | 0 | 225 | 24832 | 1704 | 4640 | 277 | 3381 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 0117 | 580 | Caltrans | RIP | 670 | 133 | 941 | 0 | 0 | 0 | 0 | 0 | 131 | 737 | 127 | 543 | 2 | 204 |  | 131 | [8 empty] | 737 | [5 empty] | 127 | [7 empty] | 543 | [8 empty] | 2 | [8 empty] | 204 | [5 empty] | 10600000718 | RIP |  |  |  | X | 2553 | 2553 | 141 | 141 | 2698 | 2698 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 262 | 2211 | 2211 | 127 | 127 | 543 | 543 | 4 | 4 | 612 | 612
| 28390K | 10.3/10.5 | Livermore WB I-580 Noise Barrier | TOTAL | 670 | 133 | 941 | 0 | 0 | 0 | 0 | 0 | 131 | 737 | 127 | 543 | 2 | 204 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 0139B | 580 | Caltrans | RIP | 400 | 600 | 130 | 0 | 0 | 5150 | 0 | 0 | 100 | 4500 | 0 | 1000 | 30 | 650 |  |  | 100 | [10 empty] | 4500 | [10 empty] | 400 | 600 | [8 empty] | 30 | [10 empty] | 650 |  |  | 10600000777 | RIP |  |  |  | X | 1600 | 1600 | 2400 | 2400 | 250 | 250 | 0 | 0 | 0 | 0 | 12900 | 12900 | 0 | 0 | 0 | 0 | 300 | 300 | 27000 | 27000 | 0 | 0 | 1600 | 1600 | 90 | 90 | 3900 | 3900
| 126200 | 33.5/34.6 | San Leandro I-580 Noise Barrier | TOTAL | 400 | 600 | 130 | 0 | 0 | 5150 | 0 | 0 | 100 | 4500 | 0 | 1000 | 30 | 650 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 0148A | 580 | Caltrans | RIP | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 73 | 10 | 0 | [17 empty] | 39 | [7 empty] | 73 | [7 empty] | 10 | [14 empty] | 20600002171 | RIP |  |  |  | X | 0 | 0 | 459 | 459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 78 | 146 | 146 | 20 | 20 | 0 | 0
|  | 42.2/41.7 | I-580 Eastbound Oakland 14th/Ardley Nois | Future Need | 0 | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 24 | 483 | 0 | 0 | 0 | 73 |  |  |  | 24 | [7 empty] | 483 | [31 empty] | 73 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1428 | 1428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 96 | 1932 | 1932 | 0 | 0 | 0 | 0 | 0 | 0 | 292 | 292
|  | Change Reason ==> |  | TOTAL | 0 | 122 | 0 | 580 | 0 | 0 | 0 | 0 | 24 | 483 | 39 | 73 | 10 | 73 | [48 empty] | 0
ALA | 0069F | 80 | Caltrans | RIP | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | [16 empty] | 500 | [31 empty] | 10600000444 | RIP |  |  |  | X | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0
| 256200 | 4.2/4.8 | Ashby/Bay Interchange (environmental) | TOTAL | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 0069N | 80 | Caltrans | RIP | 0 | 0 | 0 | 0 | 0 | 2986 | 0 | 0 | 0 | 2554 | 0 | 251 | 0 | 181 | [13 empty] | 2554 | [15 empty] | 251 | [15 empty] | 181 |  |  | 10600000926 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7198 | 7198 | 0 | 0 | 0 | 0 | 0 | 0 | 15324 | 15324 | 0 | 0 | 1506 | 1506 | 0 | 0 | 1086 | 1086
| 180021 | 4.7/5.5 | I-80 Berkeley Aquatic Park Noise Barrier | TOTAL | 0 | 0 | 0 | 0 | 0 | 2986 | 0 | 0 | 0 | 2554 | 0 | 251 | 0 | 181 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
ALA | 0081D | 84 | Caltrans | RIP | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | [12 empty] | 10000 | [35 empty] | 10600000445 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 233030 | 6.9/10.8 | New Route 84 4-lane Expressway | Loc Funds (CO) | 0 | 0 | 0 | 0 | 46000 | 0 | 0 | 0 | 0 | 46000 | 0 | 0 | 0 | 0 | [12 empty] | 46000 | [35 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92000 | 92000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 230000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | 56000 | 0 | 0 | 0 | 0 | [48 empty] | 0
ALA | 1017 | 84 | Caltrans | RIP | 175 | 480 | 280 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 280 | 375 | 30 | 0 |  |  | 250 | [13 empty] | 175 | 105 | [7 empty] | 375 | [8 empty] | 30 | [13 empty] | 10600000746 | RIP |  |  |  | X | 525 | 525 | 1815 | 1815 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 0 | 0 | 385 | 385 | 750 | 750 | 90 | 90 | 0 | 0
| 44400K | 4.9/5.9 | Route 84 Westbound HOV Lane Extension | Future Need | 0 | 0 | 3700 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 0 | 0 | 0 | 400 | [10 empty] | 3300 | [31 empty] | 400 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200
|  | Change Reason ==> |  | TOTAL | 175 | 480 | 3980 | 0 | 0 | 0 | 0 | 0 | 250 | 3300 | 280 | 375 | 30 | 400 | [48 empty] | 0
ALA | 1018 | 84 | Caltrans | RIP | 175 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 175 | 300 | 30 | 0 |  | 250 | [14 empty] | 175 | [8 empty] | 300 | [7 empty] | 30 | [14 empty] | 10600000747 | RIP |  |  |  | X | 525 | 525 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 175 | 175 | 600 | 600 | 60 | 60 | 0 | 0
| 443901 | 4.4/4.9 | Route 84 WB HOV On-Ramp | Future Need | 0 | 0 | 0 | 3150 | 0 | 0 | 0 | 0 | 0 | 2800 | 0 | 0 | 0 | 350 | [11 empty] | 2800 | [31 empty] | 350 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7700 | 7700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11200 | 11200 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 1400
|  | Change Reason ==> |  | TOTAL | 175 | 580 | 0 | 3150 | 0 | 0 | 0 | 0 | 250 | 2800 | 175 | 300 | 30 | 350 | [48 empty] | 0
ALA | 0042C | 880 | Caltrans | RIP | 6223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3608 | 2615 | 0 | 0 | [16 empty] | 3608 | [7 empty] | 2615 | [23 empty] | 10600000173 | RIP |  |  |  | X | 21284 | 21284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3608 | 3608 | 2615 | 2615 | 0 | 0 | 0 | 0
| 260000 | 27.7/32.2 | 880 Broadway/Jackson Interchange | Future Need | 0 | 0 | 75 | 19704 | 0 | 0 | 0 | 0 | 357 | 17491 | 0 | 0 | 75 | 1856 |  |  |  | 357 | [7 empty] | 17491 | [22 empty] | 75 | [8 empty] | 1856 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 375 | 375 | 46475 | 46475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428 | 1428 | 69964 | 69964 | 0 | 0 | 0 | 0 | 225 | 225 | 7424 | 7424
|  | Change Reason ==> |  | TOTAL | 6223 | 0 | 75 | 19704 | 0 | 0 | 0 | 0 | 357 | 17491 | 3608 | 2615 | 75 | 1856 | [48 empty] | 0
ALA | 0016S | 880 | Caltrans | RIP | 0 | 0 | 0 | 0 | 400 | 3240 | 0 | 0 | 0 | 2940 | 50 | 350 | 0 | 300 | [13 empty] | 2940 | [6 empty] | 50 | [7 empty] | 350 | [16 empty] | 300 |  |  | 10600000963 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550 | 1550 | 7680 | 7680 | 0 | 0 | 0 | 0 | 0 | 0 | 17640 | 17640 | 250 | 250 | 1750 | 1750 | 0 | 0 | 1800 | 1800
| 2332A1 | 0.0/2.9 | Route 880 Landscaping | TOTAL | 0 | 0 | 0 | 0 | 400 | 3240 | 0 | 0 | 0 | 2940 | 50 | 350 | 0 | 300 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
|  |  |  | Total RIP | 14989 | 2543 | 17137 | 48864 | 47891 | 48369 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 14764 | 02/03: 1534
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 225 | 02/03: 381
|  |  |  | Total RIP Eligible for Reprogramming | 0 | 628 | 17137 | 37064 | 47891 | 48369 | 0 | 0
[8 empty] | 54829 | 47891 | 48369