## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Butte County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
BUT | 1L43 |  | Butte County | RIP | 70 | 20 | 792 | 0 | 0 | 0 | 0 | 0 | 20 | 792 | 0 | 70 | 0 | 0 |  | 20 | [8 empty] | 792 | [13 empty] | 70 | [23 empty] | 10200000056 | RIP |  |  |  |  | 280 | 280 | 20 | 20 | 1584 | 1584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 2376 | 2376 | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 0
| 0L0174 |  | Keefer Road Rehab. | TOTAL | 70 | 20 | 792 | 0 | 0 | 0 | 0 | 0 | 20 | 792 | 0 | 70 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 1L44 |  | Butte County | RIP | 0 | 0 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | [13 empty] | 1150 | [34 empty] | 10200000057 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 6900 | 6900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 453384 |  | Butte Creek Bridge | Local HBRR | 400 | 40 | 0 | 0 | 0 | 5200 | 0 | 0 | 40 | 5200 | 20 | 380 | 0 | 0 |  | 40 | [11 empty] | 5200 |  |  | 20 | [7 empty] | 380 | [23 empty] | 0 | [5 empty] | 1580 | 1580 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 10400 | 10400 | 0 | 0 | 0 | 0 | 80 | 80 | 31200 | 31200 | 20 | 20 | 380 | 380 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (LTF) | 5 | 10 | 0 | 0 | 0 | 150 | 0 | 0 | 10 | 150 | 5 | 0 | 0 | 0 |  | 10 | [11 empty] | 150 |  |  | 5 | [31 empty] | 0 | [5 empty] | 15 | 15 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 20 | 20 | 900 | 900 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 405 | 50 | 0 | 0 | 0 | 6500 | 0 | 0 | 50 | 6500 | 25 | 380 | 0 | 0 | [48 empty] | 0
BUT | 1L47 |  | Butte County | RIP | 3060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 2967 | 0 | 0 | 0 | 0 | 93 | [7 empty] | 2967 | [39 empty] | 10200000059 | RIP |  |  |  |  | 6027 | 6027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 93 | 2967 | 2967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 454364 |  | West Eighth Avenue Reconstruction | Loc Funds (CITY) | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 90 | 150 | 0 | 0 | 92 | [15 empty] | 90 | [7 empty] | 150 | [23 empty] | 0 | [5 empty] | 962 | 962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 92 | 0 | 0 | 90 | 90 | 150 | 150 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 3392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 2967 | 90 | 150 | 0 | 0 | [48 empty] | 0
BUT | 2L91 |  | Butte County | RIP | 0 | 69 | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 0 | 69 | 0 | 0 | [10 empty] | 462 | [14 empty] | 69 | [22 empty] | 10200000069 | RIP |  |  |  |  | 0 | 0 | 276 | 276 | 924 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386 | 1386 | 0 | 0 | 138 | 138 | 0 | 0 | 0 | 0
| 0L0574 |  | Entler Avenue Rehabilitation | TOTAL | 0 | 69 | 462 | 0 | 0 | 0 | 0 | 0 | 0 | 462 | 0 | 69 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 2L93 |  | Butte County | RIP | 0 | 610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 0 | [9 empty] | 610 | [38 empty] | 10200000071 | RIP |  |  |  |  | 0 | 0 | 1220 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 454214 |  | Neal Road Reconstruction | TOTAL | 0 | 610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 2L94 |  | Butte County | RIP | 85 | 1015 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 965 | 0 | 85 | 0 | 0 |  | 50 | [7 empty] | 965 | [14 empty] | 85 | [23 empty] | 10200000072 | RIP |  |  |  |  | 340 | 340 | 1980 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 1930 | 1930 | 0 | 0 | 85 | 85 | 0 | 0 | 0 | 0
| 454244 |  | Oroville Bangor Highway Reconstruction | TOTAL | 85 | 1015 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 965 | 0 | 85 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 2L98 |  | Butte County | RIP | 0 | 235 | 235 | 0 | 0 | 0 | 0 | 0 | 200 | 235 | 0 | 35 | 0 | 0 |  | 200 | [8 empty] | 235 | [14 empty] | 35 | [22 empty] | 10200000076 | RIP |  |  |  |  | 0 | 0 | 340 | 340 | 470 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 705 | 705 | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 0
| 0L0734 |  | Speedway Avenue Extension | TOTAL | 0 | 235 | 235 | 0 | 0 | 0 | 0 | 0 | 200 | 235 | 0 | 35 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 0L16 |  | Butte County Association of Governments | RIP | 0 | 0 | 55 | 55 | 54 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | [10 empty] | 55 | 55 | 54 | [35 empty] | 10200000020 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 110 | 110 | 110 | 110 | 108 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 655 | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0L0634 |  | Plan, program and monitor | TOTAL | 0 | 0 | 55 | 55 | 54 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 3L75 |  | Butte County Association of Governments | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10200000118 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0L0124 |  | FH 171 Widening from Inskip to Butte Meadows | Future Need | 0 | 0 | 798 | 1596 | 0 | 6120 | 0 | 0 | 798 | 5322 | 0 | 798 | 798 | 798 |  |  |  | 798 | [9 empty] | 5322 | [12 empty] | 798 | [8 empty] | 798 | [9 empty] | 798 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 3192 | 3192 | 4788 | 4788 | 0 | 0 | 15432 | 15432 | 0 | 0 | 0 | 0 | 3192 | 3192 | 31932 | 31932 | 0 | 0 | 2394 | 2394 | 3192 | 3192 | 4788 | 4788
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 798 | 1596 | 0 | 6120 | 0 | 0 | 798 | 5322 | 0 | 798 | 798 | 798 | [48 empty] | 0
BUT | 1L24 |  | Paradise, City of | RIP | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607 | 0 | 0 | 0 | 0 | [8 empty] | 607 | [39 empty] | 10200000045 | RIP |  |  |  |  | 1214 | 1214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607 | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 453504 |  | Clark/Skyway Safety Improv, Add Signals | Loc Funds (LTF) | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 20 | 10 | 10 | 0 | 0 | 100 | [7 empty] | 20 | [7 empty] | 10 | [7 empty] | 10 | [23 empty] | 0 | [5 empty] | 210 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 20 | 20 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 627 | 10 | 10 | 0 | 0 | [48 empty] | 0
BUT | 2L114 |  | Paradise, City of | RIP | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 0 | 0 | 0 | 0 | [9 empty] | 195 | [38 empty] | 10200000092 | RIP |  |  |  |  | 0 | 0 | 390 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0L0034 |  | Almond Street Widening/Drainage Imprv | Loc Funds (CITY) | 15 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 5 | 10 | 0 | 0 | [9 empty] | 255 | [6 empty] | 5 | [7 empty] | 10 | [23 empty] | 0 | [5 empty] | 55 | 55 | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 510 | 5 | 5 | 10 | 10 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 15 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 5 | 10 | 0 | 0 | [48 empty] | 0
BUT | 2L116 |  | Paradise, City of | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10200000094 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Bille Road Widening and Overlay Study | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 2L117 |  | Paradise, City of | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10200000095 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0L0054 |  | Buschmann Road Extension Study | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 2L118 |  | Paradise, City of | RIP | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | [8 empty] | 290 | [39 empty] | 10200000096 | RIP |  |  |  |  | 580 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 454014 |  | Upper Clark Widening and Overlay | TOTAL | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 2L119 |  | Paradise, City of | RIP | 0 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 0 | 0 | 0 | 0 | [9 empty] | 522 | [38 empty] | 10200000097 | RIP |  |  |  |  | 0 | 0 | 1044 | 1044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1044 | 1044 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 454354 |  | Pearson Road Rehabilitation | TOTAL | 0 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 2L120 |  | Paradise, City of | RIP | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442 | 0 | 0 | 0 | 0 | [9 empty] | 442 | [38 empty] | 10200000098 | RIP |  |  |  |  | 0 | 0 | 884 | 884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884 | 884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0L0024 |  | Skyway/Wagstaff Signalization | TOTAL | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 0016W | 149 | Caltrans | GF IIP | 59144 | 7553 | 0 | 0 | 0 | 0 | 0 | 0 | 2886 | 44811 | 5000 | 5000 | 1000 | 8000 | 2886 | [7 empty] | 44811 | [7 empty] | 346 | 4654 | [6 empty] | 3709 | 1291 | [6 empty] | 596 | 404 | [6 empty] | 6796 | 1204 | [6 empty] | 10200000028 | [5 empty] | 152138 | 152138 | 28370 | 28370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2886 | 2886 | 44811 | 44811 | 9654 | 9654 | 6291 | 6291 | 1404 | 1404 | 9204 | 9204
| 3822U0 | 0.0/R4.6 | Hwy 149 4 Lane Expressway | RIP | 0 | 7100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7100 | 0 | 0 | 0 | 0 | [9 empty] | 7100 | [38 empty] | 0 | RIP |  |  |  | X | 0 | 0 | 14200 | 14200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14200 | 14200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | IIP | 6124 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 6614 | 19510 | 0 | 0 | 0 | 0 |  | 6614 | [6 empty] | 6124 | 13386 | [38 empty] | 0 | [5 empty] | 12248 | 12248 | 33386 | 33386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13228 | 13228 | 32896 | 32896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 65268 | 34653 | 0 | 0 | 0 | 0 | 0 | 0 | 9500 | 71421 | 5000 | 5000 | 1000 | 8000 | [48 empty] | 0
BUT | 3L76 | 191 | Butte County Association of Governments | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10200000117 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4A980K | 10.1/11.4 | SR 191 Widening and Lane Addition Phase 1 | Future Need | 0 | 0 | 488 | 843 | 0 | 4484 | 0 | 0 | 400 | 4000 | 0 | 488 | 443 | 484 |  |  |  | 400 | [9 empty] | 4000 | [12 empty] | 488 | [8 empty] | 443 | [9 empty] | 484 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 1952 | 1952 | 2615 | 2615 | 0 | 0 | 10904 | 10904 | 0 | 0 | 0 | 0 | 1600 | 1600 | 24000 | 24000 | 0 | 0 | 1464 | 1464 | 1772 | 1772 | 2904 | 2904
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 488 | 843 | 0 | 4484 | 0 | 0 | 400 | 4000 | 0 | 488 | 443 | 484 | [48 empty] | 0
BUT | A0364A | 70 | Caltrans | RIP | 3000 | 3390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3390 | 0 | 0 | [16 empty] | 3000 | [8 empty] | 3390 | [22 empty] | 10200000026 | RIP |  |  |  | X | 9000 | 9000 | 13560 | 13560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 6780 | 6780 | 0 | 0 | 0 | 0
| 372300 | R0.0/13.5 | Route70 Expressway | IIP | 3000 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 7000 | 0 | 0 | [16 empty] | 3000 | [8 empty] | 7000 | [22 empty] | 0 | [5 empty] | 9000 | 9000 | 28000 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 14000 | 14000 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65500 | 44000 | 0 | 0 | 17000 | 4500 | 0 | [7 empty] | 44000 | [23 empty] | 17000 | [7 empty] | 4500 | [8 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134500 | 134500 | 352000 | 352000 | 0 | 0 | 0 | 0 | 136000 | 136000 | 36000 | 36000 | 0 | 0
|  |  |  | Loc Funds (CITY) | 0 | 610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | [25 empty] | 610 | [22 empty] | 0 | [5 empty] | 0 | 0 | 2440 | 2440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 1220 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 6000 | 11000 | 0 | 0 | 0 | 0 | 0 | 65500 | 44000 | 0 | 6000 | 28000 | 4500 | 0 | [48 empty] | 0
BUT | 2262 | 70 | Caltrans | RIP | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 0 | 0 | 0 | [16 empty] | 522 | [31 empty] | 10200000040 | RIP |  |  |  | X | 1566 | 1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 522 | 0 | 0 | 0 | 0 | 0 | 0
| 3A630K | 10.3/13.0 | Oroville Freeway Extension | IIP | 6162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3725 | 0 | 522 | 1565 | 350 | 0 | 3725 | [15 empty] | 522 | [7 empty] | 1565 | [7 empty] | 350 | [15 empty] | 0 | [5 empty] | 13301 | 13301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3725 | 3725 | 0 | 0 | 522 | 522 | 1565 | 1565 | 350 | 350 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 34500 | 0 | 0 | 30000 | 0 | 0 | 0 | 4500 | [14 empty] | 30000 | [31 empty] | 4500 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 87000 | 0 | 0 | 0 | 0 | 210000 | 210000 | 0 | 0 | 0 | 0 | 0 | 0 | 31500 | 31500
|  |  |  | Demo | 5640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3725 | 0 | 0 | 1565 | 350 | 0 | 3725 | [23 empty] | 1565 | [7 empty] | 350 | [15 empty] | 0 | [5 empty] | 11735 | 11735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3725 | 3725 | 0 | 0 | 0 | 0 | 1565 | 1565 | 350 | 350 | 0 | 0
|  |  |  | TOTAL | 12324 | 0 | 0 | 0 | 0 | 0 | 34500 | 0 | 7450 | 30000 | 1044 | 3130 | 700 | 4500 | [48 empty] | 0
BUT | 2410 | 99 | Caltrans | RIP | 0 | 0 | 578 | 1000 | 3578 | 0 | 0 | 0 | 30 | 3070 | 0 | 1283 | 265 | 508 |  |  | 30 | [9 empty] | 3070 | [13 empty] | 523 | 760 | [6 empty] | 25 | 240 | [8 empty] | 508 |  |  |  | 10200000064 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 2247 | 2247 | 4240 | 4240 | 9188 | 9188 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 15350 | 15350 | 0 | 0 | 4609 | 4609 | 1035 | 1035 | 2540 | 2540
| 3A040K | R33.2/R33.3 | Butte 99 Chico Aux Lanes/Intersection | Future Need | 0 | 0 | 0 | 0 | 14332 | 0 | 0 | 0 | 0 | 12908 | 0 | 0 | 0 | 1424 | [12 empty] | 12908 | [31 empty] | 1424 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34360 | 34360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64540 | 64540 | 0 | 0 | 0 | 0 | 0 | 0 | 7120 | 7120
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 578 | 1000 | 17910 | 0 | 0 | 0 | 30 | 15978 | 0 | 1283 | 265 | 1932 | [48 empty] | 0
BUT | 2411 | 99 | Caltrans | RIP | 308 | 0 | 723 | 0 | 2283 | 0 | 0 | 0 | 367 | 1930 | 0 | 308 | 356 | 353 |  |  | 367 | [9 empty] | 1930 | [11 empty] | 308 | [9 empty] | 356 | [9 empty] | 353 |  |  |  | 10200000065 | RIP |  |  |  | X | 1232 | 1232 | 0 | 0 | 2147 | 2147 | 0 | 0 | 5978 | 5978 | 0 | 0 | 0 | 0 | 0 | 0 | 1101 | 1101 | 9650 | 9650 | 0 | 0 | 308 | 308 | 1068 | 1068 | 1765 | 1765
| 3A270K | 4.1/4.4 | Butte 99 Gridley Oper. Imprvmnts | TOTAL | 308 | 0 | 723 | 0 | 2283 | 0 | 0 | 0 | 367 | 1930 | 0 | 308 | 356 | 353 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
BUT | 2415 | 99 | Caltrans | RIP | 0 | 1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 90 | 220 | 1 | 180 | [9 empty] | 590 | [7 empty] | 90 | [7 empty] | 220 | [7 empty] | 1 | [7 empty] | 180 | [6 empty] | 10200000116 | RIP |  |  |  | X | 0 | 0 | 3415 | 3415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1180 | 1180 | 180 | 180 | 440 | 440 | 2 | 2 | 360 | 360
| 4A840K | 23.9/23.9 | Butte 99 & Durham Pentz Rd Interchange | TOTAL | 0 | 1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 90 | 220 | 1 | 180 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
|  |  |  | Total RIP | 7942 | 14679 | 2845 | 1055 | 5915 | 1150 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 3830 | 02/03: 3881
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 0 | 02/03: 0
|  |  |  | Total RIP Eligible for Reprogramming | 4112 | 10798 | 2845 | 1055 | 5915 | 1150 | 0 | 0
[8 empty] | 18810 | 5915 | 1150