## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Humboldt County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
HUM | 2059P |  | Arcata, City of | RIP | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | [9 empty] | 660 | [38 empty] | 13000000858 | RIP |  |  |  |  | 0 | 0 | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 280434 |  | K Street/Alliance Rd Rehab, Pedestrian | Loc Funds (CITY) | 14 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 13 | 0 | 0 | [9 empty] | 9 | [6 empty] | 1 | [7 empty] | 13 | [23 empty] | 0 | [5 empty] | 55 | 55 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 1 | 1 | 13 | 13 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 14 | 669 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 669 | 1 | 13 | 0 | 0 | [48 empty] | 0
HUM | 2071 |  | Arcata, City of | RIP | 0 | 0 | 110 | 0 | 471 | 1219 | 0 | 0 | 240 | 1219 | 110 | 231 | 0 | 0 |  |  |  |  | 240 | [8 empty] | 1219 |  |  |  |  | 110 | [9 empty] | 231 | [19 empty] | 13000001206 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 330 | 330 | 0 | 0 | 1164 | 1164 | 2438 | 2438 | 0 | 0 | 0 | 0 | 1200 | 1200 | 7314 | 7314 | 330 | 330 | 1155 | 1155 | 0 | 0 | 0 | 0
|  |  | Foster Ave. to Sunset Ave. Extension | TOTAL | 0 | 0 | 110 | 0 | 471 | 1219 | 0 | 0 | 240 | 1219 | 110 | 231 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2072 |  | Arcata, City of | RIP | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | [11 empty] | 70 | [36 empty] | 13000001207 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Railroad Crossing Rehabilitation | TOTAL | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2073 |  | Blue Lake, City of | RIP | 0 | 0 | 46 | 304 | 0 | 0 | 0 | 0 | 10 | 304 | 6 | 30 | 0 | 0 |  |  | 10 | [8 empty] | 304 | [6 empty] | 6 | [7 empty] | 30 | [21 empty] | 13000001208 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 148 | 148 | 608 | 608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 1216 | 1216 | 18 | 18 | 90 | 90 | 0 | 0 | 0 | 0
|  |  | Pedestrian and Bicycle Improvements | TOTAL | 0 | 0 | 46 | 304 | 0 | 0 | 0 | 0 | 10 | 304 | 6 | 30 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2002T |  | Eureka, City of | RIP | 0 | 0 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 261 | 0 | 0 | 0 | 0 | [10 empty] | 261 | [37 empty] | 13000000145 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 522 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783 | 783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| B000BA |  | Replace Regional Transit Vehicles | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (LTF) | 114 | 32 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | [8 empty] | 114 | 32 | 34 | [37 empty] | 0 | [5 empty] | 228 | 228 | 64 | 64 | 68 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 114 | 32 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 441 | 0 | 0 | 0 | 0 | [48 empty] | 0
HUM | 2061P |  | Eureka, City of | RIP | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 0 | 0 | 0 | 0 | [8 empty] | 310 | [39 empty] | 13000000860 | RIP |  |  |  |  | 620 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 7th Street Bike Lanes | Loc Funds (CITY) | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | [24 empty] | 30 | [23 empty] | 0 | [5 empty] | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 0 | 30 | 0 | 0 | [48 empty] | 0
HUM | 2069 |  | Eureka, City of | Othr. State | 0 | 0 | 3632 | 0 | 0 | 0 | 0 | 0 | 3269 | 0 | 0 | 363 | 0 | 0 |  |  | 3269 | [23 empty] | 363 | [21 empty] | 13000001032 | [5 empty] | 0 | 0 | 0 | 0 | 4721 | 4721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9807 | 9807 | 0 | 0 | 0 | 0 | 1089 | 1089 | 0 | 0 | 0 | 0
|  |  | Waterfront Drive Extension | RIP | 0 | 0 | 486 | 0 | 0 | 2019 | 0 | 0 | 486 | 2019 | 0 | 0 | 0 | 0 |  |  | 486 | [10 empty] | 2019 | [34 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 486 | 486 | 0 | 0 | 0 | 0 | 4038 | 4038 | 0 | 0 | 0 | 0 | 1458 | 1458 | 12114 | 12114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 0 | 0 | 3248 | 0 | 0 | 0 | 3248 | 0 | 0 | 0 | 0 | [13 empty] | 3248 | [34 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6496 | 6496 | 0 | 0 | 0 | 0 | 0 | 0 | 19488 | 19488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 0 | 4118 | 0 | 0 | 5267 | 0 | 0 | 3755 | 5267 | 0 | 363 | 0 | 0 | [48 empty] | 0
HUM | 2074 |  | Eureka, City of | RIP | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | [9 empty] | 100 | [38 empty] | 13000001209 | RIP |  |  |  |  | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 281354 |  | Railroad Crossing Improvements | TOTAL | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2101 |  | Eureka, City of | RIP | 0 | 0 | 692 | 0 | 0 | 0 | 0 | 0 | 0 | 692 | 0 | 0 | 0 | 0 | [10 empty] | 692 | [37 empty] | 13000001236 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1384 | 1384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2076 | 2076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Vehicle Replacement | Loc Funds (CITY) | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | [9 empty] | 103 | [38 empty] | 0 | [5 empty] | 0 | 0 | 206 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 103 | 692 | 0 | 0 | 0 | 0 | 0 | 0 | 795 | 0 | 0 | 0 | 0 | [48 empty] | 0
HUM | 2075 |  | Ferndale, City of | RIP | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 8 | 267 | 0 | 25 | 0 | 0 |  |  |  | 8 | [7 empty] | 267 | [15 empty] | 25 | [20 empty] | 13000001210 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 642 | 642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 1068 | 1068 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  |  | Ocean Ave. & Eugene St Reconstruction | TOTAL | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 8 | 267 | 0 | 25 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2076 |  | Fortuna, City of | RIP | 0 | 0 | 0 | 0 | 711 | 0 | 0 | 0 | 0 | 711 | 0 | 0 | 0 | 0 | [12 empty] | 711 | [35 empty] | 13000001211 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422 | 1422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3555 | 3555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Rohnerville Road Widening (Redwood - Jordan) | TOTAL | 0 | 0 | 0 | 0 | 711 | 0 | 0 | 0 | 0 | 711 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2077 |  | Fortuna, City of | RIP | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | [12 empty] | 300 | [35 empty] | 13000001212 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Rhonerville Widening (Newburg to Strong) | TOTAL | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2078 |  | Fortuna, City of | RIP | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | [10 empty] | 30 | [37 empty] | 13000001213 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 281214 |  | Railroad Grade Crossing | TOTAL | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2001R |  | Humboldt County | RIP | 0 | 5605 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 4805 | 0 | 0 | 0 | 0 |  | 800 | [7 empty] | 4805 | [38 empty] | 13000000143 | RIP |  |  |  |  | 0 | 0 | 10410 | 10410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | 9610 | 9610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 279634 |  | Old Arcata Road/Myrtle Ave Rehab and Widening | TOTAL | 0 | 5605 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 4805 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2054P |  | Humboldt County | RIP | 0 | 551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 0 | 0 | 0 | 0 | [9 empty] | 551 | [38 empty] | 13000000873 | RIP |  |  |  |  | 0 | 0 | 1102 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 280584 |  | Walnut Drive Bike Lane | TOTAL | 0 | 551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2081 |  | Humboldt County | RIP | 0 | 0 | 144 | 173 | 0 | 1583 | 0 | 0 | 100 | 1583 | 144 | 73 | 0 | 0 |  |  |  | 100 | [9 empty] | 1583 |  |  |  |  | 144 | [8 empty] | 73 | [20 empty] | 13000001216 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 432 | 432 | 392 | 392 | 0 | 0 | 3166 | 3166 | 0 | 0 | 0 | 0 | 400 | 400 | 9498 | 9498 | 432 | 432 | 292 | 292 | 0 | 0 | 0 | 0
|  |  | Union St and Sea Ave Reconstruction | TOTAL | 0 | 0 | 144 | 173 | 0 | 1583 | 0 | 0 | 100 | 1583 | 144 | 73 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2082 |  | Humboldt County | RIP | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 532 | 0 | 48 | 0 | 0 | [10 empty] | 532 | [15 empty] | 48 | [21 empty] | 13000001217 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1256 | 1256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1596 | 1596 | 0 | 0 | 144 | 144 | 0 | 0 | 0 | 0
|  |  | Washington & McKinleyville Ave Rehab | TOTAL | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 532 | 0 | 48 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2083 |  | Humboldt County | RIP | 0 | 0 | 19 | 316 | 0 | 0 | 0 | 0 | 0 | 316 | 0 | 19 | 0 | 0 | [11 empty] | 316 | [14 empty] | 19 | [21 empty] | 13000001218 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 76 | 76 | 632 | 632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1264 | 1264 | 0 | 0 | 57 | 57 | 0 | 0 | 0 | 0
|  |  | Maple Creek Road Rehab | TOTAL | 0 | 0 | 19 | 316 | 0 | 0 | 0 | 0 | 0 | 316 | 0 | 19 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2084 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 21 | 470 | 0 | 0 | 0 | 470 | 0 | 21 | 0 | 0 | [13 empty] | 470 | [14 empty] | 21 | [19 empty] | 13000001219 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 940 | 940 | 0 | 0 | 0 | 0 | 0 | 0 | 2820 | 2820 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 0
|  |  | Alderpoint and Mattlole Rd Rehab | TOTAL | 0 | 0 | 0 | 0 | 21 | 470 | 0 | 0 | 0 | 470 | 0 | 21 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2085 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 307 | 0 | 0 | 0 | 0 | 282 | 0 | 25 | 0 | 0 | [12 empty] | 282 | [15 empty] | 25 | [19 empty] | 13000001220 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 664 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1410 | 1410 | 0 | 0 | 125 | 125 | 0 | 0 | 0 | 0
|  |  | Walnut Drive Rehab | TOTAL | 0 | 0 | 0 | 0 | 307 | 0 | 0 | 0 | 0 | 282 | 0 | 25 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2086 |  | Humboldt County | RIP | 0 | 0 | 45 | 0 | 702 | 0 | 0 | 0 | 0 | 702 | 0 | 45 | 0 | 0 | [12 empty] | 702 | [13 empty] | 45 | [21 empty] | 13000001221 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 180 | 180 | 0 | 0 | 1404 | 1404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3510 | 3510 | 0 | 0 | 135 | 135 | 0 | 0 | 0 | 0
|  |  | Murray and Fieldbrook Rd Rehab | TOTAL | 0 | 0 | 45 | 0 | 702 | 0 | 0 | 0 | 0 | 702 | 0 | 45 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2087 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 49 | 550 | 0 | 0 | 0 | 550 | 0 | 49 | 0 | 0 | [13 empty] | 550 | [14 empty] | 49 | [19 empty] | 13000001222 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 196 | 1100 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 3300 | 3300 | 0 | 0 | 245 | 245 | 0 | 0 | 0 | 0
|  |  | Hiller and Pickett Rd Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 49 | 550 | 0 | 0 | 0 | 550 | 0 | 49 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2088 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 46 | 517 | 0 | 0 | 0 | 517 | 0 | 46 | 0 | 0 | [13 empty] | 517 | [14 empty] | 46 | [19 empty] | 13000001223 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 184 | 1034 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 3102 | 3102 | 0 | 0 | 230 | 230 | 0 | 0 | 0 | 0
|  |  | Humboldt Hill Road Rehab | TOTAL | 0 | 0 | 0 | 0 | 46 | 517 | 0 | 0 | 0 | 517 | 0 | 46 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2089 |  | Humboldt County | RIP | 0 | 0 | 40 | 640 | 0 | 0 | 0 | 0 | 0 | 640 | 0 | 40 | 0 | 0 | [11 empty] | 640 | [14 empty] | 40 | [21 empty] | 13000001224 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 160 | 160 | 1280 | 1280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2560 | 2560 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
|  |  | Tompkins Hill Rd & Fields Landing Dr. Rehab | TOTAL | 0 | 0 | 40 | 640 | 0 | 0 | 0 | 0 | 0 | 640 | 0 | 40 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2090 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 30 | 649 | 0 | 0 | 0 | 649 | 0 | 30 | 0 | 0 | [13 empty] | 649 | [14 empty] | 30 | [19 empty] | 13000001225 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 1298 | 1298 | 0 | 0 | 0 | 0 | 0 | 0 | 3894 | 3894 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0
|  |  | Redwood Drive Rehab | TOTAL | 0 | 0 | 0 | 0 | 30 | 649 | 0 | 0 | 0 | 649 | 0 | 30 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2091 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 0 | 262 | 12 | 12 | 0 | 0 | [13 empty] | 262 | [7 empty] | 12 | [7 empty] | 12 | [18 empty] | 13000001226 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 608 | 608 | 0 | 0 | 0 | 0 | 0 | 0 | 1572 | 1572 | 72 | 72 | 72 | 72 | 0 | 0 | 0 | 0
|  |  | Indianola Cuttoff Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 0 | 286 | 0 | 0 | 0 | 262 | 12 | 12 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2092 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 66 | 615 | 0 | 0 | 0 | 615 | 38 | 28 | 0 | 0 | [13 empty] | 615 | [6 empty] | 38 | [7 empty] | 28 | [19 empty] | 13000001227 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 226 | 1230 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | 3690 | 3690 | 190 | 190 | 140 | 140 | 0 | 0 | 0 | 0
|  |  | Azalea Ave Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 66 | 615 | 0 | 0 | 0 | 615 | 38 | 28 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2093 |  | Humboldt County | RIP | 0 | 0 | 53 | 663 | 0 | 0 | 0 | 0 | 0 | 663 | 0 | 53 | 0 | 0 | [11 empty] | 663 | [14 empty] | 53 | [21 empty] | 13000001228 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 212 | 212 | 1326 | 1326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2652 | 2652 | 0 | 0 | 159 | 159 | 0 | 0 | 0 | 0
|  |  | Central Ave Rehabilitation | TOTAL | 0 | 0 | 53 | 663 | 0 | 0 | 0 | 0 | 0 | 663 | 0 | 53 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2094 |  | Humboldt County | RIP | 0 | 0 | 46 | 0 | 558 | 0 | 0 | 0 | 0 | 558 | 0 | 46 | 0 | 0 | [12 empty] | 558 | [13 empty] | 46 | [21 empty] | 13000001229 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 184 | 184 | 0 | 0 | 1116 | 1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2790 | 2790 | 0 | 0 | 138 | 138 | 0 | 0 | 0 | 0
|  |  | Fieldbrook Road Rehab | TOTAL | 0 | 0 | 46 | 0 | 558 | 0 | 0 | 0 | 0 | 558 | 0 | 46 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2095 |  | Humboldt County | RIP | 0 | 0 | 0 | 18 | 18 | 398 | 0 | 0 | 0 | 398 | 18 | 18 | 0 | 0 | [13 empty] | 398 | [5 empty] | 18 | [8 empty] | 18 | [19 empty] | 13000001230 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 54 | 72 | 72 | 796 | 796 | 0 | 0 | 0 | 0 | 0 | 0 | 2388 | 2388 | 72 | 72 | 90 | 90 | 0 | 0 | 0 | 0
|  |  | Buttermilk Lane Rehabilitation | TOTAL | 0 | 0 | 0 | 18 | 18 | 398 | 0 | 0 | 0 | 398 | 18 | 18 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2096 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 33 | 365 | 0 | 0 | 0 | 365 | 0 | 33 | 0 | 0 | [13 empty] | 365 | [14 empty] | 33 | [19 empty] | 13000001231 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 132 | 730 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 2190 | 2190 | 0 | 0 | 165 | 165 | 0 | 0 | 0 | 0
|  |  | Golf Course Road Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 33 | 365 | 0 | 0 | 0 | 365 | 0 | 33 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2097 |  | Humboldt County | RIP | 0 | 0 | 0 | 20 | 103 | 286 | 0 | 0 | 85 | 286 | 20 | 18 | 0 | 0 |  |  |  |  | 85 | [8 empty] | 286 | [5 empty] | 20 | [8 empty] | 18 | [19 empty] | 13000001232 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 157 | 157 | 572 | 572 | 0 | 0 | 0 | 0 | 425 | 425 | 1716 | 1716 | 80 | 80 | 90 | 90 | 0 | 0 | 0 | 0
|  |  | Myrtle, Harris, Harrison, Lucas Sidewalks | TOTAL | 0 | 0 | 0 | 20 | 103 | 286 | 0 | 0 | 85 | 286 | 20 | 18 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2098 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 26 | 230 | 0 | 0 | 50 | 180 | 13 | 13 | 0 | 0 | [5 empty] | 50 | [7 empty] | 180 | [6 empty] | 13 | [7 empty] | 13 | [19 empty] | 13000001233 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91 | 91 | 410 | 410 | 0 | 0 | 0 | 0 | 300 | 300 | 1080 | 1080 | 65 | 65 | 65 | 65 | 0 | 0 | 0 | 0
|  |  | Herrick Ave, Elks Lodge Rd, Bay Point Ct Sidewalks | TOTAL | 0 | 0 | 0 | 0 | 26 | 230 | 0 | 0 | 50 | 180 | 13 | 13 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2099 |  | Humboldt County | RIP | 0 | 0 | 0 | 0 | 36 | 254 | 0 | 0 | 0 | 254 | 20 | 16 | 0 | 0 | [13 empty] | 254 | [6 empty] | 20 | [7 empty] | 16 | [19 empty] | 13000001234 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 124 | 508 | 508 | 0 | 0 | 0 | 0 | 0 | 0 | 1524 | 1524 | 100 | 100 | 80 | 80 | 0 | 0 | 0 | 0
|  |  | Central Ave Shoulder Widening | TOTAL | 0 | 0 | 0 | 0 | 36 | 254 | 0 | 0 | 0 | 254 | 20 | 16 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2100 |  | Humboldt County | RIP | 0 | 0 | 7 | 0 | 93 | 0 | 0 | 0 | 0 | 93 | 0 | 7 | 0 | 0 | [12 empty] | 93 | [13 empty] | 7 | [21 empty] | 13000001235 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 28 | 28 | 0 | 0 | 186 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465 | 465 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0
|  |  | Railroad Crossing Improvements | TOTAL | 0 | 0 | 7 | 0 | 93 | 0 | 0 | 0 | 0 | 93 | 0 | 7 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2002P |  | Humboldt County Association of Governments | RIP | 0 | 0 | 152 | 47 | 140 | 155 | 0 | 0 | 0 | 494 | 0 | 0 | 0 | 0 | [10 empty] | 152 | 47 | 140 | 155 | [34 empty] | 13000000144 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 304 | 304 | 94 | 94 | 280 | 280 | 310 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 2274 | 2274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 924595 |  | Plan, program and monitor | TOTAL | 0 | 0 | 152 | 47 | 140 | 155 | 0 | 0 | 0 | 494 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2079 |  | Rio Dell, City of | RIP | 0 | 0 | 78 | 0 | 573 | 0 | 0 | 0 | 0 | 573 | 0 | 78 | 0 | 0 | [12 empty] | 573 | [13 empty] | 78 | [21 empty] | 13000001214 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 312 | 312 | 0 | 0 | 1146 | 1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2865 | 2865 | 0 | 0 | 234 | 234 | 0 | 0 | 0 | 0
|  |  | Wildwood Ave. Priority Pavment Rehab | TOTAL | 0 | 0 | 78 | 0 | 573 | 0 | 0 | 0 | 0 | 573 | 0 | 78 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 2080 |  | Trinidad, City of | RIP | 0 | 0 | 41 | 0 | 289 | 0 | 0 | 0 | 0 | 289 | 1 | 40 | 0 | 0 | [12 empty] | 289 | [5 empty] | 1 | [7 empty] | 40 | [21 empty] | 13000001215 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 163 | 163 | 0 | 0 | 578 | 578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1445 | 1445 | 3 | 3 | 120 | 120 | 0 | 0 | 0 | 0
|  |  | Azalea and Pacific Ave. Reconstruction | TOTAL | 0 | 0 | 41 | 0 | 289 | 0 | 0 | 0 | 0 | 289 | 1 | 40 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
HUM | 0050 | 101 | Caltrans | RIP | 4795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2831 | 0 | 575 | 1003 | 386 | 0 | 2831 | [15 empty] | 575 | [7 empty] | 1003 | [7 empty] | 386 | [15 empty] | 13000000153 | RIP |  |  |  | X | 10498 | 10498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2831 | 2831 | 0 | 0 | 575 | 575 | 1003 | 1003 | 386 | 386 | 0 | 0
| 290300 | 57.0/58.8 | Route 101/36 Interchange | Future Need | 0 | 0 | 0 | 0 | 8029 | 0 | 0 | 0 | 0 | 6696 | 0 | 0 | 0 | 1333 | [12 empty] | 6696 | [31 empty] | 1333 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21390 | 21390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33480 | 33480 | 0 | 0 | 0 | 0 | 0 | 0 | 6665 | 6665
|  | Change Reason ==> |  | TOTAL | 4795 | 0 | 0 | 0 | 8029 | 0 | 0 | 0 | 2831 | 6696 | 575 | 1003 | 386 | 1333 | [48 empty] | 0
HUM | 0072 | 101 | Caltrans | RIP | 2613 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2613 | 0 | 0 | 0 | [16 empty] | 2613 | [31 empty] | 13000000867 | RIP |  |  |  | X | 7839 | 7839 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2613 | 2613 | 0 | 0 | 0 | 0 | 0 | 0
| 36600K | 79.8/85.8 | Eureka/Arcata Corridor Improvement | Future Need | 0 | 0 | 0 | 0 | 3680 | 0 | 460 | 2180 | 2180 | 0 | 0 | 3680 | 460 | 0 | [7 empty] | 2180 | [20 empty] | 3680 | [9 empty] | 460 | [9 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14720 | 14720 | 0 | 0 | 2300 | 2300 | 2180 | 2180 | 17440 | 17440 | 0 | 0 | 0 | 0 | 18400 | 18400 | 3220 | 3220 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 2613 | 0 | 0 | 0 | 3680 | 0 | 460 | 2180 | 2180 | 0 | 2613 | 3680 | 460 | 0 | [48 empty] | 0
SHA | A0166A | 299 | Caltrans | RIP | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | [16 empty] | 46 | [31 empty] | 11100000053 | RIP |  |  |  | X | 138 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 0
| 270310 | 0.0/R7.4 | Buckhorn Grade - Environmental Only | RIP (SHA) | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | [16 empty] | 150 | [31 empty] | 0 | [5 empty] | 450 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | IIP | 1942 | 3146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5088 | 0 | 0 | 0 | [16 empty] | 1942 | 3146 | [30 empty] | 0 | [5 empty] | 5826 | 5826 | 9438 | 9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8234 | 8234 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 1760 | 401 | 112270 | 0 | 0 | 40 | 108901 | 0 | 1760 | 361 | 3369 |  |  |  |  | 40 | [8 empty] | 108901 | [13 empty] | 1760 | [8 empty] | 361 | [8 empty] | 3369 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 7040 | 7040 | 1845 | 1845 | 238016 | 238016 | 0 | 0 | 0 | 0 | 200 | 200 | 653406 | 653406 | 0 | 0 | 7040 | 7040 | 1805 | 1805 | 20214 | 20214
|  |  |  | TOTAL | 2138 | 3146 | 0 | 1760 | 401 | 112270 | 0 | 0 | 40 | 108901 | 5284 | 1760 | 361 | 3369 | [48 empty] | 0
|  |  |  | Total RIP | 7764 | 6916 | 2830 | 2551 | 4572 | 9596 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 4623 | 02/03: 0
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 2831 | 02/03: 0
|  |  |  | Total RIP Eligible for Reprogramming | 310 | 6916 | 2830 | 2551 | 4572 | 9596 | 0 | 0
[8 empty] | 12607 | 4572 | 9596