## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Inyo County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
INY | 0004 |  | Bishop, City of | RIP | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | [8 empty] | 385 | [39 empty] | 13000000553 | RIP |  |  |  |  | 770 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385 | 385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 108554 |  | Wye Road reconstruction | Loc Funds (CITY) | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 15 | 35 | 0 | 0 | [8 empty] | 250 | [7 empty] | 15 | [7 empty] | 35 | [23 empty] | 0 | [5 empty] | 685 | 685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 15 | 15 | 35 | 35 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 635 | 15 | 35 | 0 | 0 | [48 empty] | 0
INY | 0005 |  | Bishop, City of | RIP | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | [9 empty] | 410 | [38 empty] | 13000000554 | RIP |  |  |  |  | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 820 | 820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 108564 |  | Home Street reconstruction | TOTAL | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1502 |  | Bishop, City of | RIP | 0 | 0 | 30 | 0 | 385 | 0 | 0 | 0 | 30 | 385 | 0 | 0 | 0 | 0 |  |  | 30 | [9 empty] | 385 | [35 empty] | 13000000916 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 770 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 1925 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 108684 |  | MacIver Street Extension | TOTAL | 0 | 0 | 30 | 0 | 385 | 0 | 0 | 0 | 30 | 385 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1503 |  | Bishop, City of | RIP | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 56 | 0 | 0 | [9 empty] | 14 | [15 empty] | 56 | [22 empty] | 13000000917 | RIP |  |  |  |  | 0 | 0 | 252 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 0 | 0 | 112 | 112 | 0 | 0 | 0 | 0
| 108694 |  | Pavement Management Plan - Phase I | TOTAL | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 56 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1504 |  | Bishop, City of | RIP | 0 | 0 | 35 | 320 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 35 | 0 | 0 | [11 empty] | 320 | [14 empty] | 35 | [21 empty] | 13000000918 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 140 | 140 | 640 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280 | 1280 | 0 | 0 | 105 | 105 | 0 | 0 | 0 | 0
| 108704 |  | Pavement Management Plan - Phase II | TOTAL | 0 | 0 | 35 | 320 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 35 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1005 |  | Inyo County | RIP | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 7 | 0 | 0 | [10 empty] | 59 | [15 empty] | 7 | [21 empty] | 13000000556 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 146 | 146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177 | 177 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0
|  |  | Mill Creek Road, overlay | TOTAL | 0 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 7 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1016 |  | Inyo County | RIP | 0 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 163 | 0 | 20 | 0 | 0 | [12 empty] | 163 | [15 empty] | 20 | [19 empty] | 13000000558 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406 | 406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 815 | 815 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  |  | Ed Powers Road Overlay | TOTAL | 0 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 163 | 0 | 20 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1017 |  | Inyo County | RIP | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 96 | 0 | 11 | 0 | 0 | [12 empty] | 96 | [15 empty] | 11 | [19 empty] | 13000000559 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 0 | 0 | 55 | 55 | 0 | 0 | 0 | 0
|  |  | Red Hill Road Overlay | TOTAL | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 96 | 0 | 11 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1022 |  | Inyo County | RIP | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 161 | 0 | 19 | 0 | 0 | [12 empty] | 161 | [15 empty] | 19 | [19 empty] | 13000000560 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805 | 805 | 0 | 0 | 95 | 95 | 0 | 0 | 0 | 0
|  |  | Pleasant Valley Dam Rd Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 161 | 0 | 19 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1103 |  | Inyo County | RIP | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 77 | 0 | 9 | 0 | 0 | [12 empty] | 77 | [15 empty] | 9 | [19 empty] | 13000000565 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 385 | 385 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0
|  |  | Starlite Drive Overlay | TOTAL | 0 | 0 | 0 | 0 | 86 | 0 | 0 | 0 | 0 | 77 | 0 | 9 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 2019 |  | Inyo County | RIP | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 4 | 0 | 0 | [11 empty] | 34 | [15 empty] | 4 | [20 empty] | 13000000570 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136 | 136 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0
|  |  | Collins Road Overlay | TOTAL | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 4 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 2031 |  | Inyo County | RIP | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 4 | 0 | 0 | [10 empty] | 34 | [15 empty] | 4 | [21 empty] | 13000000572 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 84 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 102 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0
|  |  | Sunland Indian Reservation Road | TOTAL | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 4 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 2034 |  | Inyo County | RIP | 0 | 0 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 0 | 31 | 0 | 0 | [10 empty] | 258 | [15 empty] | 31 | [21 empty] | 13000000573 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 640 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774 | 774 | 0 | 0 | 93 | 93 | 0 | 0 | 0 | 0
| 108594 |  |  | TOTAL | 0 | 0 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 258 | 0 | 31 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 3036 |  | Inyo County | RIP | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 11 | 0 | 0 | [9 empty] | 94 | [15 empty] | 11 | [22 empty] | 13000000581 | RIP |  |  |  |  | 0 | 0 | 232 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 188 | 0 | 0 | 22 | 22 | 0 | 0 | 0 | 0
|  |  | Shabbell Lane overlay | TOTAL | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 0 | 11 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 4019 |  | Inyo County | RIP | 0 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 24 | 0 | 0 | [9 empty] | 200 | [15 empty] | 24 | [22 empty] | 13000000583 | RIP |  |  |  |  | 0 | 0 | 496 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0
|  |  | Tuttle Creek Road overlay | TOTAL | 0 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 24 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 4021 |  | Inyo County | RIP | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 12 | 0 | 0 | [9 empty] | 99 | [15 empty] | 12 | [22 empty] | 13000000584 | RIP |  |  |  |  | 0 | 0 | 246 | 246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 198 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0
|  |  | Substation Road overlay | TOTAL | 0 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 12 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1006 |  | Inyo County | RIP | 0 | 0 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 458 | 0 | 38 | 0 | 0 | [10 empty] | 458 | [15 empty] | 38 | [21 empty] | 13000000914 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1068 | 1068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374 | 1374 | 0 | 0 | 114 | 114 | 0 | 0 | 0 | 0
|  |  | Alabama Hills Roads Resurfacing | TOTAL | 0 | 0 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 458 | 0 | 38 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1008 |  | Inyo County | RIP | 0 | 0 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 458 | 0 | 38 | 0 | 0 | [10 empty] | 458 | [15 empty] | 38 | [21 empty] | 13000000915 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1068 | 1068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374 | 1374 | 0 | 0 | 114 | 114 | 0 | 0 | 0 | 0
|  |  | Old Spanish Trail Road Resurfacing | TOTAL | 0 | 0 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 458 | 0 | 38 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1112 |  | Inyo County | RIP | 0 | 0 | 0 | 1637 | 0 | 0 | 0 | 0 | 0 | 1511 | 0 | 126 | 0 | 0 | [11 empty] | 1511 | [15 empty] | 126 | [20 empty] | 13000000924 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3526 | 3526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6044 | 6044 | 0 | 0 | 504 | 504 | 0 | 0 | 0 | 0
| 108874 |  | Gill Station - Coso Road Reconstruction | TOTAL | 0 | 0 | 0 | 1637 | 0 | 0 | 0 | 0 | 0 | 1511 | 0 | 126 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 5049 |  | Inyo County | RIP | 0 | 0 | 42 | 140 | 1718 | 0 | 0 | 0 | 0 | 1718 | 42 | 140 | 0 | 0 | [12 empty] | 1718 | [5 empty] | 42 | [8 empty] | 140 | [20 empty] | 13000001159 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 126 | 126 | 560 | 560 | 3436 | 3436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8590 | 8590 | 126 | 126 | 560 | 560 | 0 | 0 | 0 | 0
|  |  | Whitney Portal Road Reconstruction | TOTAL | 0 | 0 | 42 | 140 | 1718 | 0 | 0 | 0 | 0 | 1718 | 42 | 140 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 5050 |  | Inyo County | RIP | 0 | 0 | 0 | 66 | 220 | 2714 | 0 | 0 | 0 | 2714 | 66 | 220 | 0 | 0 | [13 empty] | 2714 | [5 empty] | 66 | [8 empty] | 220 | [19 empty] | 13000001160 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 198 | 880 | 880 | 5428 | 5428 | 0 | 0 | 0 | 0 | 0 | 0 | 16284 | 16284 | 264 | 264 | 1100 | 1100 | 0 | 0 | 0 | 0
|  |  | Glacier Lodge Rd. Reconstruction | TOTAL | 0 | 0 | 0 | 66 | 220 | 2714 | 0 | 0 | 0 | 2714 | 66 | 220 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 5051 |  | Inyo County | RIP | 0 | 0 | 0 | 0 | 6 | 794 | 0 | 0 | 0 | 744 | 6 | 50 | 0 | 0 | [13 empty] | 744 | [6 empty] | 6 | [8 empty] | 50 | [18 empty] | 13000001161 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 1688 | 1688 | 0 | 0 | 0 | 0 | 0 | 0 | 4464 | 4464 | 30 | 30 | 300 | 300 | 0 | 0 | 0 | 0
|  |  | Onion Valley Rd Resurfacing Project | TOTAL | 0 | 0 | 0 | 0 | 6 | 794 | 0 | 0 | 0 | 744 | 6 | 50 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 5052 |  | Inyo County | RIP | 0 | 0 | 0 | 3 | 30 | 367 | 0 | 0 | 0 | 367 | 3 | 30 | 0 | 0 | [13 empty] | 367 | [5 empty] | 3 | [8 empty] | 30 | [19 empty] | 13000001162 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 120 | 120 | 734 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 2202 | 2202 | 12 | 12 | 150 | 150 | 0 | 0 | 0 | 0
|  |  | Mustang Mesa Resurfacing Project | TOTAL | 0 | 0 | 0 | 3 | 30 | 367 | 0 | 0 | 0 | 367 | 3 | 30 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 5053 |  | Inyo County | RIP | 0 | 0 | 0 | 90 | 710 | 0 | 0 | 0 | 0 | 710 | 30 | 60 | 0 | 0 | [12 empty] | 710 | [6 empty] | 30 | [7 empty] | 60 | [20 empty] | 13000001163 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 330 | 1420 | 1420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | 3550 | 120 | 120 | 240 | 240 | 0 | 0 | 0 | 0
|  |  | 9 Mile Canyon Rd Reconstruction, Phase 2 | TOTAL | 0 | 0 | 0 | 90 | 710 | 0 | 0 | 0 | 0 | 710 | 30 | 60 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 5054 |  | Inyo County | RIP | 0 | 0 | 0 | 0 | 10 | 665 | 0 | 0 | 0 | 625 | 10 | 40 | 0 | 0 | [13 empty] | 625 | [6 empty] | 10 | [8 empty] | 40 | [18 empty] | 13000001164 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 1410 | 1410 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 50 | 50 | 240 | 240 | 0 | 0 | 0 | 0
|  |  | Trona Wildrose Rd. Reconstruction Phase II | TOTAL | 0 | 0 | 0 | 0 | 10 | 665 | 0 | 0 | 0 | 625 | 10 | 40 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 5055 |  | Inyo County | RIP | 0 | 0 | 0 | 250 | 250 | 250 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | [11 empty] | 250 | 250 | 250 | [34 empty] | 13000001239 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 500 | 500 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Purchase transit buses | TOTAL | 0 | 0 | 0 | 250 | 250 | 250 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 1010 |  | Inyo County Local Transportation Commission | RIP | 0 | 0 | 117 | 50 | 50 | 50 | 0 | 0 | 0 | 267 | 0 | 0 | 0 | 0 | [10 empty] | 117 | 50 | 50 | 50 | [34 empty] | 13000000259 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 234 | 234 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 1101 | 1101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 955056 |  | Plan Program and Monitor | TOTAL | 0 | 0 | 117 | 50 | 50 | 50 | 0 | 0 | 0 | 267 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
KER | 8010 | 14 | Caltrans | RIP | 458 | 1383 | 4149 | 0 | 0 | 0 | 0 | 0 | 1144 | 3780 | 105 | 353 | 239 | 369 |  | 1144 | [8 empty] | 3780 | [5 empty] | 105 | [7 empty] | 353 | [8 empty] | 239 | [8 empty] | 369 | [5 empty] | 10400000072 | RIP |  |  |  | X | 1727 | 1727 | 2339 | 2339 | 9774 | 9774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2288 | 2288 | 11340 | 11340 | 105 | 105 | 353 | 353 | 478 | 478 | 1107 | 1107
| 40840K | 16.2/26.0 | North Mojave four lanes | RIP (KER) | 1832 | 5533 | 16594 | 0 | 0 | 0 | 0 | 0 | 4574 | 15120 | 420 | 1412 | 959 | 1474 |  | 4574 | [8 empty] | 15120 | [5 empty] | 420 | [7 empty] | 1412 | [8 empty] | 959 | [8 empty] | 1474 | [5 empty] | 0 | [5 empty] | 6908 | 6908 | 9369 | 9369 | 39084 | 39084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9148 | 9148 | 45360 | 45360 | 420 | 420 | 1412 | 1412 | 1918 | 1918 | 4422 | 4422
|  | Change Reason ==> |  | RIP (MNO) | 458 | 1383 | 4149 | 0 | 0 | 0 | 0 | 0 | 1143 | 3780 | 105 | 353 | 240 | 369 |  | 1143 | [8 empty] | 3780 | [5 empty] | 105 | [7 empty] | 353 | [8 empty] | 240 | [8 empty] | 369 | [5 empty] | 0 | [5 empty] | 1727 | 1727 | 2343 | 2343 | 9774 | 9774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2286 | 2286 | 11340 | 11340 | 105 | 105 | 353 | 353 | 480 | 480 | 1107 | 1107
|  |  |  | IIP | 1832 | 5533 | 16594 | 0 | 0 | 0 | 0 | 0 | 4574 | 15120 | 420 | 1412 | 959 | 1474 |  | 4574 | [8 empty] | 15120 | [5 empty] | 420 | [7 empty] | 1412 | [8 empty] | 959 | [8 empty] | 1474 | [5 empty] | 0 | [5 empty] | 6908 | 6908 | 9369 | 9369 | 39084 | 39084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9148 | 9148 | 45360 | 45360 | 420 | 420 | 1412 | 1412 | 1918 | 1918 | 4422 | 4422
|  |  |  | TOTAL | 4580 | 13832 | 41486 | 0 | 0 | 0 | 0 | 0 | 11435 | 37800 | 1050 | 3530 | 2397 | 3686 | [48 empty] | 0
KER | 8042 | 14 | Caltrans | RIP | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381 | 0 | 0 | 0 | [17 empty] | 381 | [30 empty] | 10400000147 | RIP |  |  |  | X | 0 | 0 | 1143 | 1143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762 | 762 | 0 | 0 | 0 | 0 | 0 | 0
| 45710K | 45.9/62.3 | FREEMAN GULCH WIDENING | RIP (KER) | 0 | 1524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1524 | 0 | 0 | 0 | [17 empty] | 1524 | [30 empty] | 0 | [5 empty] | 0 | 0 | 4572 | 4572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3048 | 3048 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | RIP (MNO) | 0 | 381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381 | 0 | 0 | 0 | [17 empty] | 381 | [30 empty] | 0 | [5 empty] | 0 | 0 | 1143 | 1143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 762 | 762 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | IIP | 0 | 1520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1520 | 0 | 0 | 0 | [17 empty] | 1520 | [30 empty] | 0 | [5 empty] | 0 | 0 | 4560 | 4560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3040 | 3040 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 | 3050 | 1150 | 0 | [30 empty] | 3050 | [7 empty] | 1150 | [9 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17950 | 17950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21350 | 21350 | 8050 | 8050 | 0 | 0
|  |  |  | TOTAL | 0 | 3806 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 3806 | 3050 | 1150 | 0 | [48 empty] | 0
KER | 8539 | 395 | Caltrans | RIP | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | [17 empty] | 200 | [30 empty] | 10400000148 | RIP |  |  |  | X | 0 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0
| 44310K | 14.8/23.0 | INYOKERN 4 LANE | RIP (KER) | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | [17 empty] | 800 | [30 empty] | 0 | [5 empty] | 0 | 0 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | RIP (MNO) | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | [17 empty] | 200 | [30 empty] | 0 | [5 empty] | 0 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | IIP | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | [17 empty] | 800 | [30 empty] | 0 | [5 empty] | 0 | 0 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800 | 6000 | 0 | 0 | 1470 | 2330 | 0 | [7 empty] | 6000 | [23 empty] | 1470 | [7 empty] | 2330 | [8 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23530 | 23530 | 48000 | 48000 | 0 | 0 | 0 | 0 | 11760 | 11760 | 18640 | 18640 | 0 | 0
|  |  |  | TOTAL | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 9800 | 6000 | 0 | 2000 | 1470 | 2330 | 0 | [48 empty] | 0
SBD | 0260B | 395 | Caltrans | RIP | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | [17 empty] | 2000 | [30 empty] | 10900001293 | RIP |  |  |  | X | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
| 34040K | R4.0/48.0 | US-395 Widening | RIP (KER) | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | [17 empty] | 2000 | [30 empty] | 0 | [5 empty] | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | RIP (MNO) | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | [17 empty] | 2000 | [30 empty] | 0 | [5 empty] | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | RIP (SBD) | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | [17 empty] | 4000 | [30 empty] | 0 | [5 empty] | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | IIP | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | [17 empty] | 4000 | [30 empty] | 0 | [5 empty] | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 46260 | 23760 | 0 | 0 | 22000 | 4500 | 0 | [7 empty] | 23760 | [21 empty] | 4000 |  | 18000 | [7 empty] | 4500 | [8 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16000 | 16000 | 0 | 0 | 118260 | 118260 | 190080 | 190080 | 0 | 0 | 0 | 0 | 168000 | 168000 | 36000 | 36000 | 0 | 0
|  |  |  | TOTAL | 0 | 14000 | 0 | 0 | 0 | 4000 | 0 | 46260 | 23760 | 0 | 14000 | 22000 | 4500 | 0 | [48 empty] | 0
INY | 0192 | 395 | Caltrans | RIP | 4343 | 48 | 0 | 0 | 34024 | 0 | 0 | 0 | 310 | 31660 | 1015 | 2625 | 441 | 2364 | 262 | 48 | [10 empty] | 31660 |  |  |  | 1015 | [7 empty] | 2625 | [7 empty] | 441 | [11 empty] | 2364 |  |  |  | 13000000270 | RIP |  |  |  | X | 16012 | 16012 | 48 | 48 | 0 | 0 | 0 | 0 | 77504 | 77504 | 0 | 0 | 0 | 0 | 0 | 0 | 358 | 358 | 158300 | 158300 | 1015 | 1015 | 2625 | 2625 | 441 | 441 | 11820 | 11820
| 214600 | 77.3/91.6 | BLACK ROCK 4-LANE | TOTAL | 4343 | 48 | 0 | 0 | 34024 | 0 | 0 | 0 | 310 | 31660 | 1015 | 2625 | 441 | 2364 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
INY | 0170 | 395 | Caltrans | RIP | 461 | 0 | 1215 | 3984 | 0 | 0 | 0 | 0 | 3341 | 0 | 461 | 1215 | 643 | 0 |  |  |  | 3341 | [12 empty] | 461 | [9 empty] | 1215 | [8 empty] | 643 | [12 empty] | 13000000638 | RIP |  |  |  | X | 1383 | 1383 | 0 | 0 | 4860 | 4860 | 6556 | 6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13364 | 13364 | 0 | 0 | 461 | 461 | 3645 | 3645 | 2572 | 2572 | 0 | 0
| 21340K | 30.8/41.8 | Olancha and Cartago expressway | RIP (KER) | 115 | 0 | 304 | 997 | 0 | 0 | 0 | 0 | 836 | 0 | 115 | 304 | 161 | 0 |  |  |  | 836 | [12 empty] | 115 | [9 empty] | 304 | [8 empty] | 161 | [12 empty] | 0 | [5 empty] | 345 | 345 | 0 | 0 | 1216 | 1216 | 1641 | 1641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3344 | 3344 | 0 | 0 | 115 | 115 | 912 | 912 | 644 | 644 | 0 | 0
|  | Change Reason ==> |  | RIP (MNO) | 115 | 0 | 304 | 997 | 0 | 0 | 0 | 0 | 836 | 0 | 115 | 304 | 161 | 0 |  |  |  | 836 | [12 empty] | 115 | [9 empty] | 304 | [8 empty] | 161 | [12 empty] | 0 | [5 empty] | 345 | 345 | 0 | 0 | 1216 | 1216 | 1641 | 1641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3344 | 3344 | 0 | 0 | 115 | 115 | 912 | 912 | 644 | 644 | 0 | 0
|  |  |  | IIP | 461 | 0 | 1215 | 3984 | 0 | 0 | 0 | 0 | 3341 | 0 | 461 | 1215 | 643 | 0 |  |  |  | 3341 | [12 empty] | 461 | [9 empty] | 1215 | [8 empty] | 643 | [12 empty] | 0 | [5 empty] | 1383 | 1383 | 0 | 0 | 4860 | 4860 | 6556 | 6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13364 | 13364 | 0 | 0 | 461 | 461 | 3645 | 3645 | 2572 | 2572 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68776 | 0 | 65807 | 0 | 0 | 0 | 2969 | [15 empty] | 65807 | [31 empty] | 2969 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149428 | 149428 | 0 | 0 | 526456 | 526456 | 0 | 0 | 0 | 0 | 0 | 0 | 23752 | 23752
|  |  |  | TOTAL | 1152 | 0 | 3038 | 9962 | 0 | 0 | 0 | 68776 | 8354 | 65807 | 1152 | 3038 | 1608 | 2969 | [48 empty] | 0
MNO | 0241 | 395 | Caltrans | RIP | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | [17 empty] | 131 | [30 empty] | 13000001053 | RIP |  |  |  | X | 0 | 0 | 393 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 262 | 0 | 0 | 0 | 0 | 0 | 0
| 23770K | 117.9/119.4 | Highpoint Curve Corrections | RIP (KER) | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 0 | 0 | 0 | [17 empty] | 131 | [30 empty] | 0 | [5 empty] | 0 | 0 | 393 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 262 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | RIP (MNO) | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | [17 empty] | 525 | [30 empty] | 0 | [5 empty] | 0 | 0 | 1575 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 1050 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | IIP | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | [17 empty] | 525 | [30 empty] | 0 | [5 empty] | 0 | 0 | 1575 | 1575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 1050 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 1847 | 0 | 263 | 0 | 0 | 1258 | 326 | 0 | [6 empty] | 263 | [23 empty] | 1258 | [7 empty] | 326 | [9 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6925 | 6925 | 0 | 0 | 1841 | 1841 | 0 | 0 | 0 | 0 | 8806 | 8806 | 2282 | 2282 | 0 | 0
|  |  |  | TOTAL | 0 | 1312 | 0 | 0 | 0 | 0 | 1847 | 0 | 263 | 0 | 1312 | 1258 | 326 | 0 | [48 empty] | 0
|  |  |  | Total RIP | 5647 | 5063 | 6973 | 6578 | 37959 | 4840 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 5000 | 02/03: 2951
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 262 | 02/03: 1192
|  |  |  | Total RIP Eligible for Reprogramming | 385 | 920 | 6973 | 6578 | 37959 | 4840 | 0 | 0
[8 empty] | 14856 | 37959 | 4840