## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Monterey County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
MON | 0935 |  | Association of Monterey Bay Area Governments | RIP | 0 | 0 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 0 | 0 | 0 | 0 | [10 empty] | 214 | [37 empty] | 10100000024 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 428 | 428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 642 | 642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4A0734 |  | Regional Rideshare Program | TOTAL | 0 | 0 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1141 |  | Association of Monterey Bay Area Governments | RIP | 0 | 0 | 0 | 235 | 259 | 214 | 0 | 0 | 0 | 708 | 0 | 0 | 0 | 0 | [11 empty] | 235 | 259 | 214 | [34 empty] | 10100000194 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 470 | 518 | 518 | 428 | 428 | 0 | 0 | 0 | 0 | 0 | 0 | 3519 | 3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Rideshare Program for Monterey County | TOTAL | 0 | 0 | 0 | 235 | 259 | 214 | 0 | 0 | 0 | 708 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1005 |  | Carmel By The Sea, City of | RIP | 0 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | 171 | 0 | 0 | 0 | 0 | [12 empty] | 171 | [35 empty] | 10100000158 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855 | 855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Junipero Ave. Repaving and Streetscape | RSTP | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | [12 empty] | 50 | [35 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CITY) | 25 | 15 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 29 | 5 | 35 | 0 | 0 | [12 empty] | 29 |  |  |  | 5 | [7 empty] | 20 | 15 | [22 empty] | 0 | [5 empty] | 95 | 95 | 60 | 60 | 0 | 0 | 0 | 0 | 58 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 145 | 5 | 5 | 50 | 50 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 25 | 15 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 250 | 5 | 35 | 0 | 0 | [48 empty] | 0
MON | 1224 |  | Carmel By The Sea, City of | RIP | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | [12 empty] | 50 | [35 empty] | 10100000223 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | San Carlos Street Repaving Project | Loc Funds (CITY) | 0 | 2 | 8 | 0 | 30 | 0 | 0 | 0 | 0 | 30 | 2 | 8 | 0 | 0 | [12 empty] | 30 |  |  |  |  | 2 | [8 empty] | 8 | [21 empty] | 0 | [5 empty] | 0 | 0 | 6 | 6 | 32 | 32 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 4 | 4 | 24 | 24 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 2 | 8 | 0 | 80 | 0 | 0 | 0 | 0 | 80 | 2 | 8 | 0 | 0 | [48 empty] | 0
MON | 1147 |  | Del Rey Oaks, City of | RIP | 0 | 0 | 0 | 0 | 5 | 50 | 0 | 0 | 0 | 50 | 0 | 5 | 0 | 0 | [13 empty] | 50 | [14 empty] | 5 | [19 empty] | 10100000184 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0
|  |  | Del Rey Oaks-Work Ave Re-Surfacing | TOTAL | 0 | 0 | 0 | 0 | 5 | 50 | 0 | 0 | 0 | 50 | 0 | 5 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1146 |  | Del Rey Oaks, City of | RIP | 0 | 0 | 0 | 0 | 9 | 90 | 0 | 0 | 0 | 90 | 0 | 9 | 0 | 0 | [13 empty] | 90 | [14 empty] | 9 | [19 empty] | 10100000213 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 540 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0
|  |  | Carlton Drive Resurfacing | TOTAL | 0 | 0 | 0 | 0 | 9 | 90 | 0 | 0 | 0 | 90 | 0 | 9 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1012 |  | Gonzales, City of | RIP | 0 | 0 | 0 | 50 | 0 | 150 | 0 | 0 | 0 | 183 | 0 | 17 | 0 | 0 | [11 empty] | 46 |  | 137 | [13 empty] | 4 |  | 13 | [18 empty] | 10100000165 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 108 | 0 | 0 | 326 | 326 | 0 | 0 | 0 | 0 | 0 | 0 | 1006 | 1006 | 0 | 0 | 94 | 94 | 0 | 0 | 0 | 0
|  |  | North Alta Street Rehabilitation | TOTAL | 0 | 0 | 0 | 50 | 0 | 150 | 0 | 0 | 0 | 183 | 0 | 17 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1149 |  | Greenfield, City of | RIP | 0 | 0 | 0 | 0 | 0 | 246 | 0 | 0 | 0 | 246 | 0 | 0 | 0 | 0 | [13 empty] | 246 | [34 empty] | 10100000185 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492 | 492 | 0 | 0 | 0 | 0 | 0 | 0 | 1476 | 1476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Oak Ave Pavement Overlay | Loc Funds (CITY) | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 18 | 0 | 0 | [9 empty] | 10 | [6 empty] | 2 | [7 empty] | 18 | [23 empty] | 0 | [5 empty] | 78 | 78 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 2 | 2 | 18 | 18 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 20 | 10 | 0 | 0 | 0 | 246 | 0 | 0 | 0 | 256 | 2 | 18 | 0 | 0 | [48 empty] | 0
MON | 1154 |  | King City, City of | RIP | 0 | 0 | 0 | 0 | 0 | 261 | 0 | 0 | 0 | 261 | 0 | 0 | 0 | 0 | [13 empty] | 261 | [34 empty] | 10100000186 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 522 | 0 | 0 | 0 | 0 | 0 | 0 | 1566 | 1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Reconstruct South Second St | Loc Funds (RED) | 0 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331 | 10 | 37 | 0 | 0 | [9 empty] | 331 | [7 empty] | 10 | [7 empty] | 37 | [22 empty] | 0 | [5 empty] | 0 | 0 | 840 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 662 | 662 | 20 | 20 | 74 | 74 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 378 | 0 | 0 | 0 | 261 | 0 | 0 | 0 | 592 | 10 | 37 | 0 | 0 | [48 empty] | 0
MON | 1150 |  | Marina, City of | RIP | 0 | 0 | 0 | 0 | 20 | 409 | 0 | 0 | 0 | 409 | 0 | 20 | 0 | 0 | [13 empty] | 409 | [14 empty] | 20 | [19 empty] | 10100000187 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 818 | 818 | 0 | 0 | 0 | 0 | 0 | 0 | 2454 | 2454 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  |  | Overlay City Streets | TOTAL | 0 | 0 | 0 | 0 | 20 | 409 | 0 | 0 | 0 | 409 | 0 | 20 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1155 |  | Monterey County | RIP | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | [12 empty] | 1500 | [35 empty] | 10100000180 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Pajaro Yard and Rail Station Improvements | TOTAL | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1152 |  | Monterey County | RIP | 0 | 0 | 130 | 135 | 135 | 1100 | 0 | 0 | 50 | 1100 | 265 | 85 | 0 | 0 |  |  |  |  | 50 | [8 empty] | 1100 |  |  |  |  | 130 | 135 | [8 empty] | 85 | [19 empty] | 10100000182 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 390 | 390 | 405 | 405 | 390 | 390 | 2200 | 2200 | 0 | 0 | 0 | 0 | 250 | 250 | 6600 | 6600 | 930 | 930 | 425 | 425 | 0 | 0 | 0 | 0
|  |  | Davis Road Bridge Replacement | Local HBRR | 0 | 0 | 328 | 322 | 9350 | 0 | 0 | 0 | 200 | 9150 | 135 | 515 | 0 | 0 |  |  |  |  | 200 | [7 empty] | 9150 | [5 empty] | 135 | [7 empty] | 193 | 322 | [20 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 1177 | 1177 | 1288 | 1288 | 18500 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 45750 | 45750 | 405 | 405 | 1867 | 1867 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (DEV FEE) | 0 | 0 | 0 | 200 | 400 | 1300 | 0 | 0 | 0 | 1300 | 400 | 200 | 0 | 0 | [13 empty] | 1300 | [5 empty] | 200 | 200 | [7 empty] | 200 | [19 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 1400 | 1400 | 2600 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 7800 | 7800 | 1800 | 1800 | 1000 | 1000 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 0 | 458 | 657 | 9885 | 2400 | 0 | 0 | 250 | 11550 | 800 | 800 | 0 | 0 | [48 empty] | 0
MON | 1151 |  | Monterey County | RIP | 0 | 0 | 0 | 170 | 1960 | 0 | 0 | 0 | 0 | 1960 | 0 | 170 | 0 | 0 | [12 empty] | 1960 | [14 empty] | 170 | [20 empty] | 10100000189 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 680 | 3920 | 3920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800 | 9800 | 0 | 0 | 680 | 680 | 0 | 0 | 0 | 0
|  |  | Abbott Street Overlay | TOTAL | 0 | 0 | 0 | 170 | 1960 | 0 | 0 | 0 | 0 | 1960 | 0 | 170 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1153 |  | Monterey County | RIP | 0 | 200 | 0 | 0 | 3440 | 0 | 0 | 0 | 0 | 3440 | 0 | 200 | 0 | 0 | [12 empty] | 3440 | [12 empty] | 200 | [22 empty] | 10100000190 | RIP |  |  |  |  | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 0 | 6880 | 6880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17200 | 17200 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0
|  |  | Hall Road Overlay | TOTAL | 0 | 200 | 0 | 0 | 3440 | 0 | 0 | 0 | 0 | 3440 | 0 | 200 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1157 |  | Monterey Salinas Transit | RIP | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | [10 empty] | 2500 | [37 empty] | 10100000181 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Marina Transit Station | TOTAL | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1158 |  | Pacific Grove, City of | RIP | 0 | 0 | 15 | 0 | 0 | 459 | 0 | 0 | 0 | 459 | 0 | 15 | 0 | 0 | [13 empty] | 459 | [12 empty] | 15 | [21 empty] | 10100000191 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 918 | 918 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2754 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0
|  |  | Lighthouse Ave Rehabilitation | Loc Funds (CITY) | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | [9 empty] | 6 | [38 empty] | 0 | [5 empty] | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 6 | 15 | 0 | 0 | 459 | 0 | 0 | 0 | 465 | 0 | 15 | 0 | 0 | [48 empty] | 0
MON | 1016 |  | Salinas, City of | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10100000169 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4A1284 |  | Citywide Street Overlays | Loc Funds (CITY) | 45 | 551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 5 | 40 | 0 | 0 | [9 empty] | 551 | [6 empty] | 5 | [7 empty] | 40 | [23 empty] | 0 | [5 empty] | 175 | 175 | 1102 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1102 | 1102 | 5 | 5 | 40 | 40 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 45 | 551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 551 | 5 | 40 | 0 | 0 | [48 empty] | 0
MON | 1160 |  | Salinas, City of | RIP | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | [9 empty] | 1000 | [38 empty] | 10100000183 | RIP |  |  |  |  | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Sanborn Rd Improvement Project | Future Need | 0 | 2014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2014 | 0 | 0 | 0 | 0 | [9 empty] | 2014 | [38 empty] | 0 | [5 empty] | 0 | 0 | 4028 | 4028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4028 | 4028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 3014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3014 | 0 | 0 | 0 | 0 | [48 empty] | 0
MON | 1159 |  | Salinas, City of | RIP | 0 | 0 | 0 | 0 | 993 | 1986 | 0 | 0 | 0 | 2979 | 0 | 0 | 0 | 0 | [12 empty] | 993 | 1986 | [34 empty] | 10100000192 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1986 | 1986 | 3972 | 3972 | 0 | 0 | 0 | 0 | 0 | 0 | 16881 | 16881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | City Street Rehabilitation | Loc Funds (CITY) | 35 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 35 | 40 | 0 | 0 | [9 empty] | 57 | [6 empty] | 35 | [8 empty] | 40 | [22 empty] | 0 | [5 empty] | 105 | 105 | 274 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 114 | 35 | 35 | 80 | 80 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 35 | 97 | 0 | 0 | 993 | 1986 | 0 | 0 | 0 | 3036 | 35 | 40 | 0 | 0 | [48 empty] | 0
MON | 1010A |  | Sand City, City of | RIP | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 138 | 4 | 8 | 0 | 0 | [13 empty] | 138 | [7 empty] | 4 | [7 empty] | 8 | [18 empty] | 10100000215 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 828 | 828 | 24 | 24 | 48 | 48 | 0 | 0 | 0 | 0
|  |  | California Avenue Pavement Overlay | TOTAL | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 138 | 4 | 8 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1162 |  | Seaside, City of | RIP | 0 | 0 | 0 | 430 | 251 | 0 | 0 | 0 | 0 | 681 | 0 | 0 | 0 | 0 | [11 empty] | 430 | 251 | [35 empty] | 10100000193 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 860 | 860 | 502 | 502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2975 | 2975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Fremont Blvd Improvements | RSTP | 102 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 199 | 2 | 100 | 0 | 0 | [9 empty] | 199 | [6 empty] | 2 | [7 empty] | 100 | [23 empty] | 0 | [5 empty] | 406 | 406 | 398 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 398 | 398 | 2 | 2 | 100 | 100 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 102 | 199 | 0 | 430 | 251 | 0 | 0 | 0 | 0 | 880 | 2 | 100 | 0 | 0 | [48 empty] | 0
MON | 1015A |  | Soledad, City of | RIP | 0 | 0 | 0 | 0 | 0 | 444 | 0 | 0 | 0 | 411 | 0 | 33 | 0 | 0 | [13 empty] | 411 | [15 empty] | 33 | [18 empty] | 10100000168 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 954 | 0 | 0 | 0 | 0 | 0 | 0 | 2466 | 2466 | 0 | 0 | 198 | 198 | 0 | 0 | 0 | 0
|  |  | West St. and Front St. Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 0 | 444 | 0 | 0 | 0 | 411 | 0 | 33 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1165 |  | Transportation Agency For Monterey Co | RIP | 0 | 0 | 513 | 525 | 538 | 0 | 0 | 0 | 0 | 1576 | 0 | 0 | 0 | 0 | [10 empty] | 513 | 525 | 538 | [35 empty] | 10100000022 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1026 | 1026 | 1050 | 1050 | 1076 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6329 | 6329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4A1294 |  | Plan, program and monitor | TOTAL | 0 | 0 | 513 | 525 | 538 | 0 | 0 | 0 | 0 | 1576 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MON | 1164 |  | Transportation Agency For Monterey Co | Othr. State | 0 | 98 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 102 | 0 | 0 | [17 empty] | 98 | [8 empty] | 102 | [21 empty] | 10100000212 | [5 empty] | 0 | 0 | 294 | 294 | 408 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 196 | 306 | 306 | 0 | 0 | 0 | 0
|  |  | Monterey Bay Rail Station Improvements | RIP | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | [13 empty] | 3000 | [34 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CO) | 0 | 0 | 0 | 93 | 122 | 0 | 0 | 0 | 0 | 122 | 0 | 93 | 0 | 0 | [12 empty] | 122 | [14 empty] | 93 | [20 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 372 | 244 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 610 | 0 | 0 | 372 | 372 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 98 | 102 | 93 | 122 | 3000 | 0 | 0 | 0 | 3122 | 98 | 195 | 0 | 0 | [48 empty] | 0
MON | 0032G | 1 | Caltrans | RIP | 1161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1161 | 0 | 0 | 0 | [16 empty] | 1161 | [31 empty] | 10100000117 | RIP |  |  |  | X | 3483 | 3483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1161 | 1161 | 0 | 0 | 0 | 0 | 0 | 0
| 315920 | 100.4/R101.5 | Salinas Road Interchange | IIP | 1114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114 | 0 | 0 | 0 | [16 empty] | 1114 | [31 empty] | 0 | [5 empty] | 3342 | 3342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1114 | 1114 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 3013 | 0 | 109 | 1757 | 35747 | 1757 | 32203 | 0 | 3013 | 109 | 3544 | [6 empty] | 1757 | [8 empty] | 32203 | [11 empty] | 3013 | [9 empty] | 109 | [9 empty] | 3544 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 12052 | 12052 | 0 | 0 | 545 | 545 | 1757 | 1757 | 85670 | 85670 | 12299 | 12299 | 257624 | 257624 | 0 | 0 | 12052 | 12052 | 654 | 654 | 28352 | 28352
|  |  |  | TOTAL | 2275 | 0 | 0 | 3013 | 0 | 109 | 1757 | 35747 | 1757 | 32203 | 2275 | 3013 | 109 | 3544 | [48 empty] | 0
MON | 4281 | 1 | Transportation Agency For Monterey Co | RIP | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | [19 empty] | 1400 | [28 empty] | 10100000219 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 5600 | 0 | 0 | 0 | 0 | 0 | 0
| 42810 | 80.7/89.8 | SR 1 Improvements - Phase 1 | Future Need | 0 | 0 | 0 | 0 | 1310 | 0 | 0 | 0 | 0 | 0 | 0 | 1310 | 0 | 0 | [28 empty] | 1310 | [19 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5240 | 5240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6550 | 6550 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 0 | 1400 | 1310 | 0 | 0 | 0 | 0 | 0 | 1400 | 1310 | 0 | 0 | [48 empty] | 0
MON | 0058F | 101 | Caltrans | GF IIP | 71640 | 0 | 0 | 0 | 0 | 25087 | 0 | 0 | 47554 | 22261 | 10584 | 13296 | 206 | 2826 | 47554 | [12 empty] | 22261 |  |  | 10584 | [7 empty] | 13296 | [7 empty] | 206 | [12 empty] | 2826 |  |  | 10100000031 | [5 empty] | 133520 | 133520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61478 | 61478 | 0 | 0 | 0 | 0 | 47554 | 47554 | 133566 | 133566 | 10584 | 10584 | 13296 | 13296 | 206 | 206 | 16956 | 16956
| 0161X0 | R91.2/100.4 | Prunedale Freeway | RIP | 0 | 0 | 0 | 0 | 0 | 91462 | 0 | 0 | 0 | 84855 | 0 | 0 | 0 | 6607 | [13 empty] | 84855 | [31 empty] | 6607 |  |  | 0 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209352 | 209352 | 0 | 0 | 0 | 0 | 0 | 0 | 509130 | 509130 | 0 | 0 | 0 | 0 | 0 | 0 | 39642 | 39642
|  | Change Reason ==> |  | IIP | 14385 | 0 | 0 | 0 | 0 | 36145 | 0 | 0 | 6451 | 36145 | 528 | 1926 | 5480 | 0 | 6451 | [12 empty] | 36145 |  |  | 528 | [7 empty] | 1926 | [7 empty] | 5480 | [15 empty] | 0 | [5 empty] | 43139 | 43139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72290 | 72290 | 0 | 0 | 0 | 0 | 6451 | 6451 | 216870 | 216870 | 528 | 528 | 1926 | 1926 | 5480 | 5480 | 0 | 0
|  |  |  | Demo | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 0 | 0 | 0 | 0 | [10 empty] | 1650 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 3300 | 3300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4950 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Demo | 4000 | 0 | 7250 | 0 | 0 | 0 | 0 | 0 | 4000 | 7250 | 0 | 0 | 0 | 0 | 4000 | [9 empty] | 7250 | [37 empty] | 0 | [5 empty] | 4000 | 4000 | 0 | 0 | 14500 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 21750 | 21750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 90025 | 0 | 8900 | 0 | 0 | 152694 | 0 | 0 | 58005 | 152161 | 11112 | 15222 | 5686 | 9433 | [48 empty] | 0
MON | 0318 | 101 | Caltrans | RIP | 122 | 200 | 0 | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 322 | 688 | 0 | 0 | [16 empty] | 122 | 200 | [10 empty] | 688 | [19 empty] | 10100000118 | RIP |  |  |  | X | 366 | 366 | 600 | 600 | 0 | 0 | 0 | 0 | 2752 | 2752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522 | 522 | 3440 | 3440 | 0 | 0 | 0 | 0
| 349500 | 84.6/86.6 | Airport Boulevard Overcrossing | IIP | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | [16 empty] | 98 | [31 empty] | 0 | [5 empty] | 294 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 98 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 0 | 24265 | 0 | 44075 | 0 | 22308 | 40697 | 0 | 0 | 1957 | 3378 |  |  |  |  | 22308 | [9 empty] | 40697 | [21 empty] | 1957 | [9 empty] | 3378 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32093 | 32093 | 0 | 0 | 101662 | 101662 | 0 | 0 | 111540 | 111540 | 284879 | 284879 | 0 | 0 | 0 | 0 | 9785 | 9785 | 23646 | 23646
|  |  |  | Demo | 1678 | 0 | 0 | 0 | 2757 | 0 | 0 | 0 | 0 | 0 | 1678 | 2757 | 0 | 0 | [16 empty] | 1678 | [11 empty] | 2757 | [19 empty] | 0 | [5 empty] | 5034 | 5034 | 0 | 0 | 0 | 0 | 0 | 0 | 11028 | 11028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1678 | 1678 | 13785 | 13785 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 1898 | 200 | 0 | 0 | 27710 | 0 | 44075 | 0 | 22308 | 40697 | 2098 | 3445 | 1957 | 3378 | [48 empty] | 0
MON | 0680 | 68 | Caltrans | RIP | 0 | 0 | 4690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4690 | 0 | 0 | 0 | [18 empty] | 4690 | [29 empty] | 10100000179 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 14070 | 14070 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14070 | 14070 | 0 | 0 | 0 | 0 | 0 | 0
| 0C6800 | 4.0/15.9 | Route 68 Corridor | Future Need | 0 | 0 | 0 | 0 | 0 | 102950 | 0 | 0 | 91000 | 0 | 0 | 4610 | 7340 | 0 | [5 empty] | 91000 | [23 empty] | 4610 | [7 empty] | 7340 | [10 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 146140 | 146140 | 0 | 0 | 0 | 0 | 546000 | 546000 | 0 | 0 | 0 | 0 | 27660 | 27660 | 44040 | 44040 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 4690 | 0 | 0 | 102950 | 0 | 0 | 91000 | 0 | 4690 | 4610 | 7340 | 0 | [48 empty] | 0
MON | 0480 | 68 | Monterey, City of | RIP | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | [24 empty] | 600 | [23 empty] | 10100000123 | RIP |  |  |  |  | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 0 | 0 | 0 | 0
| 448000 | 3.8/L4.3 | Rte 68 (Holman Highway) Widening | Future Need | 0 | 284 | 8009 | 0 | 0 | 0 | 0 | 0 | 239 | 6964 | 0 | 0 | 45 | 1045 |  | 239 | [8 empty] | 6964 | [22 empty] | 45 | [8 empty] | 1045 | [5 empty] | 0 | [5 empty] | 0 | 0 | 464 | 464 | 20198 | 20198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478 | 478 | 20892 | 20892 | 0 | 0 | 0 | 0 | 90 | 90 | 3135 | 3135
|  | Change Reason ==> |  | RSTP | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | [24 empty] | 400 | [23 empty] | 0 | [5 empty] | 1600 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 1000 | 284 | 8009 | 0 | 0 | 0 | 0 | 0 | 239 | 6964 | 0 | 1000 | 45 | 1045 | [48 empty] | 0
|  |  |  | Total RIP | 1883 | 1400 | 8062 | 2945 | 10019 | 100021 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 1283 | 02/03: 200
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 0 | 02/03: 0
|  |  |  | Total RIP Eligible for Reprogramming | 600 | 1200 | 8062 | 2945 | 10019 | 100021 | 0 | 0
[8 empty] | 12807 | 10019 | 100021