## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Mariposa County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
MPA | 2K11 |  | Mariposa County | RIP | 0 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 0 | 0 | 0 | 0 | [9 empty] | 415 | [38 empty] | 13000000926 | RIP |  |  |  |  | 0 | 0 | 830 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830 | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4A1714 |  | Darrah Road Rehabilitation | TOTAL | 0 | 415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 415 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 2K12 |  | Mariposa County | RIP | 0 | 10 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 10 | 0 | 0 | [10 empty] | 200 | [14 empty] | 10 | [22 empty] | 13000000927 | RIP |  |  |  |  | 0 | 0 | 40 | 40 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0
|  |  | Don Pedro Subdivision Rehabilitation | TOTAL | 0 | 10 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 10 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K12 |  | Mariposa County | RIP | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 0 | 31 | 0 | 0 | [10 empty] | 282 | [15 empty] | 31 | [21 empty] | 13000001121 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 688 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846 | 846 | 0 | 0 | 93 | 93 | 0 | 0 | 0 | 0
|  |  | Colorodo Road Rehabilitation | TOTAL | 0 | 0 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 282 | 0 | 31 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K13 |  | Mariposa County | RIP | 0 | 0 | 17 | 326 | 0 | 0 | 0 | 0 | 0 | 326 | 0 | 17 | 0 | 0 | [11 empty] | 326 | [14 empty] | 17 | [21 empty] | 13000001138 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 68 | 68 | 652 | 652 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1304 | 1304 | 0 | 0 | 51 | 51 | 0 | 0 | 0 | 0
|  |  | East Westfall Road Rehabilitation | TOTAL | 0 | 0 | 17 | 326 | 0 | 0 | 0 | 0 | 0 | 326 | 0 | 17 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K14 |  | Mariposa County | RIP | 0 | 0 | 15 | 221 | 0 | 0 | 0 | 0 | 0 | 221 | 0 | 15 | 0 | 0 | [11 empty] | 221 | [14 empty] | 15 | [21 empty] | 13000001140 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 60 | 60 | 442 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884 | 884 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0
|  |  | East Whitlock Road Rehabilitation | TOTAL | 0 | 0 | 15 | 221 | 0 | 0 | 0 | 0 | 0 | 221 | 0 | 15 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K19 |  | Mariposa County | RIP | 0 | 0 | 15 | 208 | 0 | 0 | 0 | 0 | 0 | 208 | 0 | 15 | 0 | 0 | [11 empty] | 208 | [14 empty] | 15 | [21 empty] | 13000001141 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 60 | 60 | 416 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 832 | 832 | 0 | 0 | 45 | 45 | 0 | 0 | 0 | 0
|  |  | Triangle Road Rehabilitation | TOTAL | 0 | 0 | 15 | 208 | 0 | 0 | 0 | 0 | 0 | 208 | 0 | 15 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K16 |  | Mariposa County | RIP | 0 | 0 | 8 | 157 | 0 | 0 | 0 | 0 | 0 | 157 | 0 | 8 | 0 | 0 | [11 empty] | 157 | [14 empty] | 8 | [21 empty] | 13000001142 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 32 | 32 | 314 | 314 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628 | 628 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0
|  |  | Homitos Road Rehabilitation | TOTAL | 0 | 0 | 8 | 157 | 0 | 0 | 0 | 0 | 0 | 157 | 0 | 8 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K10 |  | Mariposa County | RIP | 0 | 0 | 0 | 20 | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 20 | 0 | 0 | [12 empty] | 360 | [14 empty] | 20 | [20 empty] | 13000001144 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 720 | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0
|  |  | Ben Hur Road Rehabilitation | TOTAL | 0 | 0 | 0 | 20 | 360 | 0 | 0 | 0 | 0 | 360 | 0 | 20 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K17 |  | Mariposa County | RIP | 0 | 0 | 0 | 15 | 199 | 0 | 0 | 0 | 0 | 199 | 0 | 15 | 0 | 0 | [12 empty] | 199 | [14 empty] | 15 | [20 empty] | 13000001145 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 398 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 995 | 995 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
|  |  | Old Highway Road Rehabilitation | TOTAL | 0 | 0 | 0 | 15 | 199 | 0 | 0 | 0 | 0 | 199 | 0 | 15 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K18 |  | Mariposa County | RIP | 0 | 0 | 0 | 0 | 20 | 740 | 0 | 0 | 0 | 740 | 0 | 20 | 0 | 0 | [13 empty] | 740 | [14 empty] | 20 | [19 empty] | 13000001147 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 1480 | 1480 | 0 | 0 | 0 | 0 | 0 | 0 | 4440 | 4440 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  |  | Smith Station Road Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 20 | 740 | 0 | 0 | 0 | 740 | 0 | 20 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K15 |  | Mariposa County | RIP | 0 | 0 | 0 | 0 | 20 | 377 | 0 | 0 | 0 | 377 | 0 | 20 | 0 | 0 | [13 empty] | 377 | [14 empty] | 20 | [19 empty] | 13000001149 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 754 | 754 | 0 | 0 | 0 | 0 | 0 | 0 | 2262 | 2262 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  |  | Granite Springs Road Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 20 | 377 | 0 | 0 | 0 | 377 | 0 | 20 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K11 |  | Mariposa County | RIP | 0 | 0 | 0 | 0 | 20 | 420 | 0 | 0 | 0 | 420 | 0 | 20 | 0 | 0 | [13 empty] | 420 | [14 empty] | 20 | [19 empty] | 13000001155 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 840 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 2520 | 2520 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  |  | Chowchilla Mountain Road Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 20 | 420 | 0 | 0 | 0 | 420 | 0 | 20 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 3K1A |  | Mariposa County | RIP | 0 | 0 | 0 | 0 | 20 | 385 | 0 | 0 | 0 | 385 | 0 | 20 | 0 | 0 | [13 empty] | 385 | [14 empty] | 20 | [19 empty] | 13000001157 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 770 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 2310 | 2310 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  |  | Traingle Road Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 20 | 385 | 0 | 0 | 0 | 385 | 0 | 20 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 4957 |  | Mariposa County Local Transportation Commission | RIP | 0 | 0 | 19 | 20 | 19 | 20 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | [10 empty] | 19 | 20 | 19 | 20 | [34 empty] | 13000000317 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 38 | 38 | 40 | 40 | 38 | 38 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 352 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4A1424 |  | Plan, program and monitor | TOTAL | 0 | 0 | 19 | 20 | 19 | 20 | 0 | 0 | 0 | 78 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
MPA | 4147 | 49 | Caltrans | RIP | 1614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 410 | 1061 | 97 | 0 | 46 | [15 empty] | 410 | [7 empty] | 1061 | [7 empty] | 97 | [15 empty] | 13000000604 | RIP |  |  |  | X | 6005 | 6005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 46 | 0 | 0 | 410 | 410 | 1061 | 1061 | 97 | 97 | 0 | 0
| 1A8400 | 17.1/17.5 | Old Highway Intersection and Bridge | Future Need | 0 | 0 | 0 | 4340 | 0 | 0 | 0 | 0 | 0 | 3787 | 0 | 0 | 0 | 553 | [11 empty] | 3787 | [31 empty] | 553 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 10892 | 10892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15148 | 15148 | 0 | 0 | 0 | 0 | 0 | 0 | 2212 | 2212
|  | Change Reason ==> |  | TOTAL | 1614 | 0 | 0 | 4340 | 0 | 0 | 0 | 0 | 46 | 3787 | 410 | 1061 | 97 | 553 | [48 empty] | 0
|  |  |  | Total RIP | 1614 | 425 | 587 | 967 | 658 | 1942 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 1568 | 02/03: 0
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 46 | 02/03: 0
|  |  |  | Total RIP Eligible for Reprogramming | 0 | 425 | 587 | 967 | 658 | 1942 | 0 | 0
[8 empty] | 1979 | 658 | 1942