## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Riverside County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
RIV | 0000C |  | Blythe, City of | RIP | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | 0 | 0 | 1875 | 0 | 0 | 0 | 0 | [10 empty] | 1875 | [37 empty] | 10900001062 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5625 | 5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Hobsonway Arterial Improvements | Loc Funds (CITY) | 160 | 1609 | 1486 | 0 | 0 | 0 | 0 | 0 | 0 | 2687 | 0 | 568 | 0 | 0 | [9 empty] | 1201 | 1486 | [13 empty] | 160 | 408 | [22 empty] | 0 | [5 empty] | 640 | 640 | 4034 | 4034 | 2972 | 2972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6860 | 6860 | 0 | 0 | 976 | 976 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 160 | 1609 | 3361 | 0 | 0 | 0 | 0 | 0 | 0 | 4562 | 0 | 568 | 0 | 0 | [48 empty] | 0
RIV | 1001 |  | Cathedral City, City of | RIP | 0 | 0 | 0 | 0 | 1385 | 0 | 0 | 0 | 0 | 1385 | 0 | 0 | 0 | 0 | [12 empty] | 1385 | [35 empty] | 10900001350 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2770 | 2770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6925 | 6925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Cathedral-Ramon Road Improvements | Loc Funds (CITY) | 0 | 225 | 31 | 0 | 206 | 0 | 0 | 0 | 31 | 206 | 25 | 200 | 0 | 0 |  |  | 31 | [9 empty] | 206 |  |  |  |  | 25 | [7 empty] | 200 | [22 empty] | 0 | [5 empty] | 0 | 0 | 875 | 875 | 31 | 31 | 0 | 0 | 412 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 93 | 1030 | 1030 | 50 | 50 | 400 | 400 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 225 | 31 | 0 | 1591 | 0 | 0 | 0 | 31 | 1591 | 25 | 200 | 0 | 0 | [48 empty] | 0
RIV | 1002 |  | Coachella, City of | RIP | 0 | 0 | 0 | 0 | 0 | 4559 | 0 | 0 | 0 | 4559 | 0 | 0 | 0 | 0 | [13 empty] | 4559 | [34 empty] | 10900001351 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9118 | 9118 | 0 | 0 | 0 | 0 | 0 | 0 | 27354 | 27354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coachella-Dillion Rd. Railroad Grade Separation | Loc Funds (AGENCY) | 0 | 0 | 850 | 2650 | 0 | 1500 | 0 | 0 | 2650 | 1500 | 220 | 630 | 0 | 0 |  |  |  | 2650 | [9 empty] | 1500 |  |  |  |  | 220 | [7 empty] | 630 | [21 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 3180 | 3180 | 2650 | 2650 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 10600 | 10600 | 9000 | 9000 | 660 | 660 | 1890 | 1890 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CITY) | 0 | 0 | 0 | 0 | 0 | 535 | 0 | 0 | 0 | 535 | 0 | 0 | 0 | 0 | [13 empty] | 535 | [34 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1070 | 1070 | 0 | 0 | 0 | 0 | 0 | 0 | 3210 | 3210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (CITY) | 0 | 0 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 610 | 0 | 0 | 0 | 0 | [13 empty] | 610 | [34 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 3660 | 3660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 0 | 850 | 2650 | 0 | 7204 | 0 | 0 | 2650 | 7204 | 220 | 630 | 0 | 0 | [48 empty] | 0
RIV | 9992 |  | Coachella, City of | RIP | 0 | 0 | 0 | 0 | 0 | 2117 | 0 | 0 | 0 | 2117 | 0 | 0 | 0 | 0 | [13 empty] | 2117 | [34 empty] | 10900001364 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4234 | 4234 | 0 | 0 | 0 | 0 | 0 | 0 | 12702 | 12702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Coachella-Dillion Road Widening | Loc Funds (CITY) | 0 | 75 | 525 | 0 | 0 | 483 | 0 | 0 | 0 | 483 | 75 | 525 | 0 | 0 | [13 empty] | 483 |  |  |  | 75 | [8 empty] | 525 | [21 empty] | 0 | [5 empty] | 0 | 0 | 225 | 225 | 2100 | 2100 | 0 | 0 | 0 | 0 | 966 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 2898 | 2898 | 150 | 150 | 1575 | 1575 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 75 | 525 | 0 | 0 | 2600 | 0 | 0 | 0 | 2600 | 75 | 525 | 0 | 0 | [48 empty] | 0
RIV | 0000F |  | Corona, City of | RIP | 0 | 0 | 671 | 0 | 0 | 0 | 0 | 0 | 0 | 671 | 0 | 0 | 0 | 0 | [10 empty] | 671 | [37 empty] | 10900001103 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1342 | 1342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2013 | 2013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| LINCLN |  | Lincoln Ave Impmts (Pomona Rd to 6th St) | Loc Funds (CITY) | 293 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 200 | 447 | 10 | 83 | 0 | 0 | 200 | [9 empty] | 447 | [5 empty] | 10 | [7 empty] | 83 | [23 empty] | 0 | [5 empty] | 562 | 562 | 0 | 0 | 894 | 894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 1341 | 1341 | 10 | 10 | 83 | 83 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 293 | 0 | 1118 | 0 | 0 | 0 | 0 | 0 | 200 | 1118 | 10 | 83 | 0 | 0 | [48 empty] | 0
RIV | 1004 |  | Corona, City of | RIP | 0 | 0 | 1990 | 0 | 0 | 0 | 0 | 0 | 0 | 1990 | 0 | 0 | 0 | 0 | [10 empty] | 1990 | [37 empty] | 10900001353 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 3980 | 3980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5970 | 5970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Corona-Advanced Transportation Management System | Loc Funds (CITY) | 504 | 0 | 766 | 0 | 0 | 0 | 0 | 0 | 0 | 766 | 252 | 252 | 0 | 0 | [10 empty] | 766 | [5 empty] | 252 | [7 empty] | 252 | [23 empty] | 0 | [5 empty] | 1764 | 1764 | 0 | 0 | 1532 | 1532 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2298 | 2298 | 252 | 252 | 252 | 252 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 504 | 0 | 2756 | 0 | 0 | 0 | 0 | 0 | 0 | 2756 | 252 | 252 | 0 | 0 | [48 empty] | 0
RIV | 0000L |  | Desert Hot Springs, City of | RIP | 0 | 627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592 | 0 | 35 | 0 | 0 | [9 empty] | 592 | [15 empty] | 35 | [22 empty] | 10900001121 | RIP |  |  |  |  | 0 | 0 | 1324 | 1324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1184 | 1184 | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 0
| 412504 |  | Pierson Boulevard Street Improvements | Loc Funds (CITY) | 4 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 4 | 12 | 0 | 0 | [9 empty] | 197 | [6 empty] | 4 | [8 empty] | 12 | [22 empty] | 0 | [5 empty] | 12 | 12 | 442 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 394 | 394 | 4 | 4 | 24 | 24 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 4 | 836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 789 | 4 | 47 | 0 | 0 | [48 empty] | 0
RIV | 1005 |  | Moreno Valley, City of | RIP | 0 | 0 | 0 | 0 | 3184 | 0 | 0 | 0 | 0 | 3184 | 0 | 0 | 0 | 0 | [12 empty] | 3184 | [35 empty] | 10900001354 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6368 | 6368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15920 | 15920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Moreno-Perris Blvd. Improvements | Loc Funds (CITY) | 0 | 0 | 500 | 0 | 1130 | 0 | 0 | 0 | 0 | 1130 | 0 | 500 | 0 | 0 | [12 empty] | 1130 | [13 empty] | 500 | [21 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 2260 | 2260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5650 | 5650 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 500 | 0 | 4314 | 0 | 0 | 0 | 0 | 4314 | 0 | 500 | 0 | 0 | [48 empty] | 0
RIV | 9993 |  | Moreno Valley, City of | RIP | 0 | 0 | 0 | 0 | 0 | 1967 | 0 | 0 | 0 | 1967 | 0 | 0 | 0 | 0 | [13 empty] | 1967 | [34 empty] | 10900001365 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3934 | 3934 | 0 | 0 | 0 | 0 | 0 | 0 | 11802 | 11802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Moreno Valley-Reche Vista Dr. Realignment, Signal | Loc Funds (CITY) | 0 | 0 | 380 | 0 | 0 | 626 | 0 | 0 | 0 | 626 | 0 | 380 | 0 | 0 | [13 empty] | 626 | [12 empty] | 380 | [21 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 1520 | 1520 | 0 | 0 | 0 | 0 | 1252 | 1252 | 0 | 0 | 0 | 0 | 0 | 0 | 3756 | 3756 | 0 | 0 | 1140 | 1140 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 380 | 0 | 0 | 2593 | 0 | 0 | 0 | 2593 | 0 | 380 | 0 | 0 | [48 empty] | 0
RIV | 1006 |  | Palm Desert, City of | RIP | 0 | 0 | 0 | 744 | 1381 | 0 | 0 | 0 | 744 | 1381 | 0 | 0 | 0 | 0 |  |  |  | 744 | [8 empty] | 1381 | [35 empty] | 10900001355 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 744 | 744 | 2762 | 2762 | 0 | 0 | 0 | 0 | 0 | 0 | 2976 | 2976 | 6905 | 6905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Palm Desert-Monterey Avenue Widening | Loc Funds (CITY) | 0 | 225 | 0 | 386 | 473 | 0 | 0 | 0 | 386 | 473 | 29 | 196 | 0 | 0 |  |  |  | 386 | [8 empty] | 473 |  |  |  |  | 29 | [7 empty] | 196 | [22 empty] | 0 | [5 empty] | 0 | 0 | 871 | 871 | 0 | 0 | 386 | 386 | 946 | 946 | 0 | 0 | 0 | 0 | 0 | 0 | 1544 | 1544 | 2365 | 2365 | 58 | 58 | 392 | 392 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 225 | 0 | 1130 | 1854 | 0 | 0 | 0 | 1130 | 1854 | 29 | 196 | 0 | 0 | [48 empty] | 0
RIV | 0000K |  | Palm Springs, City of | RIP | 0 | 190 | 0 | 1540 | 0 | 0 | 0 | 0 | 0 | 1540 | 0 | 190 | 0 | 0 | [11 empty] | 1540 | [13 empty] | 190 | [22 empty] | 10900001122 | RIP |  |  |  |  | 0 | 0 | 760 | 760 | 0 | 0 | 3080 | 3080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6160 | 6160 | 0 | 0 | 380 | 380 | 0 | 0 | 0 | 0
| 412444 |  | Gene Autry Trail Bridge and Roadway Widening | Loc Funds (CITY) | 3 | 60 | 726 | 0 | 0 | 0 | 0 | 0 | 0 | 726 | 3 | 60 | 0 | 0 | [10 empty] | 726 | [5 empty] | 3 | [8 empty] | 60 | [22 empty] | 0 | [5 empty] | 9 | 9 | 240 | 240 | 1452 | 1452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2178 | 2178 | 3 | 3 | 120 | 120 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 3 | 250 | 726 | 1540 | 0 | 0 | 0 | 0 | 0 | 2266 | 3 | 250 | 0 | 0 | [48 empty] | 0
RIV | 1007 |  | Palm Springs, City of | RIP | 0 | 263 | 0 | 1936 | 0 | 0 | 0 | 0 | 0 | 1936 | 87 | 176 | 0 | 0 | [11 empty] | 1936 | [5 empty] | 87 | [7 empty] | 176 | [22 empty] | 10900001356 | RIP |  |  |  |  | 0 | 0 | 965 | 965 | 0 | 0 | 3872 | 3872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7744 | 7744 | 174 | 174 | 352 | 352 | 0 | 0 | 0 | 0
|  |  | Palm Springs-Indian Canyon Drive Widening | Loc Funds (CITY) | 0 | 135 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 990 | 45 | 90 | 0 | 0 | [11 empty] | 990 | [5 empty] | 45 | [7 empty] | 90 | [22 empty] | 0 | [5 empty] | 0 | 0 | 495 | 495 | 0 | 0 | 1980 | 1980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3960 | 3960 | 90 | 90 | 180 | 180 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 398 | 0 | 2926 | 0 | 0 | 0 | 0 | 0 | 2926 | 132 | 266 | 0 | 0 | [48 empty] | 0
RIV | 0000J |  | Riverside County | RIP | 0 | 0 | 0 | 1564 | 0 | 0 | 0 | 0 | 0 | 1564 | 0 | 0 | 0 | 0 | [11 empty] | 1564 | [36 empty] | 10900001106 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3128 | 3128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6256 | 6256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| VALYWY |  | Valley Wy/Armstrong Rd Widening & Reconstruction | Loc Funds (CO) | 1545 | 0 | 276 | 0 | 0 | 0 | 0 | 0 | 1300 | 276 | 45 | 200 | 0 | 0 | 1300 | [9 empty] | 276 | [5 empty] | 45 | [7 empty] | 200 | [23 empty] | 0 | [5 empty] | 2235 | 2235 | 0 | 0 | 552 | 552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 1300 | 828 | 828 | 45 | 45 | 200 | 200 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 1545 | 0 | 276 | 1564 | 0 | 0 | 0 | 0 | 1300 | 1840 | 45 | 200 | 0 | 0 | [48 empty] | 0
RIV | 1100 |  | Riverside County | RIP | 0 | 0 | 0 | 3158 | 0 | 0 | 0 | 0 | 0 | 3158 | 0 | 0 | 0 | 0 | [11 empty] | 3158 | [36 empty] | 10900001358 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6316 | 6316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12632 | 12632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Limonite Ave. Widening and Reconstruction | Loc Funds (CO) | 330 | 15 | 0 | 2132 | 0 | 0 | 0 | 0 | 15 | 2132 | 45 | 285 | 0 | 0 |  | 15 | [9 empty] | 2132 |  |  |  |  | 45 | [7 empty] | 285 | [23 empty] | 0 | [5 empty] | 1275 | 1275 | 15 | 15 | 0 | 0 | 4264 | 4264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 8528 | 8528 | 45 | 45 | 285 | 285 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 330 | 15 | 0 | 5290 | 0 | 0 | 0 | 0 | 15 | 5290 | 45 | 285 | 0 | 0 | [48 empty] | 0
RIV | 1101 |  | Riverside County | RIP | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | [12 empty] | 2040 | [35 empty] | 10900001359 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4080 | 4080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10200 | 10200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Miles Ave./Clinton St. Widening & Bridge Construct | Loc Funds (CO) | 25 | 675 | 300 | 3960 | 0 | 0 | 0 | 0 | 300 | 3960 | 25 | 675 | 0 | 0 |  |  | 300 | [8 empty] | 3960 |  |  |  |  | 25 | [8 empty] | 675 | [22 empty] | 0 | [5 empty] | 75 | 75 | 2700 | 2700 | 300 | 300 | 7920 | 7920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 900 | 15840 | 15840 | 25 | 25 | 1350 | 1350 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 25 | 675 | 300 | 3960 | 2040 | 0 | 0 | 0 | 300 | 6000 | 25 | 675 | 0 | 0 | [48 empty] | 0
RIV | 9801 |  | Riverside County Trans Commission (RCTC) | RIP | 0 | 400 | 520 | 300 | 0 | 0 | 0 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | [9 empty] | 400 | 520 | 300 | [36 empty] | 10900000411 | RIP |  |  |  |  | 0 | 0 | 800 | 800 | 1040 | 1040 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3560 | 3560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| A00004 |  | Regional rideshare program | TOTAL | 0 | 400 | 520 | 300 | 0 | 0 | 0 | 0 | 0 | 1220 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
RIV | 9803 |  | Riverside County Trans Commission (RCTC) | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10900000413 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 412374 |  | Planning, programming and monitoring | RIP | 0 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 0 | 0 | 0 | 0 | [10 empty] | 166 | [37 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 332 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 166 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 0 | 0 | 0 | 0 | [48 empty] | 0
RIV | 0001M |  | Riverside County Trans Commission (RCTC) | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10900001452 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Corridor studies (APDE) | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
RIV | 0121P |  | Riverside County Trans Commission (RCTC) | RIP | 0 | 0 | 0 | 0 | 0 | 26625 | 0 | 0 | 0 | 26625 | 0 | 0 | 0 | 0 | [13 empty] | 26625 | [34 empty] | 10900001571 | RIP | X |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53250 | 53250 | 0 | 0 | 0 | 0 | 0 | 0 | 159750 | 159750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 33489G |  | AB 3090 Reimbursement Project | IIP | 0 | 0 | 0 | 0 | 0 | 4699 | 0 | 0 | 0 | 4699 | 0 | 0 | 0 | 0 | [13 empty] | 4699 | [34 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9398 | 9398 | 0 | 0 | 0 | 0 | 0 | 0 | 28194 | 28194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 0 | 0 | 0 | 31324 | 0 | 0 | 0 | 31324 | 0 | 0 | 0 | 0 | [48 empty] | 0
RIV | 9994 |  | Riverside, City of | RIP | 0 | 0 | 25 | 221 | 439 | 2780 | 0 | 0 | 439 | 2780 | 25 | 221 | 0 | 0 |  |  |  |  | 439 | [8 empty] | 2780 |  |  |  |  | 25 | [8 empty] | 221 | [20 empty] | 10900001366 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 75 | 75 | 884 | 884 | 439 | 439 | 5560 | 5560 | 0 | 0 | 0 | 0 | 2195 | 2195 | 16680 | 16680 | 75 | 75 | 884 | 884 | 0 | 0 | 0 | 0
|  |  | Riverside-Van Buren Blvd. Widening | Loc Funds (CITY) | 0 | 0 | 12 | 112 | 225 | 1422 | 0 | 0 | 225 | 1422 | 12 | 112 | 0 | 0 |  |  |  |  | 225 | [8 empty] | 1422 |  |  |  |  | 12 | [8 empty] | 112 | [20 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 36 | 36 | 448 | 448 | 225 | 225 | 2844 | 2844 | 0 | 0 | 0 | 0 | 1125 | 1125 | 8532 | 8532 | 36 | 36 | 448 | 448 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 37 | 333 | 664 | 4202 | 0 | 0 | 664 | 4202 | 37 | 333 | 0 | 0 | [48 empty] | 0
RIV | 1104 |  | Temecula, City of | RIP | 0 | 0 | 0 | 2720 | 0 | 0 | 0 | 0 | 0 | 2720 | 0 | 0 | 0 | 0 | [11 empty] | 2720 | [36 empty] | 10900001362 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5440 | 5440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10880 | 10880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Butterfield Stage Rd. Extension Beltway Project | Loc Funds (CITY) | 572 | 330 | 0 | 12078 | 0 | 0 | 0 | 0 | 330 | 12078 | 285 | 287 | 0 | 0 |  | 330 | [9 empty] | 12078 |  |  |  |  | 285 | [7 empty] | 287 | [23 empty] | 0 | [5 empty] | 2003 | 2003 | 330 | 330 | 0 | 0 | 24156 | 24156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 660 | 48312 | 48312 | 285 | 285 | 287 | 287 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 572 | 330 | 0 | 14798 | 0 | 0 | 0 | 0 | 330 | 14798 | 285 | 287 | 0 | 0 | [48 empty] | 0
RIV | 0007D | 10 | Caltrans | RIP | 3728 | 0 | 0 | 0 | 18538 | 0 | 0 | 0 | 797 | 16144 | 547 | 2157 | 227 | 2394 | 797 | [11 empty] | 16144 |  |  |  | 547 | [7 empty] | 2157 | [7 empty] | 227 | [11 empty] | 2394 |  |  |  | 10900000419 | RIP |  |  |  | X | 12201 | 12201 | 0 | 0 | 0 | 0 | 0 | 0 | 46652 | 46652 | 0 | 0 | 0 | 0 | 0 | 0 | 797 | 797 | 80720 | 80720 | 547 | 547 | 2157 | 2157 | 227 | 227 | 11970 | 11970
| 456001 | 42.6/43.9 | Ramon Road Interchange | TOTAL | 3728 | 0 | 0 | 0 | 18538 | 0 | 0 | 0 | 797 | 16144 | 547 | 2157 | 227 | 2394 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
RIV | 1003 | 15 | Corona, City of | RIP | 0 | 0 | 0 | 0 | 0 | 6418 | 0 | 0 | 0 | 5870 | 0 | 0 | 0 | 548 | [13 empty] | 5870 | [31 empty] | 548 |  |  | 10900001352 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15028 | 15028 | 0 | 0 | 0 | 0 | 0 | 0 | 35220 | 35220 | 0 | 0 | 0 | 0 | 0 | 0 | 3288 | 3288
| 452200 | 40.2/40.6 | Magnolia Ave./ I-15 Interchange Improvements | Loc Funds (CITY) | 0 | 798 | 600 | 0 | 0 | 436 | 0 | 0 | 600 | 0 | 350 | 448 | 0 | 436 |  |  | 600 | [14 empty] | 350 | [7 empty] | 448 | [19 empty] | 436 |  |  | 0 | [5 empty] | 0 | 0 | 2842 | 2842 | 600 | 600 | 0 | 0 | 0 | 0 | 2616 | 2616 | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 0 | 700 | 700 | 896 | 896 | 0 | 0 | 2616 | 2616
|  | Change Reason ==> |  | TOTAL | 0 | 798 | 600 | 0 | 0 | 6854 | 0 | 0 | 600 | 5870 | 350 | 448 | 0 | 984 | [48 empty] | 0
RIV | 9991 | 15 | Murrieta, City of | RIP | 0 | 0 | 0 | 0 | 3224 | 4142 | 0 | 0 | 3224 | 4142 | 0 | 0 | 0 | 0 |  |  |  |  | 3224 | [8 empty] | 4142 | [34 empty] | 10900001363 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3224 | 3224 | 8284 | 8284 | 0 | 0 | 0 | 0 | 16120 | 16120 | 24852 | 24852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 10.3/10.8 | Murrieta-I-15 Interchange and Ramp Reconfiguration | Loc Funds (CITY) | 0 | 1200 | 0 | 0 | 1100 | 1469 | 0 | 0 | 1100 | 1469 | 100 | 1100 | 0 | 0 |  |  |  |  | 1100 | [8 empty] | 1469 |  |  |  | 100 | [7 empty] | 1100 | [22 empty] | 0 | [5 empty] | 0 | 0 | 4700 | 4700 | 0 | 0 | 0 | 0 | 1100 | 1100 | 2938 | 2938 | 0 | 0 | 0 | 0 | 5500 | 5500 | 8814 | 8814 | 200 | 200 | 2200 | 2200 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 1200 | 0 | 0 | 4324 | 5611 | 0 | 0 | 4324 | 5611 | 100 | 1100 | 0 | 0 | [48 empty] | 0
RIV | 0121D | 215 | Caltrans | GF RIP | 50697 | 0 | 18913 | 0 | 0 | 0 | 0 | 0 | 24397 | 0 | 0 | 14148 | 12152 | 18913 | 24397 | [23 empty] | 14148 | [7 empty] | 12152 | [9 empty] | 18913 | [5 empty] | 10900000429 | RIP |  |  |  | X | 141749 | 141749 | 0 | 0 | 113478 | 113478 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24397 | 24397 | 0 | 0 | 0 | 0 | 14148 | 14148 | 12152 | 12152 | 56739 | 56739
| 3348U1 | 40.1/43.3 | HOV, TCL El Cerrito Dr to Jct 60/91/215 (Riv-215 C | RIP | 7597 | 0 | 6314 | 0 | 0 | 1251 | 0 | 0 | 0 | 0 | 0 | 6685 | 1997 | 6480 | [24 empty] | 6685 | [7 empty] | 912 |  | 1085 | [7 empty] | 5229 |  |  | 1251 |  |  | 0 | RIP |  |  |  | X | 31300 | 31300 | 0 | 0 | 36799 | 36799 | 0 | 0 | 0 | 0 | 7506 | 7506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6685 | 6685 | 4167 | 4167 | 23193 | 23193
|  | Change Reason ==> |  | RIP | 0 | 0 | 0 | 14790 | 14790 | 25415 | 25415 | 25415 | 0 | 105825 | 0 | 0 | 0 | 0 | [11 empty] | 14790 | 14790 | 25415 | 25415 | 25415 | [32 empty] | 0 | RIP |  |  | GARVEE | X | 0 | 0 | 0 | 0 | 0 | 0 | 29580 | 29580 | 29580 | 29580 | 50830 | 50830 | 50830 | 50830 | 50830 | 50830 | 0 | 0 | 666825 | 666825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | IIP | 2101 | 0 | 4935 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101 | 0 | 4935 | [24 empty] | 2101 | [17 empty] | 4935 | [5 empty] | 0 | [5 empty] | 8404 | 8404 | 0 | 0 | 29610 | 29610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2101 | 2101 | 0 | 0 | 14805 | 14805
|  |  |  | IIP | 0 | 0 | 0 | 2610 | 2610 | 4485 | 4485 | 4485 | 0 | 18675 | 0 | 0 | 0 | 0 | [11 empty] | 2610 | 2610 | 4485 | 4485 | 4485 | [32 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 5220 | 5220 | 5220 | 5220 | 8970 | 8970 | 8970 | 8970 | 8970 | 8970 | 0 | 0 | 117675 | 117675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TCRP | 0 | 0 | 1085 | 0 | 17000 | 0 | 0 | 0 | 0 | 18085 | 0 | 0 | 0 | 0 | [10 empty] | 1085 |  | 17000 | [35 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2170 | 2170 | 0 | 0 | 34000 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88255 | 88255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | RSTP | 0 | 0 | 13327 | 0 | 0 | 0 | 0 | 0 | 0 | 13327 | 0 | 0 | 0 | 0 | [10 empty] | 13327 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 26654 | 26654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39981 | 39981 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | CMAQ | 0 | 0 | 15042 | 0 | 0 | 0 | 0 | 0 | 0 | 15042 | 0 | 0 | 0 | 0 | [10 empty] | 15042 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 30084 | 30084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45126 | 45126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (LTF) | 0 | 0 | 33915 | 0 | 0 | 0 | 0 | 0 | 0 | 33915 | 0 | 0 | 0 | 0 | [10 empty] | 33915 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 67830 | 67830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101745 | 101745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 60395 | 0 | 93531 | 17400 | 34400 | 31151 | 29900 | 29900 | 24397 | 204869 | 0 | 22934 | 14149 | 30328 | [48 empty] | 0
RIV | 0033 | 60 | Caltrans | RIP | 0 | 3261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3261 | 0 | 0 | 0 | 0 | [9 empty] | 3261 | [38 empty] | 10900001053 | RIP |  |  |  | X | 0 | 0 | 6522 | 6522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6522 | 6522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 354801 | R0.5/7.5 | Riv-60 HOV Lanes | IIP | 0 | 9785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9785 | 0 | 0 | 0 | 0 | [9 empty] | 9785 | [38 empty] | 0 | [5 empty] | 0 | 0 | 19570 | 19570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19570 | 19570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TCRP | 4000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 17500 | 1340 | 2460 | 150 | 3500 | 50 | [8 empty] | 17500 | [6 empty] | 1340 | [7 empty] | 2460 | [7 empty] | 150 | [8 empty] | 3500 | [6 empty] | 0 | [5 empty] | 14660 | 14660 | 56000 | 56000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 35000 | 35000 | 1340 | 1340 | 2460 | 2460 | 150 | 150 | 7000 | 7000
|  |  |  | TOTAL | 4000 | 34046 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 30546 | 1340 | 2460 | 150 | 3500 | [48 empty] | 0
RIV | 0066D | 79 | Caltrans | RIP | 3988 | 0 | 0 | 16857 | 0 | 0 | 0 | 0 | 1527 | 15051 | 1000 | 1012 | 449 | 1806 | 1527 | [10 empty] | 15051 |  |  |  |  | 1000 | [7 empty] | 1012 | [7 empty] | 449 | [10 empty] | 1806 |  |  |  |  | 10900000584 | RIP |  |  |  | X | 10820 | 10820 | 0 | 0 | 0 | 0 | 40938 | 40938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1527 | 1527 | 60204 | 60204 | 1000 | 1000 | 1012 | 1012 | 449 | 449 | 7224 | 7224
| 464600 | R6.0/R15.8 | Widening - from Keller Road-Domenigoni Pkwy | Loc Funds (LTF) | 0 | 0 | 3000 | 4000 | 0 | 0 | 0 | 0 | 1500 | 3758 | 0 | 1000 | 500 | 242 |  |  | 1500 | [8 empty] | 3758 | [14 empty] | 1000 | [7 empty] | 500 | [8 empty] | 242 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 8000 | 8000 | 8968 | 8968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 15032 | 15032 | 0 | 0 | 3000 | 3000 | 1500 | 1500 | 968 | 968
|  | Change Reason ==> |  | TOTAL | 3988 | 0 | 3000 | 20857 | 0 | 0 | 0 | 0 | 3027 | 18809 | 1000 | 2012 | 949 | 2048 | [48 empty] | 0
RIV | 0001N | 79 | Riverside County Trans Commission (RCTC) | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10900001453 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | SR 79 realignment (Environmental) | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
RIV | 0076B | 91 | Caltrans | RIP | 0 | 0 | 0 | 3889 | 0 | 0 | 0 | 0 | 0 | 3889 | 0 | 0 | 0 | 0 | [11 empty] | 3889 | [36 empty] | 10900000890 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 7778 | 7778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15556 | 15556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 456610 | R0.9/R2.2 | Green River Road Interchange | IIP | 2049 | 145 | 0 | 12294 | 0 | 0 | 0 | 0 | 0 | 10062 | 512 | 1537 | 145 | 2232 | [11 empty] | 10062 |  |  |  |  | 512 | [7 empty] | 1537 | [8 empty] | 145 | [9 empty] | 2232 |  |  |  |  | 0 | [5 empty] | 7684 | 7684 | 725 | 725 | 0 | 0 | 33516 | 33516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40248 | 40248 | 512 | 512 | 1537 | 1537 | 290 | 290 | 8928 | 8928
|  | Change Reason ==> |  | TCRP | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | [11 empty] | 590 | [36 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1180 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360 | 2360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Demo | 0 | 0 | 0 | 4417 | 0 | 0 | 0 | 0 | 590 | 3827 | 0 | 0 | 0 | 0 |  |  |  | 590 | [7 empty] | 3827 | [36 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 8244 | 8244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2360 | 2360 | 15308 | 15308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 2049 | 145 | 0 | 21190 | 0 | 0 | 0 | 0 | 590 | 18368 | 512 | 1537 | 145 | 2232 | [48 empty] | 0
|  |  |  | Total RIP | 66010 | 4741 | 30474 | 47719 | 44981 | 75274 | 25415 | 25415
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 14790 | 14790 | 25415 | 25415 | 25415
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 26625 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 39289 | 02/03: 0
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 26721 | 02/03: 0
|  |  |  | Total RIP Eligible for Reprogramming | 0 | 4741 | 30474 | 32929 | 30191 | 23234 | 0 | 0
[8 empty] | 68144 | 30191 | 23234