## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
San Diego County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
SD | 2029 |  | North County Transit District | FTA Funds | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | [10 empty] | 2000 | [37 empty] | 11000000296 | [5 empty] | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T933SB |  | Oceanside Transit Center Parking Structure | RIP | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | [10 empty] | 1300 | [37 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 2600 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3900 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | IIP | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 0 | 0 | 0 | 0 | [10 empty] | 2700 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 5400 | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8100 | 8100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TCRP | 910 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 450 | 460 | 0 | 0 | [10 empty] | 590 | [5 empty] | 450 | [7 empty] | 460 | [23 empty] | 0 | [5 empty] | 3190 | 3190 | 0 | 0 | 1180 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1770 | 1770 | 450 | 450 | 460 | 460 | 0 | 0 | 0 | 0
|  |  |  | RSTP | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | [10 empty] | 1200 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (CITY) | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 400 | [47 empty] | 0 | [5 empty] | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 1310 | 0 | 7790 | 0 | 0 | 0 | 0 | 0 | 400 | 7790 | 450 | 460 | 0 | 0 | [48 empty] | 0
SD | 7402 |  | San Diego Association of Governments | RIP | 0 | 0 | 473 | 474 | 474 | 474 | 0 | 0 | 0 | 1895 | 0 | 0 | 0 | 0 | [10 empty] | 473 | 474 | 474 | 474 | [34 empty] | 11000000056 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 946 | 946 | 948 | 948 | 948 | 948 | 948 | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 8529 | 8529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 212554 |  | Planning, Programming and Monitoring | TOTAL | 0 | 0 | 473 | 474 | 474 | 474 | 0 | 0 | 0 | 1895 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SD | 7404 |  | San Diego Association of Governments | RIP | 0 | 0 | 1688 | 1738 | 1792 | 1824 | 0 | 0 | 0 | 7042 | 0 | 0 | 0 | 0 | [10 empty] | 1688 | 1738 | 1792 | 1824 | [34 empty] | 11000000058 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 3376 | 3376 | 3476 | 3476 | 3584 | 3584 | 3648 | 3648 | 0 | 0 | 0 | 0 | 0 | 0 | 31920 | 31920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 956103 |  | Regional Rideshare Program - San Diego | TOTAL | 0 | 0 | 1688 | 1738 | 1792 | 1824 | 0 | 0 | 0 | 7042 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SD | 7401B |  | San Diego Association of Governments | RIP | 0 | 0 | 1476 | 0 | 0 | 0 | 0 | 0 | 0 | 1476 | 0 | 0 | 0 | 0 | [10 empty] | 1476 | [37 empty] | 11000000306 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 2952 | 2952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4428 | 4428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | RSTP/CMAQ/TEA Reserve | TOTAL | 0 | 0 | 1476 | 0 | 0 | 0 | 0 | 0 | 0 | 1476 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SD | 7307 |  | San Diego Metropolitan Transit Development Board | RIP | 0 | 0 | 1000 | 1000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | [26 empty] | 1000 | 1000 | 2000 | [19 empty] | 11000000184 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 4000 | 4000 | 4000 | 4000 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 17000 | 0 | 0 | 0 | 0
|  |  | Mid-Coast Balboa LRT Extension | Loc Funds (XSD) | 0 | 1000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7000 | 0 | 0 | [25 empty] | 1000 | 6000 | [21 empty] | 0 | [5 empty] | 0 | 0 | 4000 | 4000 | 24000 | 24000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 1000 | 7000 | 1000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | [48 empty] | 0
SD | 0978 |  | San Diego Metropolitan Transit Development Board | FTA Funds | 0 | 801 | 1251 | 1675 | 50 | 0 | 0 | 0 | 0 | 2826 | 0 | 951 | 0 | 0 | [9 empty] | 638 | 988 | 1200 | [13 empty] | 163 | 263 | 475 | 50 | [19 empty] | 11000000293 | [5 empty] | 0 | 0 | 1928 | 1928 | 3028 | 3028 | 4300 | 4300 | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9040 | 9040 | 0 | 0 | 3265 | 3265 | 0 | 0 | 0 | 0
|  |  | Regional Automated Fare Technology | FTA Funds | 0 | 2401 | 3751 | 5025 | 150 | 0 | 0 | 0 | 0 | 8476 | 0 | 2851 | 0 | 0 | [9 empty] | 1913 | 2963 | 3600 | [13 empty] | 488 | 788 | 1425 | 150 | [19 empty] | 0 | [5 empty] | 0 | 0 | 5778 | 5778 | 9078 | 9078 | 12900 | 12900 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27115 | 27115 | 0 | 0 | 9790 | 9790 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | RIP | 0 | 0 | 7000 | 11000 | 1500 | 0 | 0 | 0 | 0 | 14280 | 0 | 5220 | 0 | 0 | [10 empty] | 5250 | 7830 | 1200 | [13 empty] | 1750 | 3170 | 300 | [19 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 17500 | 17500 | 28340 | 28340 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53070 | 53070 | 0 | 0 | 19430 | 19430 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 3202 | 12002 | 17700 | 1700 | 0 | 0 | 0 | 0 | 25582 | 0 | 9022 | 0 | 0 | [48 empty] | 0
SD | 0223B | 15 | Caltrans | RIP | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | [16 empty] | 4500 | [31 empty] | 11000000139 | RIP |  |  |  | X | 13500 | 13500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0
| 064800 | R10.7/R31.8 | I-15 Managed Lanes | TCRP | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | [16 empty] | 3500 | [31 empty] | 0 | [5 empty] | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | [48 empty] | 0
SD | 0672F | 15 | Caltrans | RIP | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | [26 empty] | 5000 | [21 empty] | 11000000283 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0
| 081001 | M27.8/M31.5 | Managed Lanes-North Segmt (North/South Stages) | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 135190 | 0 | 1229 | 122900 | 0 | 0 | 246 | 10815 | [6 empty] | 1229 | [7 empty] | 122900 | [23 empty] | 246 | [7 empty] | 10815 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313149 | 313149 | 0 | 0 | 8603 | 8603 | 860300 | 860300 | 0 | 0 | 0 | 0 | 1722 | 1722 | 75705 | 75705
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 5000 | 0 | 0 | 0 | 135190 | 0 | 1229 | 122900 | 0 | 5000 | 246 | 10815 | [48 empty] | 0
SD | 0672G | 15 | Caltrans | RIP | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | [25 empty] | 10000 | [22 empty] | 11000000284 | RIP |  |  |  | X | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0
| 081501 | M11.5/M19.5 | Managed Lanes (No/So Stages) South Segment | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 243342 | 0 | 6145 | 208930 | 0 | 0 | 1229 | 27038 | [6 empty] | 6145 | [7 empty] | 208930 | [23 empty] | 1229 | [7 empty] | 27038 |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 592378 | 592378 | 0 | 0 | 43015 | 43015 | 1462510 | 1462510 | 0 | 0 | 0 | 0 | 8603 | 8603 | 189266 | 189266
|  | Change Reason ==> |  | TOTAL | 0 | 10000 | 0 | 0 | 0 | 0 | 243342 | 0 | 6145 | 208930 | 0 | 10000 | 1229 | 27038 | [48 empty] | 0
SD | 0672 | 15 | Caltrans | Othr. State | 0 | 0 | 4136 | 0 | 0 | 0 | 0 | 0 | 0 | 4136 | 0 | 0 | 0 | 0 | [10 empty] | 4136 | [37 empty] | 11000000291 | [5 empty] | 0 | 0 | 0 | 0 | 8272 | 8272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12408 | 12408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0809_ | M18.8/M28.1 | San Diego - Managed Lanes (stage 1) Middle Segment | RIP | 0 | 0 | 0 | 17000 | 17000 | 17000 | 0 | 0 | 0 | 51000 | 0 | 0 | 0 | 0 | [11 empty] | 17000 | 17000 | 17000 | [34 empty] | 0 | RIP |  |  | GARVEE | X | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 34000 | 34000 | 34000 | 34000 | 34000 | 0 | 0 | 0 | 0 | 0 | 0 | 255000 | 255000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | IIP | 0 | 0 | 0 | 5800 | 5800 | 5800 | 0 | 0 | 0 | 17400 | 0 | 0 | 0 | 0 | [11 empty] | 5800 | 5800 | 5800 | [34 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 11600 | 11600 | 11600 | 11600 | 11600 | 11600 | 0 | 0 | 0 | 0 | 0 | 0 | 87000 | 87000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TCRP | 30800 | 5900 | 1000 | 0 | 0 | 0 | 0 | 0 | 12000 | 6900 | 0 | 17800 | 1000 | 0 | 12000 | [8 empty] | 5900 | 1000 | [13 empty] | 17800 | [7 empty] | 1000 | [15 empty] | 0 | [5 empty] | 88200 | 88200 | 11800 | 11800 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 14800 | 14800 | 0 | 0 | 17800 | 17800 | 1000 | 1000 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 5800 | 5800 | 0 | 11600 | 0 | 0 | 0 | 0 | [14 empty] | 5800 | 5800 | [32 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11600 | 11600 | 11600 | 11600 | 0 | 0 | 87000 | 87000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 17000 | 0 | 34000 | 0 | 0 | 0 | 0 | [14 empty] | 17000 | 17000 | [32 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34000 | 34000 | 34000 | 34000 | 0 | 0 | 255000 | 255000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | RSTP | 0 | 12 | 23415 | 0 | 0 | 0 | 0 | 0 | 0 | 23000 | 0 | 0 | 0 | 427 | [10 empty] | 23000 | [30 empty] | 12 | 415 | [5 empty] | 0 | [5 empty] | 0 | 0 | 72 | 72 | 48490 | 48490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69000 | 69000 | 0 | 0 | 0 | 0 | 0 | 0 | 1269 | 1269
|  |  |  | CMAQ | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 0 | 0 | 0 | 0 | [10 empty] | 11000 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 22000 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33000 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 30800 | 5912 | 39551 | 22800 | 22800 | 22800 | 22800 | 22800 | 12000 | 159036 | 0 | 17800 | 1000 | 427 | [48 empty] | 0
SD | 0135G | 5 | Caltrans | RIP | 615 | 0 | 5485 | 0 | 0 | 0 | 0 | 0 | 53 | 4850 | 126 | 410 | 26 | 635 | 53 | [9 empty] | 4850 | [5 empty] | 126 | [7 empty] | 410 | [7 empty] | 26 | [9 empty] | 635 | [5 empty] | 11000000137 | RIP |  |  |  | X | 2201 | 2201 | 0 | 0 | 13510 | 13510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 53 | 14550 | 14550 | 126 | 126 | 410 | 410 | 26 | 26 | 1905 | 1905
| 065100 | R34.8/R35.7 | Del Mar Heights Auxiliary Lane | TOTAL | 615 | 0 | 5485 | 0 | 0 | 0 | 0 | 0 | 53 | 4850 | 126 | 410 | 26 | 635 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SD | 0615 | 5 | Caltrans | RIP | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | [17 empty] | 2000 | [30 empty] | 11000000281 | RIP |  |  |  | X | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
| 235800 | R34.1/R54.6 | I-5 Widening for HOV, Mixed flow & Aux Lanes | RSTP | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | [16 empty] | 4000 | [31 empty] | 0 | [5 empty] | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Federal Disc. | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | [17 empty] | 4000 | [30 empty] | 0 | [5 empty] | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 4000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | [48 empty] | 0
SD | 0800 | 5 | Caltrans | RIP | 0 | 450 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 0 | 450 | 0 | 450 | [10 empty] | 5600 | [14 empty] | 450 | [16 empty] | 450 | [5 empty] | 11000000287 | RIP |  |  |  | X | 0 | 0 | 1800 | 1800 | 13900 | 13900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16800 | 16800 | 0 | 0 | 900 | 900 | 0 | 0 | 1350 | 1350
| 08080K | R0.0/R29.5 | TMS on I-5, I-805 and SR-94 (Loops) | TOTAL | 0 | 450 | 6050 | 0 | 0 | 0 | 0 | 0 | 0 | 5600 | 0 | 450 | 0 | 450 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SD | 0260 | 52 | Caltrans | RIP | 25500 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 16583 | 6000 | 0 | 2500 | 6417 | 0 | 16583 | [9 empty] | 6000 | [13 empty] | 2500 | [7 empty] | 6417 | [15 empty] | 11000000084 | RIP |  |  |  | X | 58668 | 58668 | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16583 | 16583 | 18000 | 18000 | 0 | 0 | 2500 | 2500 | 6417 | 6417 | 0 | 0
| 010611 | 14.7/16.3 | New Rte52 Fwy-Rte125 to Cuyamaca-Wst end | IIP | 3400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 1000 | 0 | [24 empty] | 2400 | [7 empty] | 1000 | [15 empty] | 0 | [5 empty] | 14600 | 14600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 2400 | 1000 | 1000 | 0 | 0
|  | Change Reason ==> |  | TCRP | 25000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 25000 | 20000 | 0 | 0 | 0 | 0 | 25000 | [9 empty] | 20000 | [37 empty] | 0 | [5 empty] | 25000 | 25000 | 0 | 0 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 25000 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | RSTP | 10100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10100 | 0 | 0 | 0 | 0 | 0 | 10100 | [47 empty] | 0 | [5 empty] | 10100 | 10100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10100 | 10100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Demo | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 2250 | [47 empty] | 0 | [5 empty] | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (LTF) | 14200 | 0 | 37260 | 0 | 0 | 0 | 0 | 0 | 14200 | 30240 | 0 | 0 | 0 | 7020 | 14200 | [9 empty] | 30240 | [31 empty] | 7020 | [5 empty] | 0 | [5 empty] | 14200 | 14200 | 0 | 0 | 102600 | 102600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14200 | 14200 | 90720 | 90720 | 0 | 0 | 0 | 0 | 0 | 0 | 21060 | 21060
|  |  |  | TOTAL | 80450 | 0 | 63260 | 0 | 0 | 0 | 0 | 0 | 68133 | 56240 | 0 | 4900 | 7417 | 7020 | [48 empty] | 0
SD | 0260F | 52 | Caltrans | RIP | 3500 | 19495 | 15000 | 15000 | 11110 | 71395 | 0 | 0 | 56110 | 63180 | 0 | 4105 | 3890 | 8215 |  | 15000 | 15000 | 15000 | 11110 | [8 empty] | 63180 | [10 empty] | 3500 | 605 | [7 empty] | 3890 | [11 empty] | 8215 |  |  | 11000000085 | RIP |  |  |  | X | 14000 | 14000 | 36870 | 36870 | 15000 | 15000 | 15000 | 15000 | 11110 | 11110 | 175650 | 175650 | 0 | 0 | 0 | 0 | 190550 | 190550 | 379080 | 379080 | 0 | 0 | 4710 | 4710 | 7780 | 7780 | 49290 | 49290
| 010621 | 16.2/17.7 | New Rte 52 Freeway - Cuyamaca to Rte 67 | Future Need | 0 | 0 | 7955 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2445 | 5510 | 0 | [26 empty] | 2445 | [7 empty] | 5510 | [13 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 37330 | 37330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7335 | 7335 | 16530 | 16530 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (LTF) | 0 | 0 | 5690 | 4900 | 0 | 0 | 0 | 0 | 10590 | 0 | 0 | 0 | 0 | 0 |  |  | 5690 | 4900 | [44 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 5690 | 5690 | 4900 | 4900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36670 | 36670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 3500 | 19495 | 28645 | 19900 | 11110 | 71395 | 0 | 0 | 66700 | 63180 | 0 | 6550 | 9400 | 8215 | [48 empty] | 0
SD | 0377D | 54 | Caltrans | RIP | 0 | 500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 6500 | 0 | 0 | [17 empty] | 500 | [8 empty] | 6500 | [21 empty] | 11000000295 | RIP |  |  |  | X | 0 | 0 | 1500 | 1500 | 26000 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 19500 | 19500 | 0 | 0 | 0 | 0
|  | 1.8/6.7 | PAED/Design for SR 54/SR 125 HOV lanes | Future Need | 0 | 0 | 0 | 0 | 103000 | 0 | 0 | 0 | 0 | 90000 | 0 | 0 | 0 | 13000 | [12 empty] | 90000 | [31 empty] | 13000 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 258000 | 258000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450000 | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | 65000 | 65000
|  | Change Reason ==> |  | TOTAL | 0 | 500 | 6500 | 0 | 103000 | 0 | 0 | 0 | 0 | 90000 | 500 | 6500 | 0 | 13000 | [48 empty] | 0
SD | 0625 | 805 | Caltrans | RIP | 0 | 100 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 0 | 100 | 0 | 100 | [10 empty] | 960 | [14 empty] | 100 | [16 empty] | 100 | [5 empty] | 11000000288 | RIP |  |  |  | X | 0 | 0 | 400 | 400 | 2520 | 2520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | 2880 | 0 | 0 | 200 | 200 | 0 | 0 | 300 | 300
| 24030K | R11.4/R49.6 | TMS (I-5, I-805, SR-52 and SR-94) CMS | TOTAL | 0 | 100 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 0 | 100 | 0 | 100 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SD | 0932 | 805 | Caltrans | RIP | 0 | 640 | 8540 | 0 | 0 | 0 | 0 | 0 | 0 | 7900 | 0 | 640 | 0 | 640 | [10 empty] | 7900 | [14 empty] | 640 | [16 empty] | 640 | [5 empty] | 11000000289 | RIP |  |  |  | X | 0 | 0 | 2560 | 2560 | 19640 | 19640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23700 | 23700 | 0 | 0 | 1280 | 1280 | 0 | 0 | 1920 | 1920
| 240200 | 5.8/13.0 | Traffic Mgmt Syst (I-5,I-805, & SR 94) Ramp Meters | TOTAL | 0 | 640 | 8540 | 0 | 0 | 0 | 0 | 0 | 0 | 7900 | 0 | 640 | 0 | 640 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SD | 0374K | 905 | Caltrans | GF IIP | 2237 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 1836 | 396 | 5 | 0 | [10 empty] | 5000 | [5 empty] | 1836 | [7 empty] | 396 | [7 empty] | 5 | [15 empty] | 11000000094 | [5 empty] | 7117 | 7117 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 15000 | 1836 | 1836 | 396 | 396 | 5 | 5 | 0 | 0
| 093160 | 5.7/12.0 | New Route 905 Freeway - Otay Mesa | RIP | 0 | 0 | 22496 | 0 | 0 | 0 | 0 | 0 | 0 | 20576 | 0 | 0 | 0 | 1920 | [10 empty] | 20576 | [31 empty] | 1920 | [5 empty] | 0 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 52672 | 52672 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61728 | 61728 | 0 | 0 | 0 | 0 | 0 | 0 | 5760 | 5760
|  | Change Reason ==> |  | IIP | 16621 | 0 | 73890 | 0 | 0 | 0 | 0 | 0 | 0 | 65790 | 2771 | 11850 | 2000 | 8100 | [10 empty] | 65790 | [5 empty] | 2771 | [7 empty] | 11850 | [7 empty] | 2000 | [9 empty] | 8100 | [5 empty] | 0 | [5 empty] | 65713 | 65713 | 0 | 0 | 180180 | 180180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197370 | 197370 | 2771 | 2771 | 11850 | 11850 | 2000 | 2000 | 24300 | 24300
|  |  |  | TCRP | 0 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 21000 | 0 | 0 | 0 | 0 | 0 |  | 21000 | [46 empty] | 0 | [5 empty] | 0 | 0 | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42000 | 42000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 64756 | 0 | 0 | 0 | 0 | 0 | 55931 | 0 | 0 | 0 | 8825 | [11 empty] | 55931 | [31 empty] | 8825 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 164812 | 164812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223724 | 223724 | 0 | 0 | 0 | 0 | 0 | 0 | 35300 | 35300
|  |  |  | Federal Disc. | 0 | 0 | 7282 | 0 | 0 | 0 | 0 | 0 | 0 | 7282 | 0 | 0 | 0 | 0 | [10 empty] | 7282 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 14564 | 14564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21846 | 21846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Federal Disc. | 2490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | 0 | 0 | 0 | 0 | 0 | 2490 | [47 empty] | 0 | [5 empty] | 2490 | 2490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2490 | 2490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Federal Disc. | 4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4096 | 0 | 0 | 0 | 0 | 0 | 4096 | [47 empty] | 0 | [5 empty] | 4096 | 4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4096 | 4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Federal Disc. | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500 | [47 empty] | 0 | [5 empty] | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Demo | 0 | 29114 | 11371 | 0 | 0 | 0 | 0 | 0 | 29114 | 11371 | 0 | 0 | 0 | 0 |  | 29114 | [8 empty] | 11371 | [37 empty] | 0 | [5 empty] | 0 | 0 | 29114 | 29114 | 22742 | 22742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58228 | 58228 | 34113 | 34113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (CITY) | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 4000 | [47 empty] | 0 | [5 empty] | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 36944 | 50114 | 120039 | 64756 | 0 | 0 | 0 | 0 | 68200 | 165950 | 4607 | 12246 | 2005 | 18845 | [48 empty] | 0
|  |  |  | Total RIP | 34115 | 33185 | 89068 | 46212 | 33876 | 90693 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 17000 | 17000 | 17000 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 17479 | 02/03: 18185
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 16636 | 02/03: 15000
|  |  |  | Total RIP Eligible for Reprogramming | 0 | 0 | 89068 | 29212 | 16876 | 73693 | 0 | 0
[8 empty] | 118280 | 16876 | 73693