## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
San Francisco County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
SF | 2014R |  | Bay Area Rapid Transit District | RIP | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442 | 0 | 0 | 0 | [17 empty] | 442 | [30 empty] | 20600002152 | RIP |  |  |  |  | 0 | 0 | 1326 | 1326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884 | 884 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | BART Embarcadero and Montgomery Engineer | TOTAL | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 1003F |  | Bay Area Rapid Transit District | RIP | 0 | 0 | 7 | 70 | 2099 | 0 | 0 | 0 | 0 | 2099 | 7 | 70 | 0 | 0 | [12 empty] | 2099 | [5 empty] | 7 | [8 empty] | 70 | [20 empty] | 20600002177 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 21 | 21 | 280 | 280 | 4198 | 4198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10495 | 10495 | 21 | 21 | 280 | 280 | 0 | 0 | 0 | 0
|  | 0.0 | BART 16th St Mission Station Plaza Impro | Future Need | 0 | 0 | 1648 | 0 | 0 | 0 | 0 | 0 | 0 | 1055 | 53 | 540 | 0 | 0 | [10 empty] | 1055 | [7 empty] | 53 | [7 empty] | 540 | [21 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 4429 | 4429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3165 | 3165 | 159 | 159 | 1620 | 1620 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 1655 | 70 | 2099 | 0 | 0 | 0 | 0 | 3154 | 60 | 610 | 0 | 0 | [48 empty] | 0
SF | 2014M |  | Bay Area Rapid Transit District | RIP | 0 | 0 | 63 | 0 | 1017 | 0 | 0 | 0 | 0 | 1017 | 0 | 63 | 0 | 0 | [12 empty] | 1017 | [13 empty] | 63 | [21 empty] | 20600002220 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 252 | 252 | 0 | 0 | 2034 | 2034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5085 | 5085 | 0 | 0 | 189 | 189 | 0 | 0 | 0 | 0
|  | 0.0 | BART Downtown San Francisco Stations Tal | TOTAL | 0 | 0 | 63 | 0 | 1017 | 0 | 0 | 0 | 0 | 1017 | 0 | 63 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2014N |  | Bay Area Rapid Transit District | RIP | 0 | 0 | 50 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 50 | 0 | 0 | [12 empty] | 1200 | [13 empty] | 50 | [21 empty] | 20600002221 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0
|  | 0.0 | BART SF Stations Platform Edge Tiles Rep | TOTAL | 0 | 0 | 50 | 0 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 50 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2014B |  | Department of Parking & Transportation | RIP | 0 | 0 | 0 | 0 | 136 | 1135 | 0 | 0 | 0 | 1135 | 0 | 136 | 0 | 0 | [13 empty] | 1135 | [14 empty] | 136 | [19 empty] | 20600002141 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 544 | 544 | 2270 | 2270 | 0 | 0 | 0 | 0 | 0 | 0 | 6810 | 6810 | 0 | 0 | 680 | 680 | 0 | 0 | 0 | 0
|  | 0.0 | Oak and Fell Streets ITMS Deployment | TOTAL | 0 | 0 | 0 | 0 | 136 | 1135 | 0 | 0 | 0 | 1135 | 0 | 136 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2014D |  | Department of Parking & Transportation | RIP | 0 | 0 | 0 | 50 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 50 | 0 | 0 | [12 empty] | 150 | [14 empty] | 50 | [20 empty] | 20600002143 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0
|  | 0.0 | Addison and Digby Traffic Circle | TOTAL | 0 | 0 | 0 | 50 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 50 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2014F |  | Department of Parking & Transportation | RIP | 0 | 0 | 6 | 44 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 6 | 0 | 0 | [11 empty] | 44 | [14 empty] | 6 | [21 empty] | 20600002145 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 24 | 24 | 88 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 | 0 | 0 | 18 | 18 | 0 | 0 | 0 | 0
|  | 0.0 | Median Refuge Accessibility Retrofit | Loc Funds (GEN) | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 0 | 0 | [10 empty] | 5 | [6 empty] | 2 | [30 empty] | 0 | [5 empty] | 0 | 0 | 6 | 6 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 2 | 11 | 44 | 0 | 0 | 0 | 0 | 0 | 49 | 2 | 6 | 0 | 0 | [48 empty] | 0
SF | 2014G |  | Department of Parking & Transportation | RIP | 0 | 0 | 0 | 14 | 186 | 0 | 0 | 0 | 0 | 186 | 0 | 14 | 0 | 0 | [12 empty] | 186 | [14 empty] | 14 | [20 empty] | 20600002146 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 56 | 372 | 372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930 | 930 | 0 | 0 | 56 | 56 | 0 | 0 | 0 | 0
|  | 0.0 | Phelan Ave. Crosswalk & Traffic Calming. | Loc Funds (GEN) | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | [24 empty] | 20 | [23 empty] | 0 | [5 empty] | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 20 | 0 | 0 | 14 | 186 | 0 | 0 | 0 | 0 | 186 | 0 | 34 | 0 | 0 | [48 empty] | 0
SF | 2014J |  | Golden Gate Bridge, Highway and Transportation District | RIP | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | [13 empty] | 1000 | [34 empty] | 20600002148 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | GGBHTD San Francisco Ferry Lay Berth | RIP (MRN) | 0 | 0 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | 305 | 0 | 0 | 0 | 0 | [13 empty] | 305 | [34 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 610 | 610 | 0 | 0 | 0 | 0 | 0 | 0 | 1830 | 1830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (GEN) | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 100 | 0 | 0 | [8 empty] | 250 | [15 empty] | 100 | [23 empty] | 0 | [5 empty] | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 350 | 0 | 0 | 0 | 0 | 1305 | 0 | 0 | 0 | 1555 | 0 | 100 | 0 | 0 | [48 empty] | 0
SF | 2014P |  | Golden Gate Bridge, Highway and Transportation District | RIP | 0 | 0 | 0 | 0 | 450 | 1800 | 0 | 0 | 0 | 1800 | 0 | 450 | 0 | 0 | [13 empty] | 1800 | [14 empty] | 450 | [19 empty] | 20600002149 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 1800 | 3600 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 10800 | 10800 | 0 | 0 | 2250 | 2250 | 0 | 0 | 0 | 0
|  | 0.0 | GGBHTD San Francisco Ferry Terminal Reha | TOTAL | 0 | 0 | 0 | 0 | 450 | 1800 | 0 | 0 | 0 | 1800 | 0 | 450 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2131 |  | Metropolitan Transportation Commission | RIP | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | [10 empty] | 46 | [37 empty] | 10600000241 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 92 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073324 |  | Planning, Programming and Monitoring | TOTAL | 0 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2133 |  | Metropolitan Transportation Commission | RIP | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 0 | 0 | 0 | [8 empty] | 307 | [39 empty] | 10600000243 | RIP |  |  |  |  | 614 | 614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073344 |  | Regional Rideshare Program | TOTAL | 307 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 307 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2164 |  | Metropolitan Transportation Commission | RIP | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | [8 empty] | 9 | [39 empty] | 10600000250 | RIP |  |  |  |  | 18 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 072444 |  | CMAQ Match Reserve | TOTAL | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2014L |  | Peninsula Joint Powers Board | FTA Funds | 3660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3660 | 0 | 0 | 0 | [16 empty] | 3660 | [31 empty] | 10600000941 | [5 empty] | 10980 | 10980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3660 | 3660 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Caltrain Electrification | RIP | 0 | 0 | 0 | 0 | 0 | 4300 | 0 | 0 | 0 | 0 | 0 | 4300 | 0 | 0 | [29 empty] | 4300 | [18 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17200 | 17200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25800 | 25800 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 20000 | 0 | 541800 | 0 | 0 | 20000 | 541800 | 0 | 0 | 0 | 0 |  |  |  | 20000 | [9 empty] | 541800 | [34 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 1083600 | 1083600 | 0 | 0 | 0 | 0 | 80000 | 80000 | 3250800 | 3250800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (JPB) | 4000 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | [24 empty] | 4000 | 8000 | [22 empty] | 0 | [5 empty] | 16000 | 16000 | 32000 | 32000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (LTF) | 5915 | 1300 | 12025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14940 | 4300 | 0 | 0 | [16 empty] | 5915 |  | 9025 | [6 empty] | 1300 | 3000 | [21 empty] | 0 | [5 empty] | 17745 | 17745 | 5200 | 5200 | 39075 | 39075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32990 | 32990 | 11600 | 11600 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 13575 | 9300 | 12025 | 20000 | 0 | 546100 | 0 | 0 | 20000 | 541800 | 18600 | 20600 | 0 | 0 | [48 empty] | 0
SF | 2014K |  | Peninsula Joint Powers Board | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 20600002150 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Caltrain Rapid Rail Improvements | TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2014C |  | San Francisco County | RIP | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | [12 empty] | 1300 | [35 empty] | 20600002142 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Crosswalk restripping & crossing sign upgrades. | TOTAL | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | 1300 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2007 |  | San Francisco County Transportation Authority | RIP | 52 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | [8 empty] | 52 |  | 59 | [37 empty] | 10600000684 | RIP |  |  |  |  | 104 | 104 | 0 | 0 | 118 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0U9301 |  | Planning, Programming and Monitoring | TOTAL | 52 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 1007 |  | San Francisco Department of Parking and Traffic | RIP | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | [10 empty] | 700 | [37 empty] | 10600000693 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1400 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073034 |  | 3rd St Integrated Traffic Management | TOTAL | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 2014E |  | San Francisco Department of Parking and Traffic | RIP | 0 | 0 | 20 | 315 | 0 | 0 | 0 | 0 | 0 | 315 | 0 | 20 | 0 | 0 | [11 empty] | 315 | [14 empty] | 20 | [21 empty] | 20600002144 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 80 | 80 | 630 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1260 | 1260 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
|  | 0.0 | Audible Pedestrian Signals & Pushbuttons | Loc Funds (GEN) | 7 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 7 | 0 | 0 | 0 | [9 empty] | 38 | [6 empty] | 7 | [31 empty] | 0 | [5 empty] | 21 | 21 | 76 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 76 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 7 | 38 | 20 | 315 | 0 | 0 | 0 | 0 | 0 | 353 | 7 | 20 | 0 | 0 | [48 empty] | 0
SF | 2014T |  | San Francisco Department of Parking and Traffic | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 20600002153 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073404 | 0.0 | Laguna Honda Blvd. Bike Ln. extension/rehab. | Future Need | 0 | 0 | 0 | 0 | 1426 | 0 | 0 | 0 | 0 | 1426 | 0 | 0 | 0 | 0 | [12 empty] | 1426 | [35 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2852 | 2852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7130 | 7130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 0 | 0 | 1426 | 0 | 0 | 0 | 0 | 1426 | 0 | 0 | 0 | 0 | [48 empty] | 0
SF | 2134 |  | San Francisco Municipal Railway (MUNI) | FTA Funds | 1093 | 22448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23541 | 0 | 0 | 0 | 0 | [8 empty] | 1093 | 22448 | [38 empty] | 10600000244 | [5 empty] | 2186 | 2186 | 44896 | 44896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45989 | 45989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| R743SA |  | SF Muni 3rd Street Light Rail Extension | RIP | 0 | 0 | 22570 | 0 | 0 | 0 | 0 | 0 | 0 | 22570 | 0 | 0 | 0 | 0 | [10 empty] | 22570 | [37 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 45140 | 45140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67710 | 67710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TCRP | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 0 | 0 | 0 | 0 | [8 empty] | 126000 | [39 empty] | 0 | [5 empty] | 252000 | 252000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126000 | 126000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 49826 | 941 | 0 | 0 | 0 | 0 | 0 | 50767 | 0 | 0 | 0 | 0 | [10 empty] | 49826 | 941 | [36 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 99652 | 99652 | 1882 | 1882 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153242 | 153242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | RSTP | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | [8 empty] | 2500 | [39 empty] | 0 | [5 empty] | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (GEN) | 223439 | 159370 | 0 | 0 | 33547 | 0 | 0 | 0 | 0 | 365589 | 0 | 50767 | 0 | 0 | [8 empty] | 172672 | 159370 |  |  | 33547 | [11 empty] | 50767 | [23 empty] | 0 | [5 empty] | 548412 | 548412 | 318740 | 318740 | 0 | 0 | 0 | 0 | 67094 | 67094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659147 | 659147 | 0 | 0 | 50767 | 50767 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 353032 | 181818 | 72396 | 941 | 33547 | 0 | 0 | 0 | 0 | 590967 | 0 | 50767 | 0 | 0 | [48 empty] | 0
SF | 2014S |  | San Francisco Municipal Railway (MUNI) | FTA Funds | 41904.51 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47479.51 | 0 | 1925 | 0 | 0 | [8 empty] | 39979.51 | 7500 | [14 empty] | 1925 | [23 empty] | 10600000924 | [5 empty] | 87659.02 | 87659.02 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54979.51 | 54979.51 | 0 | 0 | 1925 | 1925 | 0 | 0 | 0 | 0
|  | 0.0 | SF Muni Rail Replacement Program 1998-20 | Othr. State | 229.322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.322 | 0 | 0 | [24 empty] | 229.322 | [23 empty] | 0 | [5 empty] | 917.288 | 917.288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 229.322 | 229.322 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Othr. State | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | [24 empty] | 500 | [23 empty] | 0 | [5 empty] | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0
|  |  |  | Othr. State | 2186.25 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386.25 | 0 | 1404 | 0 | 0 | [8 empty] | 1386.25 | [15 empty] | 800 | 604 | [22 empty] | 0 | [5 empty] | 5972.5 | 5972.5 | 2416 | 2416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386.25 | 1386.25 | 0 | 0 | 2008 | 2008 | 0 | 0 | 0 | 0
|  |  |  | RIP | 2655.899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2655.899 | 0 | 0 | 0 | 0 | [8 empty] | 2655.899 | [39 empty] | 0 | RIP |  |  |  |  | 5311.798 | 5311.798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2655.899 | 2655.899 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | RIP | 4040.099 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 4040.099 | 0 | 1000 | 0 | 0 | [8 empty] | 4040.099 | [18 empty] | 1000 | [20 empty] | 0 | RIP |  |  |  |  | 8080.198 | 8080.198 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4040.099 | 4040.099 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0
|  |  |  | RIP | 6568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6568 | 0 | 0 | 0 | 0 | [8 empty] | 6568 | [39 empty] | 0 | RIP |  |  |  |  | 13136 | 13136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6568 | 6568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 9375 | 9057 | 9375 | 9375 | 9375 | 9375 | 0 | 51171 | 0 | 4761 | 0 | 0 | [10 empty] | 7500 | 8046 | 7500 | 9375 | 9375 | 9375 | [10 empty] | 1875 | 1011 | 1875 | [19 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 22500 | 22500 | 20136 | 20136 | 22500 | 22500 | 18750 | 18750 | 18750 | 18750 | 18750 | 18750 | 0 | 0 | 289059 | 289059 | 0 | 0 | 19044 | 19044 | 0 | 0 | 0 | 0
|  |  |  | RSTP | 4960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4960 | 0 | 0 | [24 empty] | 4960 | [23 empty] | 0 | [5 empty] | 19840 | 19840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4960 | 4960 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (GEN) | 6740.508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 0 | 4640.508 | 0 | 0 | [8 empty] | 2100 | [15 empty] | 4640.508 | [23 empty] | 0 | [5 empty] | 22762.032 | 22762.032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100 | 2100 | 0 | 0 | 4640.508 | 4640.508 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 69784.588 | 8104 | 9375 | 10057 | 9375 | 9375 | 9375 | 9375 | 0 | 115400.758 | 0 | 19419.83 | 0 | 0 | [48 empty] | 0
SF | 2014H |  | San Francisco Municipal Railway (MUNI) | RIP | 0 | 0 | 0 | 0 | 1140 | 8060 | 0 | 0 | 0 | 8060 | 0 | 1140 | 0 | 0 | [13 empty] | 8060 | [14 empty] | 1140 | [19 empty] | 20600002147 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4560 | 4560 | 16120 | 16120 | 0 | 0 | 0 | 0 | 0 | 0 | 48360 | 48360 | 0 | 0 | 5700 | 5700 | 0 | 0 | 0 | 0
|  | 0.0 | 1401 Bryant Overhead Lines Building Seis | Loc Funds (GEN) | 310 | 360 | 870 | 1160 | 0 | 0 | 0 | 0 | 0 | 2600 | 0 | 100 | 0 | 0 | [8 empty] | 210 | 360 | 870 | 1160 | [12 empty] | 100 | [23 empty] | 0 | [5 empty] | 820 | 820 | 720 | 720 | 1740 | 1740 | 2320 | 2320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8180 | 8180 | 0 | 0 | 100 | 100 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 310 | 360 | 870 | 1160 | 1140 | 8060 | 0 | 0 | 0 | 10660 | 0 | 1240 | 0 | 0 | [48 empty] | 0
SF | 2014A |  | San Francisco, City of | RIP | 0 | 0 | 0 | 0 | 0 | 4768 | 0 | 0 | 0 | 4768 | 0 | 0 | 0 | 0 | [13 empty] | 4768 | [34 empty] | 20600002140 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9536 | 9536 | 0 | 0 | 0 | 0 | 0 | 0 | 28608 | 28608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | 3rd Street/Bayshore Pavement Rehab. | TOTAL | 0 | 0 | 0 | 0 | 0 | 4768 | 0 | 0 | 0 | 4768 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SF | 0619A | 101 | Caltrans | RIP | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | [25 empty] | 5000 | [22 empty] | 10600000903 | RIP |  |  |  | X | 0 | 0 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0
| 163700 | 8.3/9. | Doyle Drive Replacement | RIP | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | [18 empty] | 3000 | [29 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | IIP | 0 | 28000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28000 | 0 | 0 | [25 empty] | 28000 | [22 empty] | 0 | [5 empty] | 0 | 0 | 112000 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56000 | 56000 | 0 | 0 | 0 | 0
|  |  |  | TCRP | 3000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 12000 | 0 | 0 | [16 empty] | 3000 | [8 empty] | 12000 | [22 empty] | 0 | [5 empty] | 9000 | 9000 | 48000 | 48000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 24000 | 24000 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 14000 | 368000 | 0 | 0 | 0 | 10000 | 350000 | 0 | 0 | 4000 | 18000 |  |  |  | 10000 | [8 empty] | 350000 | [22 empty] | 4000 | [8 empty] | 18000 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 808000 | 808000 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 40000 | 1750000 | 1750000 | 0 | 0 | 0 | 0 | 16000 | 16000 | 90000 | 90000
|  |  |  | Demo | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0 | 0 | 0 | [16 empty] | 7200 | [31 empty] | 0 | [5 empty] | 21600 | 21600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 7200 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 10200 | 45000 | 3000 | 14000 | 368000 | 0 | 0 | 0 | 10000 | 350000 | 13200 | 45000 | 4000 | 18000 | [48 empty] | 0
|  |  |  | Total RIP | 13631.998 | 5442 | 26521 | 1493 | 7678 | 21063 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 0 | 5000
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 0 | 0
|  |  |  | Total RIP Eligible for Reprogramming | 13631.998 | 442 | 26521 | 1493 | 7678 | 21063 | 0 | 0
[8 empty] | 42087.998 | 7678 | 21063