## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
San Joaquin County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
SJ | 3K40 |  | Escalon, City of | RIP | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | [13 empty] | 1400 | [34 empty] | 11200000154 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 8400 | 8400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | So McHenry Ave. Improvement & Rehab | Loc Funds (CITY) | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 40 | 0 | 0 | [17 empty] | 10 | [7 empty] | 40 | [22 empty] | 0 | [5 empty] | 0 | 0 | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 80 | 80 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 50 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 1400 | 10 | 40 | 0 | 0 | [48 empty] | 0
SJ | 3K41 |  | Lathrop,City of | RIP | 0 | 200 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 800 | 0 | 0 | [17 empty] | 200 | [8 empty] | 800 | [21 empty] | 11200000155 | RIP |  |  |  |  | 0 | 0 | 600 | 600 | 3200 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 2400 | 2400 | 0 | 0 | 0 | 0
|  |  | Lathrop Rd. Grade Sep / UPRR | Future Need | 0 | 0 | 0 | 2000 | 8000 | 0 | 0 | 0 | 2000 | 8000 | 0 | 0 | 0 | 0 |  |  |  | 2000 | [8 empty] | 8000 | [35 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 16000 | 16000 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 8000 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 200 | 800 | 2000 | 8000 | 0 | 0 | 0 | 2000 | 8000 | 200 | 800 | 0 | 0 | [48 empty] | 0
SJ | 3K43 |  | Lathrop,City of | RIP | 0 | 0 | 0 | 0 | 846 | 0 | 0 | 0 | 0 | 846 | 0 | 0 | 0 | 0 | [12 empty] | 846 | [35 empty] | 11200000157 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1692 | 1692 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4230 | 4230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Louise Ave. Rehab and Widening (Ph 1) | Loc Funds (CITY) | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 30 | 0 | 0 | 0 |  | 50 | [15 empty] | 30 | [30 empty] | 0 | [5 empty] | 0 | 0 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (XSJ) | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | [25 empty] | 40 | [22 empty] | 0 | [5 empty] | 0 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 120 | 0 | 0 | 846 | 0 | 0 | 0 | 50 | 846 | 30 | 40 | 0 | 0 | [48 empty] | 0
SJ | 3K44 |  | Lathrop,City of | RIP | 0 | 0 | 0 | 0 | 620 | 1965 | 0 | 0 | 620 | 1965 | 0 | 0 | 0 | 0 |  |  |  |  | 620 | [8 empty] | 1965 | [34 empty] | 11200000158 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620 | 620 | 3930 | 3930 | 0 | 0 | 0 | 0 | 3100 | 3100 | 11790 | 11790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Louise Rd. Rehab & Widening (Phase II) | Loc Funds (CITY) | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | [17 empty] | 25 | [30 empty] | 0 | [5 empty] | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (XSJ) | 0 | 220 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 220 | 0 | 0 | [11 empty] | 35 | [13 empty] | 220 | [22 empty] | 0 | [5 empty] | 0 | 0 | 880 | 880 | 0 | 0 | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 140 | 0 | 0 | 440 | 440 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 245 | 0 | 35 | 620 | 1965 | 0 | 0 | 620 | 2000 | 25 | 220 | 0 | 0 | [48 empty] | 0
SJ | 2K57 |  | Lodi, City of | RIP | 1856 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2856 | 0 | 0 | 0 | 0 | [8 empty] | 1856 | 1000 | [38 empty] | 11200000108 | RIP |  |  |  |  | 3712 | 3712 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3856 | 3856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Lower Sacramento Road Widening | Loc Funds (CITY) | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 69 | 207 | 0 | 0 | [8 empty] | 328 | [7 empty] | 69 | [7 empty] | 207 | [23 empty] | 0 | [5 empty] | 1691 | 1691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 328 | 69 | 69 | 207 | 207 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 2460 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3184 | 69 | 207 | 0 | 0 | [48 empty] | 0
SJ | 3K57 |  | Lodi, City of | RIP | 0 | 0 | 0 | 0 | 741 | 0 | 0 | 0 | 0 | 741 | 0 | 0 | 0 | 0 | [12 empty] | 741 | [35 empty] | 11200000172 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1482 | 1482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3705 | 3705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Stockton Street Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 741 | 0 | 0 | 0 | 0 | 741 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SJ | 3K47 |  | Ripon, City of | RIP | 0 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | [13 empty] | 1102 | [34 empty] | 11200000162 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2204 | 2204 | 0 | 0 | 0 | 0 | 0 | 0 | 6612 | 6612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Main and Stockton St. Rehabilitation | Loc Funds (CITY) | 0 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 50 | 100 | 0 | 0 | [10 empty] | 248 | [7 empty] | 50 | [7 empty] | 100 | [21 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 1046 | 1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 744 | 744 | 150 | 150 | 300 | 300 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 398 | 0 | 0 | 1102 | 0 | 0 | 0 | 1350 | 50 | 100 | 0 | 0 | [48 empty] | 0
SJ | 3K48 |  | Ripon, City of | RIP | 0 | 0 | 0 | 0 | 0 | 1925 | 0 | 0 | 0 | 1925 | 0 | 0 | 0 | 0 | [13 empty] | 1925 | [34 empty] | 11200000163 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 3850 | 0 | 0 | 0 | 0 | 0 | 0 | 11550 | 11550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | South Frontage Rd. and Wilma Over Crossing | Loc Funds (CITY) | 0 | 0 | 825 | 0 | 0 | 0 | 0 | 0 | 200 | 425 | 50 | 150 | 0 | 0 |  |  | 200 | [7 empty] | 425 | [7 empty] | 50 | [7 empty] | 150 | [21 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 1800 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 1275 | 1275 | 150 | 150 | 450 | 450 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 825 | 0 | 0 | 1925 | 0 | 0 | 200 | 2350 | 50 | 150 | 0 | 0 | [48 empty] | 0
SJ | 2031 |  | SJRRC - San Joaquin Regional Rail Commission | RIP | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | [12 empty] | 1000 | [35 empty] | 11200000140 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 90.9 | Stockton SP Depot Restoration | IIP | 0 | 0 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | 3400 | 0 | 0 | 0 | 0 | [12 empty] | 3400 | [35 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6800 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17000 | 17000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (XSJ) | 8173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 7200 | 0 | 753 | 0 | 0 | 220 | [7 empty] | 7200 | [15 empty] | 753 | [23 empty] | 0 | [5 empty] | 17632 | 17632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 7200 | 7200 | 0 | 0 | 753 | 753 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 8173 | 0 | 0 | 0 | 4400 | 0 | 0 | 0 | 220 | 11600 | 0 | 753 | 0 | 0 | [48 empty] | 0
SJ | 3K59 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | [13 empty] | 1500 | [34 empty] | 11200000142 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | McHenry Avenue Improvements | Local HBRR | 0 | 0 | 0 | 0 | 10647 | 0 | 0 | 0 | 0 | 10647 | 0 | 0 | 0 | 0 | [12 empty] | 10647 | [35 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21294 | 21294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53235 | 53235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CO) | 0 | 300 | 995 | 0 | 1960 | 0 | 0 | 0 | 13 | 1960 | 300 | 982 | 0 | 0 |  |  | 13 | [9 empty] | 1960 |  |  |  |  | 300 | [8 empty] | 982 | [21 empty] | 0 | [5 empty] | 0 | 0 | 900 | 900 | 3941 | 3941 | 0 | 0 | 3920 | 3920 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 39 | 9800 | 9800 | 600 | 600 | 2946 | 2946 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (XSJ) | 0 | 300 | 997 | 0 | 955 | 0 | 0 | 0 | 14 | 955 | 300 | 983 | 0 | 0 |  |  | 14 | [9 empty] | 955 |  |  |  |  | 300 | [8 empty] | 983 | [21 empty] | 0 | [5 empty] | 0 | 0 | 900 | 900 | 3946 | 3946 | 0 | 0 | 1910 | 1910 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | 4775 | 4775 | 600 | 600 | 2949 | 2949 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 600 | 1992 | 0 | 13562 | 1500 | 0 | 0 | 27 | 15062 | 600 | 1965 | 0 | 0 | [48 empty] | 0
SJ | 3K60 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 209 | 0 | 0 | 0 | 196 | 0 | 13 | 0 | 0 | [13 empty] | 196 | [15 empty] | 13 | [18 empty] | 11200000143 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 444 | 444 | 0 | 0 | 0 | 0 | 0 | 0 | 1176 | 1176 | 0 | 0 | 78 | 78 | 0 | 0 | 0 | 0
|  |  | Carpenter Road Rehabilitaion | Loc Funds (LTF) | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 3 | 7 | 0 | 0 | [9 empty] | 104 | [7 empty] | 3 | [7 empty] | 7 | [22 empty] | 0 | [5 empty] | 0 | 0 | 245 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 208 | 6 | 6 | 14 | 14 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 114 | 0 | 0 | 0 | 209 | 0 | 0 | 0 | 300 | 3 | 20 | 0 | 0 | [48 empty] | 0
SJ | 3K61 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 211 | 0 | 16 | 0 | 0 | [13 empty] | 211 | [15 empty] | 16 | [18 empty] | 11200000144 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 486 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 1266 | 1266 | 0 | 0 | 96 | 96 | 0 | 0 | 0 | 0
|  |  | Cherryland Avenue Rehabilitation | Loc Funds (LTF) | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 114 | 3 | 9 | 0 | 0 | [9 empty] | 114 | [7 empty] | 3 | [7 empty] | 9 | [22 empty] | 0 | [5 empty] | 0 | 0 | 273 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 228 | 228 | 6 | 6 | 18 | 18 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 126 | 0 | 0 | 0 | 227 | 0 | 0 | 0 | 325 | 3 | 25 | 0 | 0 | [48 empty] | 0
SJ | 3K62 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 282 | 0 | 18 | 0 | 0 | [13 empty] | 282 | [15 empty] | 18 | [18 empty] | 11200000145 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 636 | 636 | 0 | 0 | 0 | 0 | 0 | 0 | 1692 | 1692 | 0 | 0 | 108 | 108 | 0 | 0 | 0 | 0
|  |  | Thornton Road Rehabilitation | Loc Funds (LTF) | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 151 | 2 | 10 | 0 | 0 | [9 empty] | 151 | [7 empty] | 2 | [7 empty] | 10 | [22 empty] | 0 | [5 empty] | 0 | 0 | 348 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 302 | 4 | 4 | 20 | 20 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 163 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 433 | 2 | 28 | 0 | 0 | [48 empty] | 0
SJ | 3K63 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 285 | 0 | 0 | 0 | 268 | 0 | 17 | 0 | 0 | [13 empty] | 268 | [15 empty] | 17 | [18 empty] | 11200000146 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 1608 | 1608 | 0 | 0 | 102 | 102 | 0 | 0 | 0 | 0
|  |  | North 99 Frontage Rd. (East & West) Rehab | Loc Funds (LTF) | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 2 | 9 | 0 | 0 | [9 empty] | 145 | [7 empty] | 2 | [7 empty] | 9 | [22 empty] | 0 | [5 empty] | 0 | 0 | 332 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 290 | 4 | 4 | 18 | 18 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 156 | 0 | 0 | 0 | 285 | 0 | 0 | 0 | 413 | 2 | 26 | 0 | 0 | [48 empty] | 0
SJ | 3K64 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 402 | 0 | 0 | 0 | 382 | 0 | 20 | 0 | 0 | [13 empty] | 382 | [15 empty] | 20 | [18 empty] | 11200000147 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 844 | 844 | 0 | 0 | 0 | 0 | 0 | 0 | 2292 | 2292 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
|  |  | North 99 Frontage Rd. West Rehab | Loc Funds (LTF) | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316 | 2 | 25 | 0 | 0 | [9 empty] | 316 | [7 empty] | 2 | [7 empty] | 25 | [22 empty] | 0 | [5 empty] | 0 | 0 | 738 | 738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632 | 632 | 4 | 4 | 50 | 50 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 343 | 0 | 0 | 0 | 402 | 0 | 0 | 0 | 698 | 2 | 45 | 0 | 0 | [48 empty] | 0
SJ | 3K65 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 367 | 0 | 23 | 0 | 0 | [13 empty] | 367 | [15 empty] | 23 | [18 empty] | 11200000148 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 2202 | 2202 | 0 | 0 | 138 | 138 | 0 | 0 | 0 | 0
|  |  | Thornton Road Rehabilitation | Loc Funds (LTF) | 0 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 2 | 12 | 0 | 0 | [9 empty] | 198 | [7 empty] | 2 | [7 empty] | 12 | [22 empty] | 0 | [5 empty] | 0 | 0 | 450 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396 | 396 | 4 | 4 | 24 | 24 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 212 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 565 | 2 | 35 | 0 | 0 | [48 empty] | 0
SJ | 3K66 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 397 | 0 | 0 | 0 | 377 | 0 | 20 | 0 | 0 | [13 empty] | 377 | [15 empty] | 20 | [18 empty] | 11200000149 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 834 | 834 | 0 | 0 | 0 | 0 | 0 | 0 | 2262 | 2262 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
|  |  | Duncan Road Rehabilitation | Loc Funds (LTF) | 0 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 2 | 25 | 0 | 0 | [9 empty] | 313 | [7 empty] | 2 | [7 empty] | 25 | [22 empty] | 0 | [5 empty] | 0 | 0 | 732 | 732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 626 | 626 | 4 | 4 | 50 | 50 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 340 | 0 | 0 | 0 | 397 | 0 | 0 | 0 | 690 | 2 | 45 | 0 | 0 | [48 empty] | 0
SJ | 3K67 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 356 | 0 | 0 | 0 | 336 | 0 | 20 | 0 | 0 | [13 empty] | 336 | [15 empty] | 20 | [18 empty] | 11200000150 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752 | 752 | 0 | 0 | 0 | 0 | 0 | 0 | 2016 | 2016 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
|  |  | Jahant Road Rehabilitation | Loc Funds (LTF) | 0 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 3 | 11 | 0 | 0 | [9 empty] | 180 | [7 empty] | 3 | [7 empty] | 11 | [22 empty] | 0 | [5 empty] | 0 | 0 | 413 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 360 | 6 | 6 | 22 | 22 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 194 | 0 | 0 | 0 | 356 | 0 | 0 | 0 | 516 | 3 | 31 | 0 | 0 | [48 empty] | 0
SJ | 3K68 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 464 | 0 | 0 | 0 | 445 | 0 | 19 | 0 | 0 | [13 empty] | 445 | [15 empty] | 19 | [18 empty] | 11200000151 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 966 | 966 | 0 | 0 | 0 | 0 | 0 | 0 | 2670 | 2670 | 0 | 0 | 114 | 114 | 0 | 0 | 0 | 0
|  |  | Mountain House Parkway Rehabilitation | Loc Funds (LTF) | 0 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 2 | 21 | 0 | 0 | [9 empty] | 255 | [7 empty] | 2 | [7 empty] | 21 | [22 empty] | 0 | [5 empty] | 0 | 0 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510 | 510 | 4 | 4 | 42 | 42 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 278 | 0 | 0 | 0 | 464 | 0 | 0 | 0 | 700 | 2 | 40 | 0 | 0 | [48 empty] | 0
SJ | 3K69 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 232 | 0 | 0 | 0 | 219 | 0 | 13 | 0 | 0 | [13 empty] | 219 | [15 empty] | 13 | [18 empty] | 11200000152 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 490 | 490 | 0 | 0 | 0 | 0 | 0 | 0 | 1314 | 1314 | 0 | 0 | 78 | 78 | 0 | 0 | 0 | 0
|  |  | Murphy Road Rabilitation | Loc Funds (LTF) | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 2 | 7 | 0 | 0 | [9 empty] | 117 | [7 empty] | 2 | [7 empty] | 7 | [22 empty] | 0 | [5 empty] | 0 | 0 | 268 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234 | 234 | 4 | 4 | 14 | 14 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 126 | 0 | 0 | 0 | 232 | 0 | 0 | 0 | 336 | 2 | 20 | 0 | 0 | [48 empty] | 0
SJ | 3K70 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 0 | 391 | 0 | 0 | 0 | 370 | 0 | 21 | 0 | 0 | [13 empty] | 370 | [15 empty] | 21 | [18 empty] | 11200000153 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 2220 | 2220 | 0 | 0 | 126 | 126 | 0 | 0 | 0 | 0
|  |  | Grant Line Road Rehabilitation | Loc Funds (LTF) | 0 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 2 | 12 | 0 | 0 | [9 empty] | 225 | [7 empty] | 2 | [7 empty] | 12 | [22 empty] | 0 | [5 empty] | 0 | 0 | 504 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 450 | 4 | 4 | 24 | 24 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 239 | 0 | 0 | 0 | 391 | 0 | 0 | 0 | 595 | 2 | 33 | 0 | 0 | [48 empty] | 0
SJ | 3K49 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 408 | 0 | 0 | 0 | 0 | 408 | 0 | 0 | 0 | 0 | [12 empty] | 408 | [35 empty] | 11200000164 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816 | 816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Bellota Road Rehabilitatoin | Loc Funds (CO) | 336 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294 | 2 | 40 | 0 | 0 | [8 empty] | 294 | [7 empty] | 2 | [7 empty] | 40 | [23 empty] | 0 | [5 empty] | 754 | 754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294 | 294 | 2 | 2 | 40 | 40 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 336 | 0 | 0 | 0 | 408 | 0 | 0 | 0 | 0 | 702 | 2 | 40 | 0 | 0 | [48 empty] | 0
SJ | 3K50 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 0 | [12 empty] | 257 | [35 empty] | 11200000165 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 514 | 514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285 | 1285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Davis Rd. Rehabilitation | Loc Funds (CO) | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 2 | 23 | 0 | 0 | [8 empty] | 138 | [7 empty] | 2 | [7 empty] | 23 | [23 empty] | 0 | [5 empty] | 374 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 138 | 2 | 2 | 23 | 23 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 163 | 0 | 0 | 0 | 257 | 0 | 0 | 0 | 0 | 395 | 2 | 23 | 0 | 0 | [48 empty] | 0
SJ | 3K51 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 384 | 0 | 0 | 0 | 0 | 384 | 0 | 0 | 0 | 0 | [12 empty] | 384 | [35 empty] | 11200000166 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768 | 768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1920 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Bruella Rd. Rahabilitation | Loc Funds (CO) | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | 2 | 43 | 0 | 0 | [8 empty] | 319 | [7 empty] | 2 | [7 empty] | 43 | [23 empty] | 0 | [5 empty] | 816 | 816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319 | 319 | 2 | 2 | 43 | 43 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 364 | 0 | 0 | 0 | 384 | 0 | 0 | 0 | 0 | 703 | 2 | 43 | 0 | 0 | [48 empty] | 0
SJ | 3K52 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | [12 empty] | 413 | [35 empty] | 11200000167 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2065 | 2065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Peltier Rd. Rehabilitation | Loc Funds (CO) | 257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 2 | 33 | 0 | 0 | [8 empty] | 222 | [7 empty] | 2 | [7 empty] | 33 | [23 empty] | 0 | [5 empty] | 582 | 582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 222 | 2 | 2 | 33 | 33 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 257 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 635 | 2 | 33 | 0 | 0 | [48 empty] | 0
SJ | 3K53 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 283 | 0 | 0 | 0 | 0 | 283 | 0 | 0 | 0 | 0 | [12 empty] | 283 | [35 empty] | 11200000168 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 566 | 566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1415 | 1415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | South 99 Frontage Rd. East Rehab | Loc Funds (CO) | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 2 | 28 | 0 | 0 | [8 empty] | 152 | [7 empty] | 2 | [7 empty] | 28 | [23 empty] | 0 | [5 empty] | 422 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 152 | 152 | 2 | 2 | 28 | 28 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 182 | 0 | 0 | 0 | 283 | 0 | 0 | 0 | 0 | 435 | 2 | 28 | 0 | 0 | [48 empty] | 0
SJ | 3K54 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 311 | 0 | 0 | 0 | 0 | 311 | 0 | 0 | 0 | 0 | [12 empty] | 311 | [35 empty] | 11200000169 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 622 | 622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1555 | 1555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Manthey Rd. Rehabilitation | Loc Funds (CO) | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 3 | 34 | 0 | 0 | [8 empty] | 168 | [7 empty] | 3 | [7 empty] | 34 | [23 empty] | 0 | [5 empty] | 481 | 481 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 168 | 168 | 3 | 3 | 34 | 34 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 205 | 0 | 0 | 0 | 311 | 0 | 0 | 0 | 0 | 479 | 3 | 34 | 0 | 0 | [48 empty] | 0
SJ | 3K55 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | [12 empty] | 244 | [35 empty] | 11200000170 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 488 | 488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1220 | 1220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | French Camp Rd. Rehabilitation | Loc Funds (CO) | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 3 | 17 | 0 | 0 | [8 empty] | 131 | [7 empty] | 3 | [7 empty] | 17 | [23 empty] | 0 | [5 empty] | 339 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131 | 131 | 3 | 3 | 17 | 17 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 151 | 0 | 0 | 0 | 244 | 0 | 0 | 0 | 0 | 375 | 3 | 17 | 0 | 0 | [48 empty] | 0
SJ | 3K56 |  | San Joaquin Co | RIP | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | [12 empty] | 88 | [35 empty] | 11200000171 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Marine Ave. Rehabilitation | Loc Funds (CO) | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 2 | 15 | 0 | 0 | [8 empty] | 47 | [7 empty] | 2 | [7 empty] | 15 | [23 empty] | 0 | [5 empty] | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 47 | 2 | 2 | 15 | 15 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 64 | 0 | 0 | 0 | 88 | 0 | 0 | 0 | 0 | 135 | 2 | 15 | 0 | 0 | [48 empty] | 0
SJ | 7950 |  | San Joaquin Council of Governments | RIP | 0 | 0 | 167 | 181 | 0 | 0 | 0 | 0 | 0 | 348 | 0 | 0 | 0 | 0 | [10 empty] | 167 | 181 | [36 empty] | 11200000025 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 334 | 334 | 362 | 362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1225 | 1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4A2044 |  | TDM Ridesharing | CMAQ | 317 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 481 | 0 | 0 | 0 | 0 | [8 empty] | 317 | 164 | [38 empty] | 0 | [5 empty] | 634 | 634 | 328 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 645 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (XSJ) | 0 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | [9 empty] | 50 | 50 | 50 | 50 | 50 | [34 empty] | 0 | [5 empty] | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 317 | 214 | 217 | 231 | 50 | 50 | 0 | 0 | 0 | 1079 | 0 | 0 | 0 | 0 | [48 empty] | 0
SJ | 7952 |  | San Joaquin Council of Governments | RIP | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | [10 empty] | 220 | [37 empty] | 11200000026 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 440 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4A2054 |  | Plan, program and monitor | TOTAL | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SJ | 3K45 |  | Stockton, City of | RIP | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | [13 empty] | 2000 | [34 empty] | 11200000160 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Hammer Lane Widening (phase III) | Loc Funds (CITY) | 0 | 541 | 1572 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 172 | 441 | 0 | 0 |  |  | 1500 | [14 empty] | 100 | 72 | [6 empty] | 441 | [22 empty] | 0 | [5 empty] | 0 | 0 | 2064 | 2064 | 1716 | 1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 0 | 0 | 416 | 416 | 882 | 882 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CO) | 0 | 0 | 713 | 4137 | 0 | 0 | 0 | 0 | 0 | 4137 | 0 | 713 | 0 | 0 | [11 empty] | 4137 | [14 empty] | 713 | [21 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 2852 | 2852 | 8274 | 8274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16548 | 16548 | 0 | 0 | 2139 | 2139 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 541 | 2285 | 4137 | 0 | 2000 | 0 | 0 | 1500 | 6137 | 172 | 1154 | 0 | 0 | [48 empty] | 0
SJ | 3K46A |  | Stockton, City of | Othr. State | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | [10 empty] | 250 | [37 empty] | 11200000161 | [5 empty] | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Stagecoach Road Rehab | RIP | 0 | 0 | 0 | 0 | 0 | 623 | 0 | 0 | 0 | 623 | 0 | 0 | 0 | 0 | [13 empty] | 623 | [34 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1246 | 1246 | 0 | 0 | 0 | 0 | 0 | 0 | 3738 | 3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CITY) | 0 | 576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 426 | 0 | 0 | [17 empty] | 150 | [7 empty] | 426 | [22 empty] | 0 | [5 empty] | 0 | 0 | 2154 | 2154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 852 | 852 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 576 | 250 | 0 | 0 | 623 | 0 | 0 | 0 | 873 | 150 | 426 | 0 | 0 | [48 empty] | 0
SJ | 3K46B |  | Stockton, City of | RIP | 0 | 0 | 0 | 0 | 0 | 1752 | 0 | 0 | 0 | 1752 | 0 | 0 | 0 | 0 | [13 empty] | 1752 | [34 empty] | 11200000173 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3504 | 3504 | 0 | 0 | 0 | 0 | 0 | 0 | 10512 | 10512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | North Stockton Rehab | TOTAL | 0 | 0 | 0 | 0 | 0 | 1752 | 0 | 0 | 0 | 1752 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SJ | 3K46C |  | Stockton, City of | RIP | 0 | 0 | 0 | 0 | 0 | 1798 | 0 | 0 | 0 | 1798 | 0 | 0 | 0 | 0 | [13 empty] | 1798 | [34 empty] | 11200000174 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3596 | 3596 | 0 | 0 | 0 | 0 | 0 | 0 | 10788 | 10788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Stanislaus/Union Street Rehab | TOTAL | 0 | 0 | 0 | 0 | 0 | 1798 | 0 | 0 | 0 | 1798 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SJ | 2K47 |  | Tracy, City of | Othr. State | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | [16 empty] | 72 | [31 empty] | 11200000104 | [5 empty] | 216 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Tracy Downtown Multimodal Station | RIP | 0 | 2945 | 3705 | 0 | 0 | 0 | 0 | 0 | 2945 | 3705 | 0 | 0 | 0 | 0 |  | 2945 | [8 empty] | 3705 | [37 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 2945 | 2945 | 7410 | 7410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5890 | 5890 | 11115 | 11115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CITY) | 0 | 50 | 200 | 0 | 0 | 0 | 0 | 0 | 50 | 200 | 0 | 0 | 0 | 0 |  | 50 | [8 empty] | 200 | [37 empty] | 0 | [5 empty] | 0 | 0 | 50 | 50 | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 600 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (XSJ) | 1216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 800 | 0 | 0 | [16 empty] | 416 | [7 empty] | 800 | [23 empty] | 0 | [5 empty] | 4448 | 4448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 416 | 800 | 800 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 1288 | 2995 | 3905 | 0 | 0 | 0 | 0 | 0 | 2995 | 3905 | 488 | 800 | 0 | 0 | [48 empty] | 0
SJ | 7350 | 12 | Caltrans | RIP | 1614 | 711 | 0 | 16040 | 0 | 0 | 0 | 0 | 711 | 14856 | 673 | 801 | 140 | 1184 |  | 711 | [9 empty] | 14856 |  |  |  |  | 673 | [7 empty] | 801 | [7 empty] | 140 | [10 empty] | 1184 |  |  |  |  | 11200000036 | RIP |  |  |  | X | 5923 | 5923 | 711 | 711 | 0 | 0 | 36816 | 36816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1422 | 1422 | 59424 | 59424 | 673 | 673 | 801 | 801 | 140 | 140 | 4736 | 4736
| 0A840K | 0.1/10.1 | Route 12 (Bouldin Island) Passing Lanes | TOTAL | 1614 | 711 | 0 | 16040 | 0 | 0 | 0 | 0 | 711 | 14856 | 673 | 801 | 140 | 1184 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SJ | 7398 | 12 | Lodi, City of | RIP | 0 | 0 | 0 | 0 | 336 | 2293 | 0 | 0 | 336 | 2293 | 0 | 0 | 0 | 0 |  |  |  |  | 336 | [8 empty] | 2293 | [34 empty] | 11200000159 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 336 | 336 | 4586 | 4586 | 0 | 0 | 0 | 0 | 1680 | 1680 | 13758 | 13758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0G570K | 15.2/17.5 | SR-12 Kettleman Lane Gap Closure | Loc Funds (XSJ) | 473 | 241 | 109 | 0 | 0 | 0 | 0 | 0 | 186 | 109 | 140 | 333 | 55 | 0 |  | 186 | [8 empty] | 109 | [5 empty] | 140 | [7 empty] | 333 | [8 empty] | 55 | [14 empty] | 0 | [5 empty] | 1752 | 1752 | 461 | 461 | 218 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372 | 372 | 327 | 327 | 140 | 140 | 333 | 333 | 110 | 110 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 473 | 241 | 109 | 0 | 336 | 2293 | 0 | 0 | 522 | 2402 | 140 | 333 | 55 | 0 | [48 empty] | 0
STA | 7855 | 132 | Caltrans | RIP | 0 | 0 | 517 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 267 | 0 |  |  | 250 | [31 empty] | 267 | [13 empty] | 11400000054 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 1585 | 1585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 801 | 801 | 0 | 0
| 0A5100 | R5.8/R2.4 | SR-132 West Widening | RIP (STA) | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | [16 empty] | 500 | [31 empty] | 0 | [5 empty] | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | IIP | 0 | 0 | 517 | 0 | 0 | 0 | 0 | 0 | 517 | 0 | 0 | 0 | 0 | 0 |  |  | 517 | [45 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 517 | 517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1551 | 1551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TCRP | 500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1500 | 0 | 0 | [16 empty] | 500 | [9 empty] | 1500 | [21 empty] | 0 | [5 empty] | 1500 | 1500 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 4500 | 4500 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 15070 | 0 | 0 | 0 | 0 | 14300 | 0 | 0 | 0 | 770 | [12 empty] | 14300 | [31 empty] | 770 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33220 | 33220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71500 | 71500 | 0 | 0 | 0 | 0 | 0 | 0 | 3850 | 3850
|  |  |  | TOTAL | 1000 | 0 | 2534 | 0 | 15070 | 0 | 0 | 0 | 767 | 14300 | 1000 | 1500 | 267 | 770 | [48 empty] | 0
SJ | 7965B | 205 | Caltrans | RIP | 821 | 1580 | 27670 | 0 | 0 | 0 | 0 | 0 | 550 | 24618 | 821 | 1473 | 107 | 2502 |  |  | 550 | [7 empty] | 24618 | [5 empty] | 821 | [8 empty] | 1473 | [7 empty] | 107 | [8 empty] | 2502 | [5 empty] | 11200000040 | RIP |  |  |  | X | 2463 | 2463 | 6427 | 6427 | 64798 | 64798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 1650 | 73854 | 73854 | 821 | 821 | 2946 | 2946 | 214 | 214 | 7506 | 7506
| 300160 | R3.0/R13.6 | Tracy Widening, stage 2 & 3 | IIP | 822 | 1581 | 39132 | 0 | 0 | 0 | 0 | 0 | 550 | 36080 | 822 | 1474 | 107 | 2502 |  |  | 550 | [7 empty] | 36080 | [5 empty] | 822 | [8 empty] | 1474 | [7 empty] | 107 | [8 empty] | 2502 | [5 empty] | 0 | [5 empty] | 2466 | 2466 | 6431 | 6431 | 87722 | 87722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1650 | 1650 | 108240 | 108240 | 822 | 822 | 2948 | 2948 | 214 | 214 | 7506 | 7506
|  | Change Reason ==> |  | TCRP | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | [10 empty] | 25000 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 1643 | 3161 | 91802 | 0 | 0 | 0 | 0 | 0 | 1100 | 85698 | 1643 | 2947 | 214 | 5004 | [48 empty] | 0
SJ | 7213 | 5 | Caltrans | RIP | 235 | 0 | 4420 | 0 | 0 | 0 | 0 | 0 | 0 | 3244 | 235 | 525 | 1 | 650 | [10 empty] | 3244 | [5 empty] | 235 | [9 empty] | 525 | [7 empty] | 1 | [7 empty] | 650 | [5 empty] | 21200000123 | RIP |  |  |  | X | 705 | 705 | 0 | 0 | 12493 | 12493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9732 | 9732 | 235 | 235 | 1575 | 1575 | 3 | 3 | 1950 | 1950
| 3A1200 | R13.9/R15.6 | I-5 Widening in Mossdale WYE Area | TCRP | 235 | 0 | 6765 | 0 | 0 | 0 | 0 | 0 | 0 | 5589 | 235 | 525 | 1 | 650 | [10 empty] | 5589 | [5 empty] | 235 | [9 empty] | 525 | [7 empty] | 1 | [7 empty] | 650 | [5 empty] | 0 | [5 empty] | 705 | 705 | 0 | 0 | 17183 | 17183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16767 | 16767 | 235 | 235 | 1575 | 1575 | 3 | 3 | 1950 | 1950
|  | Change Reason ==> |  | TOTAL | 470 | 0 | 11185 | 0 | 0 | 0 | 0 | 0 | 0 | 8833 | 470 | 1050 | 2 | 1300 | [48 empty] | 0
SJ | 7673 | 99 | Caltrans | RIP | 0 | 0 | 5233 | 0 | 0 | 0 | 0 | 0 | 0 | 5233 | 0 | 0 | 0 | 0 | [10 empty] | 5233 | [37 empty] | 11200000039 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 10466 | 10466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15699 | 15699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 445400 | 18.6/22.9 | Route 99 Widening in North Stockton | IIP | 0 | 0 | 19476 | 0 | 0 | 0 | 0 | 0 | 0 | 16724 | 0 | 0 | 0 | 2752 | [10 empty] | 16724 | [31 empty] | 2752 | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 49960 | 49960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50172 | 50172 | 0 | 0 | 0 | 0 | 0 | 0 | 8256 | 8256
|  | Change Reason ==> |  | Loc Funds (XSJ) | 3586 | 10916 | 0 | 0 | 0 | 0 | 0 | 0 | 752 | 10124 | 967 | 2619 | 40 | 0 |  | 752 | [7 empty] | 10124 | [6 empty] | 967 | [7 empty] | 2619 | [8 empty] | 40 | [14 empty] | 0 | [5 empty] | 13377 | 13377 | 21200 | 21200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1504 | 1504 | 20248 | 20248 | 967 | 967 | 2619 | 2619 | 80 | 80 | 0 | 0
|  |  |  | TOTAL | 3586 | 10916 | 24709 | 0 | 0 | 0 | 0 | 0 | 752 | 32081 | 967 | 2619 | 40 | 2752 | [48 empty] | 0
SJ | 9841 | 99 | Caltrans | RIP | 0 | 0 | 5388 | 0 | 0 | 0 | 0 | 0 | 0 | 2921 | 0 | 0 | 0 | 2467 | [10 empty] | 2921 | [31 empty] | 2467 | [5 empty] | 11200000054 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 20644 | 20644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8763 | 8763 | 0 | 0 | 0 | 0 | 0 | 0 | 7401 | 7401
| 445600 | 22.8/23.0 | Route 99/Hammer Lane Interchange | RSTP | 0 | 404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404 | 0 | 0 | 0 | 0 | [9 empty] | 404 | [38 empty] | 0 | [5 empty] | 0 | 0 | 808 | 808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808 | 808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CITY) | 1681 | 3312 | 0 | 0 | 0 | 0 | 0 | 0 | 1681 | 3312 | 0 | 0 | 0 | 0 | 1681 | [8 empty] | 3312 | [38 empty] | 0 | [5 empty] | 1681 | 1681 | 6624 | 6624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1681 | 1681 | 6624 | 6624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (XSJ) | 1869 | 8133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8133 | 391 | 1428 | 50 | 0 | [9 empty] | 8133 | [6 empty] | 391 | [7 empty] | 1428 | [7 empty] | 50 | [15 empty] | 0 | [5 empty] | 7135 | 7135 | 16266 | 16266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16266 | 16266 | 391 | 391 | 1428 | 1428 | 50 | 50 | 0 | 0
|  |  |  | TOTAL | 3550 | 11849 | 5388 | 0 | 0 | 0 | 0 | 0 | 1681 | 14770 | 391 | 1428 | 50 | 2467 | [48 empty] | 0
SJ | 7668 | 99 | Caltrans | RIP | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | [16 empty] | 800 | [31 empty] | 11200000094 | RIP |  |  |  | X | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0
| 3A100K | 15.0/18.6 | Route 99 Widening in South Stockton | IIP | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | [16 empty] | 800 | [31 empty] | 0 | [5 empty] | 2400 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 0 | 30800 | 0 | 0 | 0 | 25000 | 0 | 0 | 3300 | 2500 | 0 |  |  |  |  | 25000 | [23 empty] | 3300 | [7 empty] | 2500 | [11 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50700 | 50700 | 0 | 0 | 0 | 0 | 0 | 0 | 125000 | 125000 | 0 | 0 | 0 | 0 | 16500 | 16500 | 12500 | 12500 | 0 | 0
|  |  |  | TOTAL | 1600 | 0 | 0 | 0 | 30800 | 0 | 0 | 0 | 25000 | 0 | 1600 | 3300 | 2500 | 0 | [48 empty] | 0
SJ | 7635 | 99 | Caltrans | RIP | 0 | 0 | 2408 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 408 | [10 empty] | 2000 | [31 empty] | 408 | [5 empty] | 11200000102 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 6448 | 6448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 1224 | 1224
| 3A090K | 6.4/7.0 | Rte 99/120 E (Yosemite Ave) Interchange | Demo | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5095 | 0 | 0 | 0 | 905 | [9 empty] | 5095 | [31 empty] | 905 | [6 empty] | 0 | [5 empty] | 0 | 0 | 15620 | 15620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10190 | 10190 | 0 | 0 | 0 | 0 | 0 | 0 | 1810 | 1810
|  | Change Reason ==> |  | Loc Funds (CITY) | 690 | 2005 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 2005 | 0 | 0 | 0 | 0 | 690 | [8 empty] | 2005 | [38 empty] | 0 | [5 empty] | 690 | 690 | 4010 | 4010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 690 | 4010 | 4010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (XSJ) | 3045 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 1400 | 635 | 1341 | 319 | 0 | 750 | [8 empty] | 1400 | [6 empty] | 635 | [7 empty] | 1341 | [7 empty] | 319 | [15 empty] | 0 | [5 empty] | 9614 | 9614 | 2800 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 2800 | 2800 | 635 | 635 | 1341 | 1341 | 319 | 319 | 0 | 0
|  |  |  | TOTAL | 3735 | 9405 | 2408 | 0 | 0 | 0 | 0 | 0 | 1440 | 10500 | 635 | 1341 | 319 | 1313 | [48 empty] | 0
|  |  |  | Total RIP | 5326 | 6436 | 50528 | 16221 | 5931 | 20011 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 3470 | 02/03: 1580
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 0 | 02/03: 711
|  |  |  | Total RIP Eligible for Reprogramming | 1856 | 4145 | 50528 | 16221 | 5931 | 20011 | 0 | 0
[8 empty] | 72750 | 5931 | 20011