## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Solano County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
SOL | 6045A |  | Benicia, City of | RIP | 0 | 0 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 0 | [13 empty] | 154 | [34 empty] | 20600002208 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 924 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | West 'K' Street Overlay and Rehabiliation. | TOTAL | 0 | 0 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 6045M |  | Benicia, City of | RIP | 0 | 0 | 225 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 1100 | 0 | 0 | [18 empty] | 225 | [8 empty] | 1100 | [20 empty] | 20600002215 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 675 | 675 | 4400 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 675 | 4400 | 4400 | 0 | 0 | 0 | 0
|  | 0.0 | Benicia Intermodal Transportation Station | Future Need | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | [11 empty] | 15000 | [36 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (GEN) | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 1400 | [47 empty] | 0 | [5 empty] | 1400 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 1400 | 0 | 225 | 16100 | 0 | 0 | 0 | 0 | 1400 | 15000 | 225 | 1100 | 0 | 0 | [48 empty] | 0
SOL | 6045L |  | Capitol Corridor Joint Powers Authority | RIP | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | [10 empty] | 1000 | [37 empty] | 10600000909 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| R952SA |  | Bahia Viaduct Track Upgrade | IIP | 0 | 190 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 40 | 150 | 0 | 0 | [10 empty] | 1060 | [6 empty] | 40 | [7 empty] | 150 | [22 empty] | 0 | [5 empty] | 0 | 0 | 720 | 720 | 2120 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3180 | 3180 | 80 | 80 | 300 | 300 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 190 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 40 | 150 | 0 | 0 | [48 empty] | 0
SOL | 6045B |  | Dixon, City of | RIP | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 0 | 0 | 105 | 0 | 0 | 0 | 0 | [13 empty] | 105 | [34 empty] | 20600002209 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 630 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | South Lincoln Street Overlay & Rehabiliation | Loc Funds (GEN) | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | [24 empty] | 5 | [23 empty] | 0 | [5 empty] | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 5 | 0 | 0 | 0 | 0 | 105 | 0 | 0 | 0 | 105 | 0 | 5 | 0 | 0 | [48 empty] | 0
SOL | 6045J |  | Dixon, City of | RIP | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | [10 empty] | 400 | [37 empty] | 20600002213 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Dixon Multimodal Transportation Center | Loc Funds (GEN) | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | [24 empty] | 40 | [23 empty] | 0 | [5 empty] | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 40 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 40 | 0 | 0 | [48 empty] | 0
SOL | 6045K |  | Fairfield, City of | FTA Funds | 0 | 492 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492 | 0 | 0 | 0 | 0 | [9 empty] | 492 | [38 empty] | 20600002178 | [5 empty] | 0 | 0 | 984 | 984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 984 | 984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Fairfield/Vacaville Rail Station | Othr. State | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774 | 0 | 126 | 0 | 0 | 0 | 774 | [15 empty] | 126 | [31 empty] | 0 | [5 empty] | 1152 | 1152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 774 | 774 | 0 | 0 | 126 | 126 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | RIP | 0 | 0 | 125 | 2125 | 0 | 0 | 0 | 0 | 0 | 2125 | 0 | 125 | 0 | 0 | [11 empty] | 2125 | [14 empty] | 125 | [21 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 500 | 500 | 4250 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 8500 | 0 | 0 | 375 | 375 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (CITY) | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 0 | 167 | 0 | 0 | [8 empty] | 308 | [15 empty] | 167 | [23 empty] | 0 | [5 empty] | 1284 | 1284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 308 | 308 | 0 | 0 | 167 | 167 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (GEN) | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617 | 0 | 333 | 0 | 0 | [8 empty] | 617 | [15 empty] | 333 | [23 empty] | 0 | [5 empty] | 2566 | 2566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 617 | 617 | 0 | 0 | 333 | 333 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 2325 | 492 | 125 | 2125 | 0 | 0 | 0 | 0 | 774 | 3542 | 126 | 625 | 0 | 0 | [48 empty] | 0
SOL | 6045C |  | Fairfield, City of | RIP | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | [13 empty] | 364 | [34 empty] | 20600002210 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 728 | 728 | 0 | 0 | 0 | 0 | 0 | 0 | 2184 | 2184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Hilborn Road Pavement Rehabilitation | Loc Funds (GEN) | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | [9 empty] | 107 | [38 empty] | 0 | [5 empty] | 0 | 0 | 214 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 107 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 471 | 0 | 0 | 0 | 0 | [48 empty] | 0
SOL | 2152 |  | Metropolitan Transportation Commission | RIP | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | [10 empty] | 26 | [37 empty] | 10600000343 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 52 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073324 |  | Planning, Programming and Monitoring | TOTAL | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 2154 |  | Metropolitan Transportation Commission | RIP | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | [10 empty] | 163 | [37 empty] | 10600000345 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 326 | 326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 489 | 489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073344 |  | Regional Rideshare Program | TOTAL | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 2170 |  | Metropolitan Transportation Commission | RIP | 0 | 0 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 0 | 0 | 0 | 0 | [10 empty] | 178 | [37 empty] | 10600000346 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 356 | 356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 072774 |  | CMAQ Match Reserve | TOTAL | 0 | 0 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 178 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 6045H |  | Rio Vista, City of | RIP | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | [13 empty] | 74 | [34 empty] | 20600002186 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 148 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 444 | 444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Front Street Rehabilitation | Loc Funds (GEN) | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 7 | 0 | 0 | [9 empty] | 10 | [15 empty] | 7 | [22 empty] | 0 | [5 empty] | 0 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 17 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 84 | 0 | 7 | 0 | 0 | [48 empty] | 0
SOL | 2263 |  | Solano Co. Trans. Auth. | RIP | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | [10 empty] | 75 | [37 empty] | 10600000752 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 073364 |  | Planning, Programming, and Monitoring | TOTAL | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 6045D |  | Solano County | RIP | 0 | 0 | 0 | 0 | 0 | 393 | 0 | 0 | 0 | 393 | 0 | 0 | 0 | 0 | [13 empty] | 393 | [34 empty] | 20600002211 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786 | 786 | 0 | 0 | 0 | 0 | 0 | 0 | 2358 | 2358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Various Roads Overlay Rehabilitation | Loc Funds (LTF) | 17 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 20 | 5 | 10 | 0 | 0 | 2 | [8 empty] | 20 | [6 empty] | 5 | [7 empty] | 10 | [23 empty] | 0 | [5 empty] | 57 | 57 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 40 | 40 | 5 | 5 | 10 | 10 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 17 | 20 | 0 | 0 | 0 | 393 | 0 | 0 | 2 | 413 | 5 | 10 | 0 | 0 | [48 empty] | 0
SOL | 5301 |  | Solano Transportation Authority | RIP | 0 | 100 | 4650 | 2650 | 8800 | 6900 | 0 | 0 | 2500 | 20350 | 0 | 250 | 0 | 0 |  | 100 |  | 2400 | [6 empty] | 4650 |  | 8800 | 6900 | [13 empty] | 250 | [20 empty] | 10600000348 | RIP |  |  |  |  | 0 | 0 | 100 | 100 | 9300 | 9300 | 3400 | 3400 | 17600 | 17600 | 13800 | 13800 | 0 | 0 | 0 | 0 | 9800 | 9800 | 99350 | 99350 | 0 | 0 | 1000 | 1000 | 0 | 0 | 0 | 0
| 0T2101 |  | I-80 Reliever Route/Jepson Pkwy | Future Need | 0 | 0 | 0 | 6830 | 8410 | 56660 | 0 | 0 | 8410 | 56660 | 0 | 6830 | 0 | 0 |  |  |  |  | 8410 | [8 empty] | 56660 | [13 empty] | 6830 | [20 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 27320 | 27320 | 8410 | 8410 | 113320 | 113320 | 0 | 0 | 0 | 0 | 42050 | 42050 | 339960 | 339960 | 0 | 0 | 27320 | 27320 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Demo | 0 | 6610 | 7760 | 0 | 0 | 0 | 0 | 0 | 5040 | 7760 | 250 | 1320 | 0 | 0 |  | 5040 | [8 empty] | 7760 | [6 empty] | 250 | [7 empty] | 1320 | [22 empty] | 0 | [5 empty] | 0 | 0 | 11070 | 11070 | 15520 | 15520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10080 | 10080 | 23280 | 23280 | 500 | 500 | 2640 | 2640 | 0 | 0 | 0 | 0
|  |  |  | Loc Funds (GEN) | 1950 | 18650 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | 18650 | 0 | 200 | 0 | 0 | 1750 | [8 empty] | 18650 | [14 empty] | 200 | [23 empty] | 0 | [5 empty] | 2550 | 2550 | 37300 | 37300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | 1750 | 37300 | 37300 | 0 | 0 | 200 | 200 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 1950 | 25360 | 12410 | 9480 | 17210 | 63560 | 0 | 0 | 17700 | 103420 | 250 | 8600 | 0 | 0 | [48 empty] | 0
SOL | 6045E |  | Suisun City, City of | RIP | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | [13 empty] | 140 | [34 empty] | 20600002212 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 840 | 840 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Various Streets Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 140 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 6045F |  | Vacaville, City of | RIP | 0 | 0 | 0 | 0 | 0 | 342 | 0 | 0 | 0 | 342 | 0 | 0 | 0 | 0 | [13 empty] | 342 | [34 empty] | 20600002184 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 684 | 684 | 0 | 0 | 0 | 0 | 0 | 0 | 2052 | 2052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Nut Tree Road Resurfacing & Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 0 | 342 | 0 | 0 | 0 | 342 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 2260 |  | Vallejo, City of | RIP | 0 | 0 | 0 | 1200 | 3000 | 3100 | 0 | 0 | 0 | 6100 | 0 | 1200 | 0 | 0 | [12 empty] | 3000 | 3100 | [13 empty] | 1200 | [20 empty] | 10600000733 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4800 | 4800 | 6000 | 6000 | 6200 | 6200 | 0 | 0 | 0 | 0 | 0 | 0 | 33600 | 33600 | 0 | 0 | 4800 | 4800 | 0 | 0 | 0 | 0
| T972SA |  | Vallejo Ferry Terminal Intermodal Fac. | Future Need | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | [11 empty] | 25000 | [36 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Federal Disc. | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 |  |  | 1500 | [45 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 1500 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 0 | 1500 | 26200 | 3000 | 3100 | 0 | 0 | 1500 | 31100 | 0 | 1200 | 0 | 0 | [48 empty] | 0
SOL | 2261 |  | Vallejo, City of | Othr. State | 0 | 0 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 203 | 0 | 0 | 0 | 0 | [10 empty] | 203 | [37 empty] | 10600000734 | [5 empty] | 0 | 0 | 0 | 0 | 406 | 406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609 | 609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| T971SA |  | Baylink Ferry Maintenance Facility | RIP | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | [26 empty] | 425 | [21 empty] | 0 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1700 | 1700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1275 | 1275 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 842 | 3250 | 0 | 0 | 0 | 0 | 0 | 0 | 4092 | 0 | 0 | 0 | 0 | [9 empty] | 842 | 3250 | [37 empty] | 0 | [5 empty] | 0 | 0 | 1684 | 1684 | 6500 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11434 | 11434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | RSTP | 0 | 0 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 248 | 0 | 0 | 0 | 0 | [10 empty] | 248 | [37 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 496 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 744 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 0 | 842 | 4126 | 0 | 0 | 0 | 0 | 0 | 0 | 4543 | 0 | 425 | 0 | 0 | [48 empty] | 0
SOL | 6045G |  | Vallejo, City of | RIP | 0 | 0 | 0 | 0 | 0 | 428 | 0 | 0 | 0 | 428 | 0 | 0 | 0 | 0 | [13 empty] | 428 | [34 empty] | 20600002185 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856 | 856 | 0 | 0 | 0 | 0 | 0 | 0 | 2568 | 2568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0.0 | Lemon Street Rehabilitation | TOTAL | 0 | 0 | 0 | 0 | 0 | 428 | 0 | 0 | 0 | 428 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 5201D | 37 | Caltrans | GF RIP | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 428 | 0 | 86 | 0 | 86 | [12 empty] | 428 | [15 empty] | 86 | [15 empty] | 86 |  |  |  | 10600000919 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 1716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2140 | 2140 | 0 | 0 | 430 | 430 | 0 | 0 | 430 | 430
| 0T14F1 | 8.0/10 | Route 37 Mitigation Planting | TOTAL | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 428 | 0 | 86 | 0 | 86 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
SOL | 5301K | 80 | Solano Co. Trans. Auth. | RIP | 0 | 0 | 0 | 0 | 7200 | 4535 | 0 | 0 | 4535 | 0 | 0 | 7200 | 0 | 0 | [5 empty] | 4535 | [22 empty] | 7200 | [19 empty] | 20600002227 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 28800 | 4535 | 4535 | 0 | 0 | 0 | 0 | 27210 | 27210 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0
| 0A5200 | 17.9/1 | I-80/I-680/SR12 Interchange/Connector Ph 2 | TCRP | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | [16 empty] | 3000 | [31 empty] | 0 | [5 empty] | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Future Need | 0 | 0 | 0 | 0 | 0 | 2965 | 47300 | 0 | 2965 | 47300 | 0 | 0 | 0 | 0 | [5 empty] | 2965 | [8 empty] | 47300 | [33 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2965 | 2965 | 94600 | 94600 | 0 | 0 | 17790 | 17790 | 331100 | 331100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 3000 | 0 | 0 | 0 | 7200 | 7500 | 47300 | 0 | 7500 | 47300 | 3000 | 7200 | 0 | 0 | [48 empty] | 0
SOL | 5301L | 80 | Solano Transportation Authority | RIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | 10600000914 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0A5300 |  | I-80/I-680/SR12 Interchange | RIP | 0 | 0 | 0 | 0 | 7200 | 4535 | 0 | 0 | 4535 | 0 | 0 | 7200 | 0 | 0 | [5 empty] | 4535 | [22 empty] | 7200 | [19 empty] | 0 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28800 | 28800 | 4535 | 4535 | 0 | 0 | 0 | 0 | 27210 | 27210 | 0 | 0 | 0 | 0 | 36000 | 36000 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TCRP | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | [16 empty] | 12000 | [31 empty] | 0 | [5 empty] | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Future Need | 0 | 0 | 0 | 0 | 0 | 2965 | 47300 | 0 | 2965 | 47300 | 0 | 0 | 0 | 0 | [5 empty] | 2965 | [8 empty] | 47300 | [33 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2965 | 2965 | 94600 | 94600 | 0 | 0 | 17790 | 17790 | 331100 | 331100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 12000 | 0 | 0 | 0 | 7200 | 7500 | 47300 | 0 | 7500 | 47300 | 12000 | 7200 | 0 | 0 | [48 empty] | 0
|  |  |  | Total RIP | 0 | 100 | 7267 | 7075 | 26800 | 21070 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 0 | 0
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 0 | 0
|  |  |  | Total RIP Eligible for Reprogramming | 0 | 100 | 7267 | 7075 | 26800 | 21070 | 0 | 0
[8 empty] | 14442 | 26800 | 21070