## Instructions
2004 STIP RIP Funded Project Inventory Worksheet Instructions
Overview:
This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.
The following project changes made on this spreadsheet do not require a STIP Fact and Funding Sheet.
l Project Schedule Delays.
l Project Schedule Advance.
l Minor Project Funding Changes. This includes shifts between components but not the addition of additional local non-STIP funds.
The following changes will still require a STIP Fact and Funding sheet:
l New Projects.
l Change of Implementing Agency for any component.
l Any change affecting project scope.
Instructions
1. Select a Change Reason, yellow highlight, for every project in the list, even if the reason is simply "No Change".
2. Update financial data by project component.
3. To delete a project, select the "Delete" change reason and zero out the dollars.
4. Do not use this form to add new projects. Instead, select the "See Attached Fact and Funding Sheet" change reason and attach the filled in sheet.
Please Note: The spreadsheet is quite wide but has been preset to print only the summary funding data. You may change the print area at any time to print the entire spreadsheet but will need to change to ledger size (11" x 17") to view it properly.
DO NOT TYPE in the GRAY COLORED AREA of the SPREADSHEET.
Questions?
l Chad Baker (916) 651-6879 - Caltrans Districts 1, 2, 3
l Leah Cagle (916) 651-6881 - Caltrans Districts 8, 11, 12
l Ken Solak (916) 654-4447 - Caltrans District 4
l Rambabu Bavirisetty (916) 654-2683 - Caltrans District 7
l Linda Newton (916) 651-6877 - Caltrans Districts 5, 6, 9, 10
To start, click on the "Project Inventory" tab below.
| This project inventory was initially generated from the Department's CTIPS database and contains all unallocated project components left over in the 2002 STIP. This worksheet is the recommended method for summarizing project data in the RTIP | and also may be used to transmit certain 2004 STIP project changes in lieu of the normal multi-page STIP Fact and Funding Sheet.

## Project Inventory
Trinity County | [18 empty] | Project Funding by Component - Update Funding Here
| PPNO | RTE | Agency |  | Project Totals by Fiscal Year | [7 empty] | Project Totals by Component | [5 empty] | Right of Way | [7 empty] | Construction | [7 empty] | Environmental & Permits | [7 empty] | Plans, Specifications, and Estimate | [7 empty] | Caltrans Right-of-Way Support | [7 empty] | Caltrans Construction Engineering | [13 empty] | Project Totals by Fiscal Year | Project Totals by Fiscal Year | [6 empty] | Project Totals by Component | Project Totals by Component
CO | EA | PM | Project | Fund | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | RW | Const | E & P | PS&E | RW Sup | Con Eng | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | Prior | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 | 07/08 | 08/09 | CTIPS ID | RIP ID | 3090 Reimb | 3090 Repl. | GARVEE | CT Impl | Prior | Prior | 03/04 | 03/04 | 05/06 | 05/06 | 07/08 | 07/08 | RW | RW | E & P | E & P | RW Sup | RW Sup
TRI | 2138 |  | Trinity County | RIP | 360 | 0 | 0 | 0 | 5731 | 0 | 0 | 0 | 1460 | 4271 | 0 | 360 | 0 | 0 |  |  |  |  | 1460 | [7 empty] | 4271 | [11 empty] | 360 | [23 empty] | 13000000722 | RIP |  |  |  |  | 1440 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 10002 | 10002 | 0 | 0 | 0 | 0 | 0 | 0 | 7300 | 7300 | 21355 | 21355 | 0 | 0 | 360 | 360 | 0 | 0 | 0 | 0
| 454184 |  | East Connector Road | TOTAL | 360 | 0 | 0 | 0 | 5731 | 0 | 0 | 0 | 1460 | 4271 | 0 | 360 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
TRI | 2140 |  | Trinity County | RIP | 0 | 437 | 0 | 4511 | 0 | 0 | 0 | 0 | 0 | 4511 | 0 | 437 | 0 | 0 | [11 empty] | 4511 | [13 empty] | 437 | [22 empty] | 13000000724 | RIP |  |  |  |  | 0 | 0 | 1748 | 1748 | 0 | 0 | 9022 | 9022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18044 | 18044 | 0 | 0 | 874 | 874 | 0 | 0 | 0 | 0
| 454204 |  | Widen Hyampom Road | TOTAL | 0 | 437 | 0 | 4511 | 0 | 0 | 0 | 0 | 0 | 4511 | 0 | 437 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
TRI | 2216 |  | Trinity County | RIP | 0 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 0 | 0 | 0 | 0 | [9 empty] | 729 | [38 empty] | 13000000849 | RIP |  |  |  |  | 0 | 0 | 1458 | 1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1458 | 1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 454874 |  | Hyampom Road Rehab | Loc Funds (LTF) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | [16 empty] | 1 | [31 empty] | 0 | [5 empty] | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 1 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 729 | 1 | 0 | 0 | 0 | [48 empty] | 0
TRI | 2220 |  | Trinity County | RIP | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | [11 empty] | 515 | [36 empty] | 13000000852 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 454894 |  | Mad River Road Rehab | Loc Funds (CO) | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | [16 empty] | 5 | [31 empty] | 0 | [5 empty] | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 5 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 515 | 5 | 0 | 0 | 0 | [48 empty] | 0
TRI | 2219 |  | Trinity County | RIP | 0 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 615 | 0 | 0 | 0 | 0 | [10 empty] | 615 | [37 empty] | 13000000853 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 1230 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1845 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 454894 |  | East Side Road Rehab | Loc Funds (LTF) | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | [16 empty] | 5 | [31 empty] | 0 | [5 empty] | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 5 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 615 | 5 | 0 | 0 | 0 | [48 empty] | 0
TRI | 2223 |  | Trinity County | RIP | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 0 | 0 | 0 | [11 empty] | 175 | [36 empty] | 13000000854 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 455274 |  | Browns Creek Bridge Replacement | Local HBRR | 124 | 36 | 0 | 700 | 0 | 0 | 0 | 0 | 36 | 700 | 40 | 84 | 0 | 0 |  | 36 | [9 empty] | 700 |  |  |  |  | 40 | [7 empty] | 84 | [23 empty] | 0 | [5 empty] | 456 | 456 | 36 | 36 | 0 | 0 | 1400 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 2800 | 2800 | 40 | 40 | 84 | 84 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CO) | 31 | 9 | 0 | 7 | 0 | 0 | 0 | 0 | 9 | 7 | 10 | 21 | 0 | 0 |  | 9 | [9 empty] | 7 |  |  |  |  | 10 | [7 empty] | 21 | [23 empty] | 0 | [5 empty] | 114 | 114 | 9 | 9 | 0 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 28 | 28 | 10 | 10 | 21 | 21 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 155 | 45 | 0 | 882 | 0 | 0 | 0 | 0 | 45 | 882 | 50 | 105 | 0 | 0 | [48 empty] | 0
TRI | 2222 |  | Trinity County | RIP | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | [10 empty] | 150 | [37 empty] | 13000000855 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 455264 |  | Kettenpom Creek Bridge HBRR Replacement | Local HBRR | 116 | 12 | 600 | 0 | 0 | 0 | 0 | 0 | 12 | 600 | 40 | 76 | 0 | 0 |  | 12 | [8 empty] | 600 | [5 empty] | 40 | [7 empty] | 76 | [23 empty] | 0 | [5 empty] | 424 | 424 | 12 | 12 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 1800 | 1800 | 40 | 40 | 76 | 76 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CO) | 29 | 3 | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 10 | 19 | 0 | 0 |  | 3 | [8 empty] | 8 | [5 empty] | 10 | [7 empty] | 19 | [23 empty] | 0 | [5 empty] | 106 | 106 | 3 | 3 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 24 | 24 | 10 | 10 | 19 | 19 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 145 | 15 | 758 | 0 | 0 | 0 | 0 | 0 | 15 | 758 | 50 | 95 | 0 | 0 | [48 empty] | 0
TRI | 2224 |  | Trinity County | RIP | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | [12 empty] | 150 | [35 empty] | 13000000856 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 455384 |  | Van Horn Creek Bridge HBRR Replace | Local HBRR | 136 | 14 | 0 | 0 | 708 | 0 | 0 | 0 | 14 | 708 | 40 | 96 | 0 | 0 |  | 14 | [10 empty] | 708 |  |  |  | 40 | [7 empty] | 96 | [23 empty] | 0 | [5 empty] | 504 | 504 | 14 | 14 | 0 | 0 | 0 | 0 | 1416 | 1416 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 28 | 3540 | 3540 | 40 | 40 | 96 | 96 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | Loc Funds (CO) | 34 | 3 | 0 | 0 | 27 | 0 | 0 | 0 | 3 | 27 | 10 | 24 | 0 | 0 |  | 3 | [10 empty] | 27 |  |  |  | 10 | [7 empty] | 24 | [23 empty] | 0 | [5 empty] | 126 | 126 | 3 | 3 | 0 | 0 | 0 | 0 | 54 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 135 | 135 | 10 | 10 | 24 | 24 | 0 | 0 | 0 | 0
|  |  |  | TOTAL | 170 | 17 | 0 | 0 | 885 | 0 | 0 | 0 | 17 | 885 | 50 | 120 | 0 | 0 | [48 empty] | 0
TRI | 2276 |  | Trinity County | RIP | 0 | 0 | 25 | 65 | 1030 | 0 | 0 | 0 | 65 | 1030 | 0 | 25 | 0 | 0 |  |  |  | 65 | [8 empty] | 1030 | [13 empty] | 25 | [21 empty] | 13000001130 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 100 | 100 | 65 | 65 | 2060 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 260 | 260 | 5150 | 5150 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 0
|  |  | Deerlick Springs Rd. Reconstruction | Loc Funds (CO) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | [17 empty] | 5 | [30 empty] | 0 | [5 empty] | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 5 | 25 | 65 | 1030 | 0 | 0 | 0 | 65 | 1030 | 5 | 25 | 0 | 0 | [48 empty] | 0
TRI | 2279 |  | Trinity County | RIP | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | [13 empty] | 2000 | [34 empty] | 13000001133 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Hyampom Road Reconstruction | Federal Disc. | 0 | 500 | 0 | 1250 | 0 | 8550 | 0 | 0 | 50 | 8550 | 500 | 1200 | 0 | 0 |  |  |  | 50 | [9 empty] | 8550 |  |  |  | 500 | [9 empty] | 1200 | [20 empty] | 0 | [5 empty] | 0 | 0 | 1500 | 1500 | 0 | 0 | 4850 | 4850 | 0 | 0 | 17100 | 17100 | 0 | 0 | 0 | 0 | 200 | 200 | 51300 | 51300 | 1000 | 1000 | 4800 | 4800 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 500 | 0 | 1250 | 0 | 10550 | 0 | 0 | 50 | 10550 | 500 | 1200 | 0 | 0 | [48 empty] | 0
TRI | 2066 |  | Trinity County Transportation Commission | RIP | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | [10 empty] | 20 | [37 empty] | 13000000220 | RIP |  |  |  |  | 0 | 0 | 0 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 455814 |  | Planning, Programming and Monitoring | TOTAL | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
TRI | 0320 | 299 | Caltrans | RIP | 160 | 130 | 1413 | 0 | 0 | 0 | 0 | 0 | 0 | 1273 | 160 | 100 | 30 | 140 | [10 empty] | 1273 | [5 empty] | 160 | [8 empty] | 100 | [7 empty] | 30 | [8 empty] | 140 | [5 empty] | 13000000857 | RIP |  |  |  | X | 480 | 480 | 550 | 550 | 3386 | 3386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3819 | 3819 | 160 | 160 | 200 | 200 | 60 | 60 | 420 | 420
| 28853K | 55.7/57.7 | Rocky Point | IIP | 240 | 196 | 2587 | 0 | 0 | 0 | 0 | 0 | 1 | 2377 | 240 | 150 | 45 | 210 |  | 1 | [8 empty] | 2377 | [5 empty] | 240 | [8 empty] | 150 | [7 empty] | 45 | [8 empty] | 210 | [5 empty] | 0 | [5 empty] | 720 | 720 | 826 | 826 | 6014 | 6014 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 7131 | 7131 | 240 | 240 | 300 | 300 | 90 | 90 | 630 | 630
|  | Change Reason ==> |  | TOTAL | 400 | 326 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 3650 | 400 | 250 | 75 | 350 | [48 empty] | 0
TRI | B0166A | 299 | Caltrans | RIP | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | [16 empty] | 150 | [31 empty] | 13000000908 | RIP |  |  |  | X | 450 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0
| 270310 | 72.0/72.3 | Buckhorn Grade - Environmental Only | TOTAL | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | [48 empty] | 0
|  | Change Reason ==> | [64 empty] | 0
TRI | 3122 | 299 | Caltrans | RIP | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | [12 empty] | 400 | [35 empty] | 13000001134 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 39000K | 60.8/61.2 | Steel Bridge | CT Minor Pgm. | 0 | 0 | 37 | 1108 | 0 | 0 | 0 | 0 | 40 | 730 | 37 | 137 | 14 | 187 |  |  |  | 40 | [7 empty] | 730 | [6 empty] | 37 | [8 empty] | 137 | [7 empty] | 14 | [7 empty] | 187 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 111 | 111 | 3240 | 3240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 160 | 2920 | 2920 | 111 | 111 | 548 | 548 | 56 | 56 | 748 | 748
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 37 | 1108 | 400 | 0 | 0 | 0 | 40 | 1130 | 37 | 137 | 14 | 187 | [48 empty] | 0
TRI | 3104 | 299 | Caltrans | RIP | 0 | 0 | 52 | 0 | 373 | 1575 | 0 | 0 | 33 | 1386 | 52 | 316 | 24 | 189 |  |  |  |  | 33 | [8 empty] | 1386 |  |  |  |  | 52 | [9 empty] | 316 | [7 empty] | 24 | [8 empty] | 189 |  |  | 13000001240 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 156 | 156 | 0 | 0 | 1417 | 1417 | 3906 | 3906 | 0 | 0 | 0 | 0 | 165 | 165 | 8316 | 8316 | 156 | 156 | 1580 | 1580 | 120 | 120 | 1134 | 1134
|  | 69.4/70.5 | Sand House Curve | IIP | 0 | 0 | 34 | 0 | 249 | 2399 | 0 | 0 | 22 | 2273 | 34 | 211 | 16 | 126 |  |  |  |  | 22 | [8 empty] | 2273 |  |  |  |  | 34 | [9 empty] | 211 | [7 empty] | 16 | [8 empty] | 126 |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 102 | 102 | 0 | 0 | 946 | 946 | 5302 | 5302 | 0 | 0 | 0 | 0 | 110 | 110 | 13638 | 13638 | 102 | 102 | 1055 | 1055 | 80 | 80 | 756 | 756
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 86 | 0 | 622 | 3974 | 0 | 0 | 55 | 3659 | 86 | 527 | 40 | 315 | [48 empty] | 0
TRI | 3163 | 299 | Trinity County | Othr. State | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | [10 empty] | 54 | [37 empty] | 13000001284 | [5 empty] | 0 | 0 | 0 | 0 | 108 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 162 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0C530K | 51.9/52.4 | Weaverville Pedestrian | RIP | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | [10 empty] | 150 | [37 empty] | 0 | RIP |  |  |  | X | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Change Reason ==> |  | TOTAL | 0 | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 204 | 0 | 0 | 0 | 0 | [48 empty] | 0
|  |  |  | Total RIP | 670 | 1296 | 2425 | 5266 | 7684 | 3575 | 0 | 0
|  |  |  | Total RIP RIP GARVEE Payback | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP AB3090 Reimbursement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total RIP Caltrans Support FY 02/03 and Prior | 310 | 02/03: 130
|  |  |  | Total RIP Caltrans RW Capital FY 02/03 and Prior | 0 | 02/03: 0
|  |  |  | Total RIP Eligible for Reprogramming | 360 | 1166 | 2425 | 5266 | 7684 | 3575 | 0 | 0
[8 empty] | 9217 | 7684 | 3575